## Settings
[7 empty] | Lunch/Tea Break hrs | 0.8
Shift | Category | Start | End | String | Gen Qty | Cont Qty | Net Hrs | Avl hrs | Category | Net Hrs | Type | Size
Shift A | Gen | 7:00 | 15:00 | 07:00 – 15:00 | 0 | 0 | 8 | 7.2 | Gen | 21.6 | 2P | 9
Shift B | Gen | 15:00 | 23:00 | 15:00 – 23:00 | 0 | 0 | 8 | 7.2 | Cont | 22.4 | SEG | 15
Shift C | Gen | 23:00 | 7:00 | 23:00 – 07:00 | 0 | 0 | 8 | 7.2 |  |  | SOL | 17
Shift S1 | Cont | 8:00 | 20:00 | 08:00 – 20:00 | 0 | 0 | 12 | 11.2 |  |  | RW | 20
Shift S2 | Cont | 20:00 | 8:00 | 20:00 – 08:00 | 0 | 0 | 12 | 11.2 |  |  | RW2 | 25
[11 empty] | FLAP | 28
[11 empty] | TUBE | 30
34
42
46
50
54
57
63
70

## Machine_List
Operation | Machine ID | Next PM Date | Dur | Freq | Status | Worker Category | Machine Min ID Limit | Machine Max OD Limit (New) | Compatible Size Range
VTL | VTL-MC-01 | 2026-04-21 | 6 | 4 | Active | General Workman | 100 | 1600 | 9, 15, 17, 20, 25, 28
VTL | VTL-MC-02 | 2027-05-14 | 6 | 4 | Active | General Workman | 600 | 2500 | 20, 25, 28, 30, 34, 42, 46
VTL | VTL-MC-03 | 2026-06-01 | 6 | 4 | Active | General Workman | 800 | 3500 | 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
VTL | VTL-MC-04 | 2027-05-10 | 6 | 4 | Active | General Workman | 1000 | 4500 | 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
SPM | SPM-MC-01 | 2026-09-20 | 6 | 4 | Active | General Workman | 100 | 3500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
SPM | SPM-MC-02 | 2027-03-13 | 6 | 4 | Active | General Workman | 100 | 3500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
SPM | SPM-MC-03 | 2026-03-23 | 6 | 4 | Active | General Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
SPM | SPM-MC-04 | 2026-06-24 | 6 | 4 | Active | General Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
SPM | SPM-MC-05 | 2026-09-06 | 6 | 4 | Active | General Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
SPM | SPM-MC-06 | 2026-06-03 | 6 | 4 | Active | General Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
CARVING | CARVING-MC-01 | 2027-01-31 | 6 | 4 | Active | General Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
CARVING | CARVING-MC-02 | 2026-09-17 | 6 | 4 | Active | General Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
CARVING | CARVING-MC-03 | 2026-10-01 | 6 | 4 | Active | General Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
CARVING | CARVING-MC-04 | 2026-08-03 | 6 | 4 | Active | General Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
CARVING | CARVING-MC-05 | 2026-08-04 | 6 | 4 | Active | General Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
CARVING | CARVING-MC-06 | 2027-01-10 | 6 | 4 | Active | General Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
EDM | EDM-MC-01 | 2026-03-11 | 6 | 4 | Active | General Workman | 100 | 1600 | 9, 15, 17, 20, 25, 28
EDM | EDM-MC-02 | 2026-05-18 | 6 | 4 | Active | General Workman | 100 | 1600 | 9, 15, 17, 20, 25, 28
EDM | EDM-MC-03 | 2026-02-04 | 6 | 4 | Active | General Workman | 100 | 1600 | 9, 15, 17, 20, 25, 28
EDM | EDM-MC-04 | 2026-03-30 | 6 | 4 | Active | General Workman | 100 | 1600 | 9, 15, 17, 20, 25, 28
EDM | EDM-MC-05 | 2026-07-22 | 6 | 4 | Active | General Workman | 100 | 1600 | 9, 15, 17, 20, 25, 28
EDM | EDM-MC-06 | 2026-11-04 | 6 | 4 | Active | General Workman | 100 | 1600 | 9, 15, 17, 20, 25, 28
EDM | EDM-MC-07 | 2026-07-05 | 6 | 4 | Active | General Workman | 100 | 1600 | 9, 15, 17, 20, 25, 28
EDM | EDM-MC-08 | 2026-09-26 | 6 | 4 | Active | General Workman | 100 | 1600 | 9, 15, 17, 20, 25, 28
EDM | EDM-MC-09 | 2026-08-03 | 6 | 4 | Active | General Workman | 300 | 2500 | 15, 17, 20, 25, 28, 30, 34, 42, 46
EDM | EDM-MC-10 | 2027-04-26 | 6 | 4 | Active | General Workman | 300 | 2500 | 15, 17, 20, 25, 28, 30, 34, 42, 46
EDM | EDM-MC-11 | 2026-03-17 | 6 | 4 | Active | General Workman | 300 | 2500 | 15, 17, 20, 25, 28, 30, 34, 42, 46
EDM | EDM-MC-12 | 2026-11-11 | 6 | 4 | Active | General Workman | 300 | 2500 | 15, 17, 20, 25, 28, 30, 34, 42, 46
EDM | EDM-MC-13 | 2026-07-09 | 6 | 4 | Active | General Workman | 300 | 2500 | 15, 17, 20, 25, 28, 30, 34, 42, 46
EDM | EDM-MC-14 | 2027-03-01 | 6 | 4 | Active | General Workman | 300 | 2500 | 15, 17, 20, 25, 28, 30, 34, 42, 46
EDM | EDM-MC-15 | 2026-12-01 | 6 | 4 | Active | General Workman | 300 | 2500 | 15, 17, 20, 25, 28, 30, 34, 42, 46
EDM | EDM-MC-16 | 2026-03-24 | 6 | 4 | Active | General Workman | 800 | 3500 | 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
EDM | EDM-MC-17 | 2027-04-27 | 6 | 4 | Active | General Workman | 800 | 3500 | 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
EDM | EDM-MC-18 | 2026-07-22 | 6 | 4 | Active | General Workman | 800 | 3500 | 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
EDM | EDM-MC-19 | 2026-08-29 | 6 | 4 | Active | General Workman | 800 | 3500 | 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
EDM | EDM-MC-20 | 2026-01-18 | 6 | 4 | Active | General Workman | 800 | 3500 | 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
EDM | EDM-MC-21 | 2027-03-30 | 6 | 4 | Active | General Workman | 800 | 3500 | 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
EDM | EDM-MC-22 | 2026-08-05 | 6 | 4 | Active | General Workman | 800 | 3500 | 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
EDM | EDM-MC-23 | 2026-10-29 | 6 | 4 | Active | General Workman | 1000 | 4500 | 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
EDM | EDM-MC-24 | 2026-03-16 | 6 | 4 | Active | General Workman | 1000 | 4500 | 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
EDM | EDM-MC-25 | 2026-03-17 | 6 | 4 | Active | General Workman | 1000 | 4500 | 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
EDM | EDM-MC-26 | 2026-06-29 | 6 | 4 | Active | General Workman | 1000 | 4500 | 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
EDM | EDM-MC-27 | 2026-06-15 | 6 | 4 | Active | General Workman | 1000 | 4500 | 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
EDM | EDM-MC-28 | 2026-06-09 | 6 | 4 | Active | General Workman | 1000 | 4500 | 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
EDM | EDM-MC-29 | 2027-04-16 | 6 | 4 | Active | General Workman | 1000 | 4500 | 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
EDM | EDM-MC-30 | 2026-03-25 | 6 | 4 | Active | General Workman | 1000 | 4500 | 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
ENG | ENG-MC-01 | 2026-03-09 | 6 | 4 | Active | General Workman | 100 | 2000 | 9, 15, 17, 20, 25, 28, 30, 34
ENG | ENG-MC-02 | 2026-07-27 | 6 | 4 | Active | General Workman | 100 | 2000 | 9, 15, 17, 20, 25, 28, 30, 34
ENG | ENG-MC-03 | 2027-02-15 | 6 | 4 | Active | General Workman | 100 | 2200 | 9, 15, 17, 20, 25, 28, 30, 34, 42
ENG | ENG-MC-04 | 2027-03-04 | 6 | 4 | Active | General Workman | 100 | 2200 | 9, 15, 17, 20, 25, 28, 30, 34, 42
ENG | ENG-MC-05 | 2026-01-27 | 6 | 4 | Active | General Workman | 100 | 2000 | 9, 15, 17, 20, 25, 28, 30, 34
ENG | ENG-MC-06 | 2026-02-21 | 6 | 4 | Active | General Workman | 600 | 3200 | 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63
ENG | ENG-MC-07 | 2026-09-07 | 6 | 4 | Active | General Workman | 600 | 3200 | 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63
ENG | ENG-MC-08 | 2026-12-27 | 6 | 4 | Active | General Workman | 600 | 3200 | 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63
ENG | ENG-MC-09 | 2027-03-25 | 6 | 4 | Active | General Workman | 600 | 3000 | 20, 25, 28, 30, 34, 42, 46, 50, 54, 57
ENG | ENG-MC-10 | 2026-12-21 | 6 | 4 | Active | General Workman | 600 | 3000 | 20, 25, 28, 30, 34, 42, 46, 50, 54, 57
ENG | ENG-MC-11 | 2027-05-10 | 6 | 4 | Active | General Workman | 600 | 3000 | 20, 25, 28, 30, 34, 42, 46, 50, 54, 57
ENG | ENG-MC-12 | 2027-03-08 | 6 | 4 | Active | General Workman | 600 | 4000 | 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
ENG | ENG-MC-13 | 2026-12-15 | 6 | 4 | Active | General Workman | 600 | 4000 | 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
ENG | ENG-MC-14 | 2026-07-16 | 6 | 4 | Active | General Workman | 600 | 4000 | 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
VENT | VENT-MC-01 | 2026-07-27 | 6 | 4 | Active | Contract Workman | 100 | 1600 | 9, 15, 17, 20, 25, 28
VENT | VENT-MC-02 | 2026-06-18 | 6 | 4 | Active | Contract Workman | 100 | 1600 | 9, 15, 17, 20, 25, 28
VENT | VENT-MC-03 | 2026-02-01 | 6 | 4 | Active | Contract Workman | 100 | 1600 | 9, 15, 17, 20, 25, 28
VENT | VENT-MC-04 | 2026-08-21 | 6 | 4 | Active | Contract Workman | 300 | 3500 | 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
VENT | VENT-MC-05 | 2027-01-07 | 6 | 4 | Active | Contract Workman | 300 | 3500 | 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
VENT | VENT-MC-06 | 2026-11-21 | 6 | 4 | Active | Contract Workman | 300 | 3500 | 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
VENT | VENT-MC-07 | 2026-07-31 | 6 | 4 | Active | Contract Workman | 500 | 4000 | 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
VENT | VENT-MC-08 | 2026-04-26 | 6 | 4 | Active | Contract Workman | 500 | 4000 | 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
FID | FID-MC-01 | 2026-03-25 | 6 | 4 | Active | Contract Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
FID | FID-MC-02 | 2026-04-30 | 6 | 4 | Active | Contract Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
FID | FID-MC-03 | 2027-04-06 | 6 | 4 | Active | Contract Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
FID | FID-MC-04 | 2026-10-23 | 6 | 4 | Active | Contract Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
FID | FID-MC-05 | 2027-02-13 | 6 | 4 | Active | Contract Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
FID | FID-MC-06 | 2026-03-07 | 6 | 4 | Active | Contract Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
FID | FID-MC-07 | 2027-01-15 | 6 | 4 | Active | Contract Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
FID | FID-MC-08 | 2026-11-02 | 6 | 4 | Active | Contract Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
FID | FID-MC-09 | 2026-05-23 | 6 | 4 | Active | Contract Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
FID | FID-MC-10 | 2027-04-06 | 6 | 4 | Active | Contract Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
QC | QC-MC-01 | 2027-05-11 | 6 | 4 | Active | General Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
QC | QC-MC-02 | 2026-04-03 | 6 | 4 | Active | General Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
QC | QC-MC-03 | 2026-05-30 | 6 | 4 | Active | General Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
QC | QC-MC-04 | 2026-06-22 | 6 | 4 | Active | General Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
QC | QC-MC-05 | 2026-12-17 | 6 | 4 | Active | General Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70

## Job_Master
Global Start | 2026-04-01 07:00 | [7 empty] | ← Type to override auto date
Job ID | Size | Type | No of Parts | Overall Start | Overall End | Priority | End Month | Status | Due Date | Customer | time axis 2026-04-01 to 2026-05-29
BJ-104 | 28 | 2P | 2 | 2026-04-09 01:40 | 2026-06-22 16:51 | Medium | Apr-2026 | Released | 2026-07-22 16:51 | Alpha Corp
BJ-101 | 42 | SOL | 4 | 2026-04-01 07:00 | 2026-05-28 08:50 | Medium | May-2026 | On Hold | 2026-06-27 08:50 | Beta Ltd
BJ-105 | 28 | RW | 2 | 2026-04-13 10:07 | 2026-06-04 22:40 | Medium | Apr-2026 | Released | 2026-07-04 22:40 | Alpha Corp
BJ-100 | 25 | SEG | 6 | 2026-04-01 07:00 | 2026-04-20 08:09 | Low | Jun-2026 | Released | 2026-05-20 08:09 | Gamma Inc
BJ-102 | 34 | SEG | 6 | 2026-04-03 21:13 | 2026-04-26 15:49 | Medium | Jun-2026 | Cancelled | 2026-05-26 15:49 | Beta Ltd
BJ-103 | 20 | RW | 2 | 2026-04-06 11:27 | 2026-06-03 04:27 | Low | Jun-2026 | Released | 2026-07-03 04:27 | Delta Co
BJ-108 | 70 | RW | 2 | 2026-04-18 12:20 | 2026-06-25 22:38 | High | May-2026 | Released | 2026-07-25 22:38 | Alpha Corp
BJ-106 | 15 | RW | 2 | 2026-04-01 07:00 | 2026-05-30 09:06 | Low | Jun-2026 | On Hold | 2026-06-29 09:06 | Gamma Inc
BJ-109 | 30 | RW | 2 | 2026-04-16 15:53 | 2026-06-06 19:07 | Medium | Jun-2026 | Released | 2026-07-06 19:07 | Beta Ltd
BJ-110 | 17 | 2P | 2 | 2026-04-18 05:40 | 2026-06-08 06:40 | Low | Jun-2026 | Released | 2026-07-08 06:40 | Delta Co
BJ-111 | 25 | RW | 2 | 2026-04-20 13:13 | 2026-06-14 12:21 | Low | Jun-2026 | Released | 2026-07-14 12:21 | Alpha Corp
BJ-107 | 20 | SEG | 6 | 2026-04-15 06:33 | 2026-06-05 14:13 | Low | Jun-2026 | On Hold | 2026-07-05 14:13 | Beta Ltd
BJ-112 | 17 | 2P | 2 | 2026-04-26 09:13 | 2026-06-15 17:14 | Low | Jun-2026 | Released | 2026-07-15 17:14 | Alpha Corp
BJ-114 | 50 | SEG | 6 | 2026-04-21 07:00 | 2026-06-29 04:25 | High | Jul-2026 | Released | 2026-07-29 04:25 | Gamma Inc
BJ-115 | 46 | 2P | 2 | 2026-04-21 15:53 | 2026-08-05 00:47 | High | Jun-2026 | Cancelled | 2026-09-04 00:47 | Beta Ltd
BJ-116 | 54 | 2P | 2 | 2026-04-27 23:00 | 2026-06-20 21:41 | High | Aug-2026 | Released | 2026-07-20 21:41 | Delta Co
BJ-118 | 28 | SOL | 4 | 2026-04-25 13:13 | 2026-07-02 10:11 | Medium | Jun-2026 | Released | 2026-08-01 10:11 | Alpha Corp
BJ-119 | 63 | SOL | 4 | 2026-05-03 03:27 | 2026-06-21 11:01 | High | Aug-2026 | On Hold | 2026-07-21 11:01 | Gamma Inc
BJ-120 | 46 | 2P | 2 | 2026-05-08 07:53 | 2026-09-05 18:50 | High | Jul-2026 | Released | 2026-10-05 18:50 | Beta Ltd
BJ-113 | 9 | SEG | 6 | 2026-04-07 18:33 | 2026-07-29 19:53 | Low | Jun-2026 | Released | 2026-08-28 19:53 | Delta Co
BJ-121 | 57 | RW | 2 | 2026-04-29 19:27 | 2026-07-06 20:51 | High | Sep-2026 | Released | 2026-08-05 20:51 | Alpha Corp
BJ-123 | 46 | RW | 2 | 2026-05-13 14:33 | 2026-09-19 08:43 | High | Jul-2026 | On Hold | 2026-10-19 08:43 | Beta Ltd
BJ-117 | 15 | RW | 2 | 2026-04-26 15:53 | 2026-08-29 15:44 | Low | Jun-2026 | Released | 2026-09-28 15:44 | Alpha Corp
BJ-122 | 54 | SOL | 4 | 2026-05-05 15:27 | 2026-06-22 02:34 | High | Sep-2026 | Released | 2026-07-22 02:34 | Gamma Inc
BJ-124 | 42 | 2P | 2 | 2026-05-04 01:40 | 2026-07-11 05:18 | Medium | Jul-2026 | Cancelled | 2026-08-10 05:18 | Beta Ltd
BJ-126 | 42 | 2P | 2 | 2026-05-07 00:47 | 2026-06-22 18:08 | Medium | Jul-2026 | Released | 2026-07-22 18:08 | Delta Co
BJ-127 | 15 | RW | 2 | 2026-05-11 20:20 | 2026-07-18 19:31 | Low | Jun-2026 | Released | 2026-08-17 19:31 | Alpha Corp
BJ-128 | 46 | 2P | 2 | 2026-05-08 10:07 | 2026-07-12 21:47 | High | Jul-2026 | On Hold | 2026-08-11 21:47 | Gamma Inc
BJ-125 | 25 | SEG | 6 | 2026-05-07 23:00 | 2026-07-15 13:45 | Low | Jul-2026 | Released | 2026-08-14 13:45 | Beta Ltd
BJ-129 | 9 | RW | 2 | 2026-05-15 08:47 | 2026-07-13 08:53 | Low | Jul-2026 | Released | 2026-08-12 08:53 | Delta Co
BJ-130 | 57 | RW | 2 | 2026-05-23 14:33 | 2026-09-26 11:50 | High | Sep-2026 | Released | 2026-10-26 11:50 | Alpha Corp
BJ-133 | 25 | RW | 2 | 2026-05-18 12:20 | 2026-07-15 12:00 | Low | Jul-2026 | On Hold | 2026-08-14 12:00 | Beta Ltd
BJ-131 | 70 | 2P | 2 | 2026-05-16 04:47 | 2026-07-14 20:27 | High | Oct-2026 | Released | 2026-08-13 20:27 | Alpha Corp
BJ-134 | 15 | RW | 2 | 2026-05-19 21:40 | 2026-07-17 01:47 | Low | Jul-2026 | Released | 2026-08-16 01:47 | Gamma Inc
BJ-135 | 28 | 2P | 2 | 2026-06-04 15:27 | 2026-10-24 13:48 | Medium | Jul-2026 | Cancelled | 2026-11-23 13:48 | Beta Ltd
BJ-132 | 57 | SOL | 4 | 2026-05-28 21:13 | 2026-10-03 21:36 | High | Oct-2026 | Released | 2026-11-02 21:36 | Delta Co
BJ-136 | 20 | RW | 2 | 2026-05-22 11:53 | 2026-07-18 20:00 | Low | Jul-2026 | Released | 2026-08-17 20:00 | Alpha Corp
BJ-137 | 34 | RW | 2 | 2026-05-16 02:33 | 2026-07-21 09:45 | Medium | Jul-2026 | On Hold | 2026-08-20 09:45 | Gamma Inc
BJ-140 | 54 | RW | 2 | 2026-06-20 04:47 | 2026-11-04 23:08 | High | Oct-2026 | Released | 2026-12-04 23:08 | Beta Ltd
BJ-138 | 9 | RW | 2 | 2026-06-15 04:47 | 2026-10-30 20:54 | Low | Jul-2026 | Released | 2026-11-29 20:54 | Delta Co
BJ-144 | 63 | RW | 2 | 2026-05-28 10:07 | 2026-07-22 04:00 | High | Nov-2026 | Released | 2026-08-21 04:00 | Alpha Corp
BJ-146 | 20 | RW | 2 | 2026-05-25 13:13 | 2026-08-19 05:53 | Low | Jul-2026 | On Hold | 2026-09-18 05:53 | Beta Ltd
BJ-139 | 15 | RW | 2 | 2026-05-24 08:20 | 2026-07-19 07:07 | Low | Jul-2026 | Released | 2026-08-18 07:07 | Alpha Corp
BJ-141 | 50 | SOL | 4 | 2026-05-25 04:20 | 2026-07-21 01:20 | High | Nov-2026 | Released | 2026-08-20 01:20 | Gamma Inc
BJ-142 | 9 | RW | 2 | 2026-05-27 00:47 | 2026-07-21 16:53 | Low | Jul-2026 | Cancelled | 2026-08-20 16:53 | Beta Ltd
BJ-147 | 34 | SOL | 4 | 2026-05-29 06:07 | 2026-07-26 10:13 | Medium | Aug-2026 | Released | 2026-08-25 10:13 | Delta Co
BJ-150 | 34 | SOL | 4 | 2026-06-06 00:47 | 2026-07-30 16:27 | Medium | Aug-2026 | Released | 2026-08-29 16:27 | Alpha Corp
BJ-151 | 25 | SOL | 4 | 2026-06-08 08:20 | 2026-08-02 04:27 | Low | Jul-2026 | On Hold | 2026-09-01 04:27 | Gamma Inc
BJ-152 | 34 | 2P | 2 | 2026-06-10 15:53 | 2026-08-03 09:20 | Medium | Aug-2026 | Released | 2026-09-02 09:20 | Beta Ltd
BJ-143 | 17 | SOL | 4 | 2026-06-26 00:47 | 2026-11-17 20:39 | Low | Jul-2026 | Released | 2026-12-17 20:39 | Delta Co
BJ-154 | 25 | RW | 2 | 2026-06-13 10:33 | 2026-09-14 11:58 | Low | Jul-2026 | Released | 2026-10-14 11:58 | Alpha Corp
BJ-156 | 25 | 2P | 2 | 2026-07-10 07:00 | 2027-01-10 02:07 | Low | Aug-2026 | On Hold | 2027-02-09 02:07 | Beta Ltd
BJ-145 | 15 | 2P | 2 | 2026-05-19 06:07 | 2026-08-07 16:07 | Low | Aug-2026 | Released | 2026-09-06 16:07 | Alpha Corp
BJ-153 | 34 | SEG | 6 | 2026-06-03 23:53 | 2026-09-11 23:58 | Medium | Sep-2026 | Released | 2026-10-11 23:58 | Gamma Inc
BJ-160 | 34 | 2P | 2 | 2026-06-14 13:13 | 2026-08-04 09:47 | Medium | Sep-2026 | Cancelled | 2026-09-03 09:47 | Beta Ltd
BJ-158 | 54 | 2P | 2 | 2026-06-12 01:13 | 2026-08-03 22:40 | High | Nov-2026 | Released | 2026-09-02 22:40 | Delta Co
BJ-157 | 50 | SEG | 6 | 2026-07-24 04:20 | 2027-01-16 09:13 | High | Jan-2027 | Released | 2027-02-15 09:13 | Alpha Corp
BJ-159 | 54 | RW | 2 | 2026-06-16 14:07 | 2026-09-21 10:38 | High | Jan-2027 | On Hold | 2026-10-21 10:38 | Gamma Inc
BJ-148 | 9 | SEG | 6 | 2026-05-31 20:20 | 2026-08-21 17:53 | Low | Aug-2026 | Released | 2026-09-20 17:53 | Beta Ltd
BJ-161 | 30 | SEG | 6 | 2026-07-29 04:20 | 2027-02-16 07:08 | Medium | Sep-2026 | Released | 2027-03-18 07:08 | Delta Co
BJ-149 | 9 | 2P | 2 | 2026-06-02 21:13 | 2026-07-29 04:53 | Low | Aug-2026 | Released | 2026-08-28 04:53 | Alpha Corp
BJ-163 | 70 | SOL | 4 | 2026-06-15 09:13 | 2026-08-05 12:27 | High | Feb-2027 | On Hold | 2026-09-04 12:27 | Beta Ltd
BJ-164 | 42 | SOL | 4 | 2026-06-17 05:40 | 2026-08-06 12:53 | Medium | Sep-2026 | Released | 2026-09-05 12:53 | Alpha Corp
BJ-168 | 20 | 2P | 2 | 2026-06-21 23:00 | 2026-08-10 12:27 | Low | Aug-2026 | Released | 2026-09-09 12:27 | Gamma Inc
BJ-155 | 17 | RW | 2 | 2026-07-05 07:00 | 2026-11-24 01:32 | Low | Aug-2026 | Cancelled | 2026-12-24 01:32 | Beta Ltd
BJ-167 | 54 | 2P | 2 | 2026-06-18 19:27 | 2026-08-09 07:33 | High | Feb-2027 | Released | 2026-09-08 07:33 | Delta Co
BJ-166 | 50 | SOL | 4 | 2026-08-16 03:27 | 2027-03-05 23:58 | High | Mar-2027 | Released | 2027-04-04 23:58 | Alpha Corp
BJ-162 | 17 | SOL | 4 | 2026-06-24 22:07 | 2026-09-27 13:18 | Low | Aug-2026 | On Hold | 2026-10-27 13:18 | Gamma Inc
BJ-165 | 17 | 2P | 2 | 2026-08-11 03:27 | 2027-02-22 12:01 | Low | Aug-2026 | Released | 2027-03-24 12:01 | Beta Ltd
BJ-169 | 17 | SEG | 6 | 2026-06-23 12:47 | 2026-08-20 01:06 | Low | Aug-2026 | Released | 2026-09-19 01:06 | Delta Co
Formulas:
Overall Start = IF([Job ID]="","",IF(A8="","", VTL_Plan!J8))
Overall Start = IF([Job ID]="","", VTL_Plan!J5)
Overall End = IF([Job ID]="","",IF(A8="","", QC_Plan!M8))
Overall End = IF([Job ID]="","", QC_Plan!M5)
Due Date = IF([Job ID]="","",[Overall End]+30)
Note on J3: AUTO: QC End Date + 30 days buffer. OVERRIDE: Type any date directly in this cell to set customer due date manually. Blank cells use the auto formula. Typed dates override it.

## VTL_Plan
VTL — Monthly Load vs Capacity
[75 empty] | Apr-2026 | May-2026 | Jun-2026 | Jul-2026 | Aug-2026 | Sep-2026 | Oct-2026 | Nov-2026 | Dec-2026 | Jan-2027
Job ID | Size | Type | Parts | Allocated Machine | Worker | PM Date | PM Hrs | Override | Start Date | Unit CT | Total Load | End Date | Shift ¦ Time | Machine Helper (Pick Compatible) | [59 empty] | Load (Hrs) | 3330 | 1678 | 1614 | 1842 | 780 | 828 | 552 | 0 | 0 | 0 | time axis 2026-04-01 to 2026-05-29
BJ-104 | 28 | 2P | 2 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-04-01 07:00 | 28 | 56 | 2026-04-03 21:13 | Shift B | ✅ Machine OK | [59 empty] | Capacity (Hrs) | 2592 | 2678.4 | 2592 | 2678.4 | 2678.4 | 2592 | 2678.4 | 2592 | 2678.4 | 2678.4
BJ-101 | 42 | SOL | 4 | VTL-MC-02 | General Workman | 2027-05-14 | 6 |  | 2026-04-01 07:00 | 42 | 168 | 2026-04-09 01:40 | Shift C | ✅ Machine OK
BJ-105 | 28 | RW | 2 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-04-03 21:13 | 28 | 56 | 2026-04-06 11:27 | Shift A | ✅ Machine OK
BJ-100 | 25 | SEG | 6 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-04-06 11:27 | 25 | 150 | 2026-04-13 10:07 | Shift A | ✅ Machine OK
BJ-102 | 34 | SEG | 6 | VTL-MC-02 | General Workman | 2027-05-14 | 6 |  | 2026-04-09 01:40 | 34 | 204 | 2026-04-18 12:20 | Shift A | ✅ Machine OK
BJ-103 | 20 | RW | 2 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-04-13 10:07 | 20 | 40 | 2026-04-15 06:33 | Shift C | ✅ Machine OK
BJ-108 | 70 | RW | 2 | VTL-MC-03 | General Workman | 2026-06-01 | 6 |  | 2026-04-01 07:00 | 70 | 140 | 2026-04-07 18:33 | Shift B | ✅ Machine OK
BJ-106 | 15 | RW | 2 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-04-15 06:33 | 15 | 30 | 2026-04-16 15:53 | Shift B | ✅ Machine OK
BJ-109 | 30 | RW | 2 | VTL-MC-02 | General Workman | 2027-05-14 | 6 |  | 2026-04-18 12:20 | 30 | 60 | 2026-04-21 07:00 | Shift A | ✅ Machine OK
BJ-110 | 17 | 2P | 2 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-04-16 15:53 | 17 | 34 | 2026-04-18 05:40 | Shift C | ✅ Machine OK
BJ-111 | 25 | RW | 2 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-04-18 05:40 | 25 | 50 | 2026-04-20 13:13 | Shift A | ✅ Machine OK
BJ-107 | 20 | SEG | 6 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-04-20 13:13 | 20 | 120 | 2026-04-26 09:13 | Shift A | ✅ Machine OK
BJ-112 | 17 | 2P | 2 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-04-26 09:13 | 17 | 34 | 2026-04-27 23:00 | Shift C | ✅ Machine OK
BJ-114 | 50 | SEG | 6 | VTL-MC-03 | General Workman | 2026-06-01 | 6 |  | 2026-04-07 18:33 | 50 | 300 | 2026-04-21 15:53 | Shift B | ✅ Machine OK
BJ-115 | 46 | 2P | 2 | VTL-MC-02 | General Workman | 2027-05-14 | 6 |  | 2026-04-21 07:00 | 46 | 92 | 2026-04-25 13:13 | Shift A | ✅ Machine OK
BJ-116 | 54 | 2P | 2 | VTL-MC-03 | General Workman | 2026-06-01 | 6 |  | 2026-04-21 15:53 | 54 | 108 | 2026-04-26 15:53 | Shift B | ✅ Machine OK
BJ-118 | 28 | SOL | 4 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-04-27 23:00 | 28 | 112 | 2026-05-03 03:27 | Shift C | ✅ Machine OK
BJ-119 | 63 | SOL | 4 | VTL-MC-03 | General Workman | 2026-06-01 | 6 |  | 2026-04-26 15:53 | 63 | 252 | 2026-05-08 07:53 | Shift A | ✅ Machine OK
BJ-120 | 46 | 2P | 2 | VTL-MC-02 | General Workman | 2027-05-14 | 6 |  | 2026-04-25 13:13 | 46 | 92 | 2026-04-29 19:27 | Shift B | ✅ Machine OK
BJ-113 | 9 | SEG | 6 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-05-03 03:27 | 9 | 54 | 2026-05-05 15:27 | Shift B | ✅ Machine OK
BJ-121 | 57 | RW | 2 | VTL-MC-03 | General Workman | 2026-06-01 | 6 |  | 2026-05-08 07:53 | 57 | 114 | 2026-05-13 14:33 | Shift A | ✅ Machine OK
BJ-123 | 46 | RW | 2 | VTL-MC-02 | General Workman | 2027-05-14 | 6 |  | 2026-04-29 19:27 | 46 | 92 | 2026-05-04 01:40 | Shift C | ✅ Machine OK
BJ-117 | 15 | RW | 2 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-05-05 15:27 | 15 | 30 | 2026-05-07 00:47 | Shift C | ✅ Machine OK
BJ-122 | 54 | SOL | 4 | VTL-MC-03 | General Workman | 2026-06-01 | 6 |  | 2026-05-13 14:33 | 54 | 216 | 2026-05-23 14:33 | Shift A | ✅ Machine OK
BJ-124 | 42 | 2P | 2 | VTL-MC-02 | General Workman | 2027-05-14 | 6 |  | 2026-05-04 01:40 | 42 | 84 | 2026-05-07 23:00 | Shift C | ✅ Machine OK
BJ-126 | 42 | 2P | 2 | VTL-MC-02 | General Workman | 2027-05-14 | 6 |  | 2026-05-07 23:00 | 42 | 84 | 2026-05-11 20:20 | Shift B | ✅ Machine OK
BJ-127 | 15 | RW | 2 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-05-07 00:47 | 15 | 30 | 2026-05-08 10:07 | Shift A | ✅ Machine OK
BJ-128 | 46 | 2P | 2 | VTL-MC-02 | General Workman | 2027-05-14 | 6 |  | 2026-05-11 20:20 | 46 | 92 | 2026-05-16 02:33 | Shift C | ✅ Machine OK
BJ-125 | 25 | SEG | 6 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-05-08 10:07 | 25 | 150 | 2026-05-15 08:47 | Shift A | ✅ Machine OK
BJ-129 | 9 | RW | 2 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-05-15 08:47 | 9 | 18 | 2026-05-16 04:47 | Shift C | ✅ Machine OK
BJ-130 | 57 | RW | 2 | VTL-MC-03 | General Workman | 2026-06-01 | 6 |  | 2026-05-23 14:33 | 57 | 114 | 2026-05-28 21:13 | Shift B | ✅ Machine OK
BJ-133 | 25 | RW | 2 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-05-16 04:47 | 25 | 50 | 2026-05-18 12:20 | Shift A | ✅ Machine OK
BJ-131 | 70 | 2P | 2 | VTL-MC-03 | General Workman | 2026-06-01 | 6 |  | 2026-05-28 21:13 | 70 | 140 | 2026-06-04 15:27 | Shift B | ✅ Machine OK
BJ-134 | 15 | RW | 2 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-05-18 12:20 | 15 | 30 | 2026-05-19 21:40 | Shift B | ✅ Machine OK
BJ-135 | 28 | 2P | 2 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-05-19 21:40 | 28 | 56 | 2026-05-22 11:53 | Shift A | ✅ Machine OK
BJ-132 | 57 | SOL | 4 | VTL-MC-03 | General Workman | 2026-06-01 | 6 |  | 2026-06-04 15:27 | 57 | 228 | 2026-06-15 04:47 | Shift C | ✅ Machine OK
BJ-136 | 20 | RW | 2 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-05-22 11:53 | 20 | 40 | 2026-05-24 08:20 | Shift A | ✅ Machine OK
BJ-137 | 34 | RW | 2 | VTL-MC-02 | General Workman | 2027-05-14 | 6 |  | 2026-05-16 02:33 | 34 | 68 | 2026-05-19 06:07 | Shift C | ✅ Machine OK
BJ-140 | 54 | RW | 2 | VTL-MC-03 | General Workman | 2026-06-01 | 6 |  | 2026-06-15 04:47 | 54 | 108 | 2026-06-20 04:47 | Shift C | ✅ Machine OK
BJ-138 | 9 | RW | 2 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-05-24 08:20 | 9 | 18 | 2026-05-25 04:20 | Shift C | ✅ Machine OK
BJ-144 | 63 | RW | 2 | VTL-MC-03 | General Workman | 2026-06-01 | 6 |  | 2026-06-20 04:47 | 63 | 126 | 2026-06-26 00:47 | Shift C | ✅ Machine OK
BJ-146 | 20 | RW | 2 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-05-25 04:20 | 20 | 40 | 2026-05-27 00:47 | Shift C | ✅ Machine OK
BJ-139 | 15 | RW | 2 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-05-27 00:47 | 15 | 30 | 2026-05-28 10:07 | Shift A | ✅ Machine OK
BJ-141 | 50 | SOL | 4 | VTL-MC-03 | General Workman | 2026-06-01 | 6 |  | 2026-06-26 00:47 | 50 | 200 | 2026-07-05 07:00 | Shift A | ✅ Machine OK
BJ-142 | 9 | RW | 2 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-05-28 10:07 | 9 | 18 | 2026-05-29 06:07 | Shift C | ✅ Machine OK
BJ-147 | 34 | SOL | 4 | VTL-MC-02 | General Workman | 2027-05-14 | 6 |  | 2026-05-19 06:07 | 34 | 136 | 2026-05-25 13:13 | Shift A | ✅ Machine OK
BJ-150 | 34 | SOL | 4 | VTL-MC-02 | General Workman | 2027-05-14 | 6 |  | 2026-05-25 13:13 | 34 | 136 | 2026-05-31 20:20 | Shift B | ✅ Machine OK
BJ-151 | 25 | SOL | 4 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-05-29 06:07 | 25 | 100 | 2026-06-02 21:13 | Shift B | ✅ Machine OK
BJ-152 | 34 | 2P | 2 | VTL-MC-02 | General Workman | 2027-05-14 | 6 |  | 2026-05-31 20:20 | 34 | 68 | 2026-06-03 23:53 | Shift C | ✅ Machine OK
BJ-143 | 17 | SOL | 4 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-06-02 21:13 | 17 | 68 | 2026-06-06 00:47 | Shift C | ✅ Machine OK
BJ-154 | 25 | RW | 2 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-06-06 00:47 | 25 | 50 | 2026-06-08 08:20 | Shift A | ✅ Machine OK
BJ-156 | 25 | 2P | 2 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-06-08 08:20 | 25 | 50 | 2026-06-10 15:53 | Shift B | ✅ Machine OK
BJ-145 | 15 | 2P | 2 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-06-10 15:53 | 15 | 30 | 2026-06-12 01:13 | Shift C | ✅ Machine OK
BJ-153 | 34 | SEG | 6 | VTL-MC-02 | General Workman | 2027-05-14 | 6 |  | 2026-06-03 23:53 | 34 | 204 | 2026-06-13 10:33 | Shift A | ✅ Machine OK
BJ-160 | 34 | 2P | 2 | VTL-MC-02 | General Workman | 2027-05-14 | 6 |  | 2026-06-13 10:33 | 34 | 68 | 2026-06-16 14:07 | Shift A | ✅ Machine OK
BJ-158 | 54 | 2P | 2 | VTL-MC-03 | General Workman | 2026-06-01 | 6 |  | 2026-07-05 07:00 | 54 | 108 | 2026-07-10 07:00 | Shift A | ✅ Machine OK
BJ-157 | 50 | SEG | 6 | VTL-MC-03 | General Workman | 2026-06-01 | 6 |  | 2026-07-10 07:00 | 50 | 300 | 2026-07-24 04:20 | Shift C | ✅ Machine OK
BJ-159 | 54 | RW | 2 | VTL-MC-03 | General Workman | 2026-06-01 | 6 |  | 2026-07-24 04:20 | 54 | 108 | 2026-07-29 04:20 | Shift C | ✅ Machine OK
BJ-148 | 9 | SEG | 6 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-06-12 01:13 | 9 | 54 | 2026-06-14 13:13 | Shift A | ✅ Machine OK
BJ-161 | 30 | SEG | 6 | VTL-MC-02 | General Workman | 2027-05-14 | 6 |  | 2026-06-16 14:07 | 30 | 180 | 2026-06-24 22:07 | Shift B | ✅ Machine OK
BJ-149 | 9 | 2P | 2 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-06-14 13:13 | 9 | 18 | 2026-06-15 09:13 | Shift A | ✅ Machine OK
BJ-163 | 70 | SOL | 4 | VTL-MC-03 | General Workman | 2026-06-01 | 6 |  | 2026-07-29 04:20 | 70 | 280 | 2026-08-11 03:27 | Shift C | ✅ Machine OK
BJ-164 | 42 | SOL | 4 | VTL-MC-02 | General Workman | 2027-05-14 | 6 |  | 2026-06-24 22:07 | 42 | 168 | 2026-07-02 16:47 | Shift B | ✅ Machine OK
BJ-168 | 20 | 2P | 2 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-06-15 09:13 | 20 | 40 | 2026-06-17 05:40 | Shift C | ✅ Machine OK
BJ-155 | 17 | RW | 2 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-06-17 05:40 | 17 | 34 | 2026-06-18 19:27 | Shift B | ✅ Machine OK
BJ-167 | 54 | 2P | 2 | VTL-MC-03 | General Workman | 2026-06-01 | 6 |  | 2026-08-11 03:27 | 54 | 108 | 2026-08-16 03:27 | Shift C | ✅ Machine OK
BJ-166 | 50 | SOL | 4 | VTL-MC-03 | General Workman | 2026-06-01 | 6 |  | 2026-08-16 03:27 | 50 | 200 | 2026-08-25 09:40 | Shift A | ✅ Machine OK
BJ-162 | 17 | SOL | 4 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-06-18 19:27 | 17 | 68 | 2026-06-21 23:00 | Shift C | ✅ Machine OK
BJ-165 | 17 | 2P | 2 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-06-21 23:00 | 17 | 34 | 2026-06-23 12:47 | Shift A | ✅ Machine OK
BJ-169 | 17 | SEG | 6 | VTL-MC-01 | General Workman | 2026-04-21 | 6 |  | 2026-06-23 12:47 | 17 | 102 | 2026-06-28 06:07 | Shift C | ✅ Machine OK

## SPM_Plan
SPM — Monthly Load vs Capacity
[75 empty] | Apr-2026 | May-2026 | Jun-2026 | Jul-2026 | Aug-2026 | Sep-2026 | Oct-2026 | Nov-2026 | Dec-2026 | Jan-2027
Job ID | Size | Type | Parts | Allocated Machine | Worker | PM Date | PM Hrs | Override | Start Date | Unit CT | Total Load | End Date | Shift ¦ Time | Machine Helper (Pick Compatible) | [59 empty] | Load (Hrs) | 1206 | 1580 | 1320 | 1162 | 1342 | 658 | 670 | 560 | 0 | 0 | time axis 2026-04-01 to 2026-05-29
BJ-104 | 28 | 2P | 2 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-04-03 21:13 | 38 | 76 | 2026-04-07 09:40 | Shift A | ✅ Machine OK | [59 empty] | Capacity (Hrs) | 3888 | 4017.6 | 3888 | 4017.6 | 4017.6 | 3888 | 4017.6 | 3888 | 4017.6 | 4017.6
BJ-101 | 42 | SOL | 4 | SPM-MC-02 | General Workman | 2027-03-13 | 6 |  | 2026-04-09 01:40 | 54 | 216 | 2026-04-19 01:40 | Shift C | ✅ Machine OK
BJ-105 | 28 | RW | 2 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-04-07 09:40 | 29 | 58 | 2026-04-10 02:07 | Shift C | ✅ Machine OK
BJ-100 | 25 | SEG | 6 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-04-13 10:07 | 38 | 228 | 2026-04-23 23:27 | Shift C | ✅ Machine OK
BJ-102 | 34 | SEG | 6 | SPM-MC-02 | General Workman | 2027-03-13 | 6 |  | 2026-04-19 01:40 | 49 | 294 | 2026-05-02 16:20 | Shift B | ✅ Machine OK
BJ-103 | 20 | RW | 2 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-04-23 23:27 | 32 | 64 | 2026-04-26 22:33 | Shift B | ✅ Machine OK
BJ-108 | 70 | RW | 2 | SPM-MC-03 | General Workman | 2026-03-23 | 6 |  | 2026-04-07 18:33 | 100 | 200 | 2026-04-17 00:47 | Shift C | ✅ Machine OK
BJ-106 | 15 | RW | 2 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-04-26 22:33 | 15 | 30 | 2026-04-28 07:53 | Shift A | ✅ Machine OK
BJ-109 | 30 | RW | 2 | SPM-MC-02 | General Workman | 2027-03-13 | 6 |  | 2026-05-02 16:20 | 32 | 64 | 2026-05-05 15:27 | Shift B | ✅ Machine OK
BJ-110 | 17 | 2P | 2 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-04-28 07:53 | 20 | 40 | 2026-04-30 04:20 | Shift C | ✅ Machine OK
BJ-111 | 25 | RW | 2 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-04-30 04:20 | 30 | 60 | 2026-05-02 23:00 | Shift C | ✅ Machine OK
BJ-107 | 20 | SEG | 6 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-05-02 23:00 | 26 | 156 | 2026-05-10 04:20 | Shift C | ✅ Machine OK
BJ-112 | 17 | 2P | 2 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-05-10 04:20 | 20 | 40 | 2026-05-12 00:47 | Shift C | ✅ Machine OK
BJ-114 | 50 | SEG | 6 | SPM-MC-03 | General Workman | 2026-03-23 | 6 |  | 2026-04-21 15:53 | 89 | 534 | 2026-05-16 09:13 | Shift A | ✅ Machine OK
BJ-115 | 46 | 2P | 2 | SPM-MC-02 | General Workman | 2027-03-13 | 6 |  | 2026-05-05 15:27 | 59 | 118 | 2026-05-11 02:33 | Shift C | ✅ Machine OK
BJ-116 | 54 | 2P | 2 | SPM-MC-03 | General Workman | 2026-03-23 | 6 |  | 2026-05-16 09:13 | 100 | 200 | 2026-05-25 15:27 | Shift B | ✅ Machine OK
BJ-118 | 28 | SOL | 4 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-05-12 00:47 | 33 | 132 | 2026-05-18 03:27 | Shift C | ✅ Machine OK
BJ-119 | 63 | SOL | 4 | SPM-MC-03 | General Workman | 2026-03-23 | 6 |  | 2026-05-25 15:27 | 115 | 460 | 2026-06-15 22:33 | Shift B | ✅ Machine OK
BJ-120 | 46 | 2P | 2 | SPM-MC-02 | General Workman | 2027-03-13 | 6 |  | 2026-05-11 02:33 | 59 | 118 | 2026-05-16 13:40 | Shift A | ✅ Machine OK
BJ-113 | 9 | SEG | 6 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-05-18 03:27 | 8 | 48 | 2026-05-20 08:47 | Shift A | ✅ Machine OK
BJ-121 | 57 | RW | 2 | SPM-MC-03 | General Workman | 2026-03-23 | 6 |  | 2026-06-15 22:33 | 108 | 216 | 2026-06-25 22:33 | Shift B | ✅ Machine OK
BJ-123 | 46 | RW | 2 | SPM-MC-02 | General Workman | 2027-03-13 | 6 |  | 2026-05-16 13:40 | 51 | 102 | 2026-05-21 07:00 | Shift A | ✅ Machine OK
BJ-117 | 15 | RW | 2 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-05-20 08:47 | 15 | 30 | 2026-05-21 18:07 | Shift B | ✅ Machine OK
BJ-122 | 54 | SOL | 4 | SPM-MC-03 | General Workman | 2026-03-23 | 6 |  | 2026-06-25 22:33 | 84 | 336 | 2026-07-11 11:53 | Shift A | ✅ Machine OK
BJ-124 | 42 | 2P | 2 | SPM-MC-02 | General Workman | 2027-03-13 | 6 |  | 2026-05-21 07:00 | 48 | 96 | 2026-05-25 17:40 | Shift B | ✅ Machine OK
BJ-126 | 42 | 2P | 2 | SPM-MC-02 | General Workman | 2027-03-13 | 6 |  | 2026-05-25 17:40 | 48 | 96 | 2026-05-30 04:20 | Shift C | ✅ Machine OK
BJ-127 | 15 | RW | 2 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-05-21 18:07 | 15 | 30 | 2026-05-23 03:27 | Shift C | ✅ Machine OK
BJ-128 | 46 | 2P | 2 | SPM-MC-02 | General Workman | 2027-03-13 | 6 |  | 2026-05-30 04:20 | 59 | 118 | 2026-06-04 15:27 | Shift B | ✅ Machine OK
BJ-125 | 25 | SEG | 6 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-05-23 03:27 | 38 | 228 | 2026-06-02 16:47 | Shift B | ✅ Machine OK
BJ-129 | 9 | RW | 2 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-06-02 16:47 | 2 | 4 | 2026-06-02 21:13 | Shift B | ✅ Machine OK
BJ-130 | 57 | RW | 2 | SPM-MC-03 | General Workman | 2026-03-23 | 6 |  | 2026-07-11 11:53 | 108 | 216 | 2026-07-21 11:53 | Shift A | ✅ Machine OK
BJ-133 | 25 | RW | 2 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-06-02 21:13 | 30 | 60 | 2026-06-05 15:53 | Shift B | ✅ Machine OK
BJ-131 | 70 | 2P | 2 | SPM-MC-03 | General Workman | 2026-03-23 | 6 |  | 2026-07-21 11:53 | 115 | 230 | 2026-08-01 03:27 | Shift C | ✅ Machine OK
BJ-134 | 15 | RW | 2 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-06-05 15:53 | 15 | 30 | 2026-06-07 01:13 | Shift C | ✅ Machine OK
BJ-135 | 28 | 2P | 2 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-06-07 01:13 | 38 | 76 | 2026-06-10 13:40 | Shift A | ✅ Machine OK
BJ-132 | 57 | SOL | 4 | SPM-MC-03 | General Workman | 2026-03-23 | 6 |  | 2026-08-01 03:27 | 99 | 396 | 2026-08-19 11:27 | Shift A | ✅ Machine OK
BJ-136 | 20 | RW | 2 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-06-10 13:40 | 32 | 64 | 2026-06-13 12:47 | Shift A | ✅ Machine OK
BJ-137 | 34 | RW | 2 | SPM-MC-02 | General Workman | 2027-03-13 | 6 |  | 2026-06-04 15:27 | 56 | 112 | 2026-06-09 19:53 | Shift B | ✅ Machine OK
BJ-140 | 54 | RW | 2 | SPM-MC-03 | General Workman | 2026-03-23 | 6 |  | 2026-08-19 11:27 | 78 | 156 | 2026-08-26 16:47 | Shift B | ✅ Machine OK
BJ-138 | 9 | RW | 2 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-06-13 12:47 | 2 | 4 | 2026-06-13 17:13 | Shift B | ✅ Machine OK
BJ-144 | 63 | RW | 2 | SPM-MC-03 | General Workman | 2026-03-23 | 6 |  | 2026-08-26 16:47 | 104 | 208 | 2026-09-05 07:53 | Shift A | ✅ Machine OK
BJ-146 | 20 | RW | 2 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-06-13 17:13 | 32 | 64 | 2026-06-16 16:20 | Shift B | ✅ Machine OK
BJ-139 | 15 | RW | 2 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-06-16 16:20 | 15 | 30 | 2026-06-18 01:40 | Shift C | ✅ Machine OK
BJ-141 | 50 | SOL | 4 | SPM-MC-03 | General Workman | 2026-03-23 | 6 |  | 2026-09-05 07:53 | 99 | 396 | 2026-09-23 15:53 | Shift B | ✅ Machine OK
BJ-142 | 9 | RW | 2 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-06-18 01:40 | 2 | 4 | 2026-06-18 06:07 | Shift C | ✅ Machine OK
BJ-147 | 34 | SOL | 4 | SPM-MC-02 | General Workman | 2027-03-13 | 6 |  | 2026-06-09 19:53 | 65 | 260 | 2026-06-21 20:47 | Shift B | ✅ Machine OK
BJ-150 | 34 | SOL | 4 | SPM-MC-02 | General Workman | 2027-03-13 | 6 |  | 2026-06-21 20:47 | 65 | 260 | 2026-07-03 21:40 | Shift B | ✅ Machine OK
BJ-151 | 25 | SOL | 4 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-06-18 06:07 | 27 | 108 | 2026-06-23 06:07 | Shift C | ✅ Machine OK
BJ-152 | 34 | 2P | 2 | SPM-MC-02 | General Workman | 2027-03-13 | 6 |  | 2026-07-03 21:40 | 50 | 100 | 2026-07-08 12:47 | Shift A | ✅ Machine OK
BJ-143 | 17 | SOL | 4 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-06-23 06:07 | 13 | 52 | 2026-06-25 15:53 | Shift B | ✅ Machine OK
BJ-154 | 25 | RW | 2 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-06-25 15:53 | 30 | 60 | 2026-06-28 10:33 | Shift A | ✅ Machine OK
BJ-156 | 25 | 2P | 2 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-06-28 10:33 | 36 | 72 | 2026-07-01 18:33 | Shift B | ✅ Machine OK
BJ-145 | 15 | 2P | 2 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-07-01 18:33 | 19 | 38 | 2026-07-03 12:47 | Shift A | ✅ Machine OK
BJ-153 | 34 | SEG | 6 | SPM-MC-02 | General Workman | 2027-03-13 | 6 |  | 2026-07-08 12:47 | 49 | 294 | 2026-07-22 03:27 | Shift C | ✅ Machine OK
BJ-160 | 34 | 2P | 2 | SPM-MC-02 | General Workman | 2027-03-13 | 6 |  | 2026-07-22 03:27 | 50 | 100 | 2026-07-26 18:33 | Shift B | ✅ Machine OK
BJ-158 | 54 | 2P | 2 | SPM-MC-03 | General Workman | 2026-03-23 | 6 |  | 2026-09-23 15:53 | 100 | 200 | 2026-10-02 22:07 | Shift B | ✅ Machine OK
BJ-157 | 50 | SEG | 6 | SPM-MC-03 | General Workman | 2026-03-23 | 6 |  | 2026-10-02 22:07 | 89 | 534 | 2026-10-27 15:27 | Shift B | ✅ Machine OK
BJ-159 | 54 | RW | 2 | SPM-MC-03 | General Workman | 2026-03-23 | 6 |  | 2026-10-27 15:27 | 78 | 156 | 2026-11-03 20:47 | Shift B | ✅ Machine OK
BJ-148 | 9 | SEG | 6 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-07-03 12:47 | 8 | 48 | 2026-07-05 18:07 | Shift B | ✅ Machine OK
BJ-161 | 30 | SEG | 6 | SPM-MC-02 | General Workman | 2027-03-13 | 6 |  | 2026-07-26 18:33 | 35 | 210 | 2026-08-05 11:53 | Shift A | ✅ Machine OK
BJ-149 | 9 | 2P | 2 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-07-05 18:07 | 6 | 12 | 2026-07-06 07:27 | Shift A | ✅ Machine OK
BJ-163 | 70 | SOL | 4 | SPM-MC-03 | General Workman | 2026-03-23 | 6 |  | 2026-11-03 20:47 | 133 | 532 | 2026-11-28 11:53 | Shift A | ✅ Machine OK
BJ-164 | 42 | SOL | 4 | SPM-MC-02 | General Workman | 2027-03-13 | 6 |  | 2026-08-05 11:53 | 54 | 216 | 2026-08-15 11:53 | Shift A | ✅ Machine OK
BJ-168 | 20 | 2P | 2 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-07-06 07:27 | 31 | 62 | 2026-07-09 04:20 | Shift C | ✅ Machine OK
BJ-155 | 17 | RW | 2 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-07-09 04:20 | 17 | 34 | 2026-07-10 18:07 | Shift B | ✅ Machine OK
BJ-167 | 54 | 2P | 2 | SPM-MC-03 | General Workman | 2026-03-23 | 6 |  | 2026-11-28 11:53 | 100 | 200 | 2026-12-07 18:07 | Shift B | ✅ Machine OK
BJ-166 | 50 | SOL | 4 | SPM-MC-03 | General Workman | 2026-03-23 | 6 |  | 2026-12-07 18:07 | 99 | 396 | 2026-12-26 02:07 | Shift C | ✅ Machine OK
BJ-162 | 17 | SOL | 4 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-07-10 18:07 | 13 | 52 | 2026-07-13 03:53 | Shift C | ✅ Machine OK
BJ-165 | 17 | 2P | 2 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-07-13 03:53 | 20 | 40 | 2026-07-15 00:20 | Shift C | ✅ Machine OK
BJ-169 | 17 | SEG | 6 | SPM-MC-01 | General Workman | 2026-09-20 | 6 |  | 2026-07-15 00:20 | 19 | 114 | 2026-07-20 07:00 | Shift A | ✅ Machine OK

## CARVING_Plan
CARVING — Monthly Load vs Capacity
[75 empty] | Apr-2026 | May-2026 | Jun-2026 | Jul-2026 | Aug-2026 | Sep-2026 | Oct-2026 | Nov-2026 | Dec-2026 | Jan-2027
Job ID | Size | Type | Parts | Allocated Machine | Worker | PM Date | PM Hrs | Override | Start Date | Unit CT | Total Load | End Date | Shift ¦ Time | Machine Helper (Pick Compatible) | [59 empty] | Load (Hrs) | 4672 | 2978 | 972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | time axis 2026-04-01 to 2026-05-29
BJ-104 | 28 | 2P | 2 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-04-01 07:00 | 30 | 60 | 2026-04-04 01:40 | Shift C | ✅ Machine OK | [59 empty] | Capacity (Hrs) | 3888 | 4017.6 | 3888 | 4017.6 | 4017.6 | 3888 | 4017.6 | 3888 | 4017.6 | 4017.6
BJ-101 | 42 | SOL | 4 | CARVING-MC-02 | General Workman | 2026-09-17 | 6 |  | 2026-04-01 07:00 | 43 | 172 | 2026-04-09 06:07 | Shift C | ✅ Machine OK
BJ-105 | 28 | RW | 2 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-04-04 01:40 | 36 | 72 | 2026-04-07 09:40 | Shift A | ✅ Machine OK
BJ-100 | 25 | SEG | 6 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-04-07 09:40 | 27 | 162 | 2026-04-14 21:40 | Shift B | ✅ Machine OK
BJ-102 | 34 | SEG | 6 | CARVING-MC-02 | General Workman | 2026-09-17 | 6 |  | 2026-04-09 06:07 | 39 | 234 | 2026-04-20 02:07 | Shift C | ✅ Machine OK
BJ-103 | 20 | RW | 2 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-04-14 21:40 | 18 | 36 | 2026-04-16 13:40 | Shift A | ✅ Machine OK
BJ-108 | 70 | RW | 2 | CARVING-MC-03 | General Workman | 2026-10-01 | 6 |  | 2026-04-01 07:00 | 96 | 192 | 2026-04-10 04:20 | Shift C | ✅ Machine OK
BJ-106 | 15 | RW | 2 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-04-16 13:40 | 11 | 22 | 2026-04-17 14:07 | Shift A | ✅ Machine OK
BJ-109 | 30 | RW | 2 | CARVING-MC-02 | General Workman | 2026-09-17 | 6 |  | 2026-04-20 02:07 | 41 | 82 | 2026-04-23 21:13 | Shift B | ✅ Machine OK
BJ-110 | 17 | 2P | 2 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-04-17 14:07 | 14 | 28 | 2026-04-18 21:13 | Shift B | ✅ Machine OK
BJ-111 | 25 | RW | 2 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-04-18 21:13 | 30 | 60 | 2026-04-21 15:53 | Shift B | ✅ Machine OK
BJ-107 | 20 | SEG | 6 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-04-21 15:53 | 29 | 174 | 2026-04-29 17:13 | Shift B | ✅ Machine OK
BJ-112 | 17 | 2P | 2 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-04-29 17:13 | 14 | 28 | 2026-05-01 00:20 | Shift C | ✅ Machine OK
BJ-114 | 50 | SEG | 6 | CARVING-MC-03 | General Workman | 2026-10-01 | 6 |  | 2026-04-10 04:20 | 70 | 420 | 2026-04-29 15:00 | Shift B | ✅ Machine OK
BJ-115 | 46 | 2P | 2 | CARVING-MC-02 | General Workman | 2026-09-17 | 6 |  | 2026-04-23 21:13 | 74 | 148 | 2026-04-30 17:40 | Shift B | ✅ Machine OK
BJ-116 | 54 | 2P | 2 | CARVING-MC-03 | General Workman | 2026-10-01 | 6 |  | 2026-04-29 15:00 | 60 | 120 | 2026-05-05 04:20 | Shift C | ✅ Machine OK
BJ-118 | 28 | SOL | 4 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-05-01 00:20 | 46 | 184 | 2026-05-09 12:47 | Shift A | ✅ Machine OK
BJ-119 | 63 | SOL | 4 | CARVING-MC-03 | General Workman | 2026-10-01 | 6 |  | 2026-05-05 04:20 | 95 | 380 | 2026-05-22 18:33 | Shift B | ✅ Machine OK
BJ-120 | 46 | 2P | 2 | CARVING-MC-02 | General Workman | 2026-09-17 | 6 |  | 2026-04-30 17:40 | 74 | 148 | 2026-05-07 14:07 | Shift A | ✅ Machine OK
BJ-113 | 9 | SEG | 6 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-05-09 12:47 | 5 | 30 | 2026-05-10 22:07 | Shift B | ✅ Machine OK
BJ-121 | 57 | RW | 2 | CARVING-MC-03 | General Workman | 2026-10-01 | 6 |  | 2026-05-22 18:33 | 99 | 198 | 2026-05-31 22:33 | Shift B | ✅ Machine OK
BJ-123 | 46 | RW | 2 | CARVING-MC-02 | General Workman | 2026-09-17 | 6 |  | 2026-05-07 14:07 | 52 | 104 | 2026-05-12 09:40 | Shift A | ✅ Machine OK
BJ-117 | 15 | RW | 2 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-05-10 22:07 | 11 | 22 | 2026-05-11 22:33 | Shift B | ✅ Machine OK
BJ-122 | 54 | SOL | 4 | CARVING-MC-03 | General Workman | 2026-10-01 | 6 |  | 2026-05-31 22:33 | 54 | 216 | 2026-06-10 22:33 | Shift B | ✅ Machine OK
BJ-124 | 42 | 2P | 2 | CARVING-MC-02 | General Workman | 2026-09-17 | 6 |  | 2026-05-12 09:40 | 48 | 96 | 2026-05-16 20:20 | Shift B | ✅ Machine OK
BJ-126 | 42 | 2P | 2 | CARVING-MC-02 | General Workman | 2026-09-17 | 6 |  | 2026-05-16 20:20 | 48 | 96 | 2026-05-21 07:00 | Shift A | ✅ Machine OK
BJ-127 | 15 | RW | 2 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-05-11 22:33 | 11 | 22 | 2026-05-12 23:00 | Shift C | ✅ Machine OK
BJ-128 | 46 | 2P | 2 | CARVING-MC-02 | General Workman | 2026-09-17 | 6 |  | 2026-05-21 07:00 | 74 | 148 | 2026-05-28 03:27 | Shift C | ✅ Machine OK
BJ-125 | 25 | SEG | 6 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-05-12 23:00 | 27 | 162 | 2026-05-20 11:00 | Shift A | ✅ Machine OK
BJ-129 | 9 | RW | 2 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-05-20 11:00 | 5 | 10 | 2026-05-20 22:07 | Shift B | ✅ Machine OK
BJ-130 | 57 | RW | 2 | CARVING-MC-03 | General Workman | 2026-10-01 | 6 |  | 2026-06-10 22:33 | 99 | 198 | 2026-06-20 02:33 | Shift C | ✅ Machine OK
BJ-133 | 25 | RW | 2 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-05-20 22:07 | 30 | 60 | 2026-05-23 16:47 | Shift B | ✅ Machine OK
BJ-131 | 70 | 2P | 2 | CARVING-MC-03 | General Workman | 2026-10-01 | 6 |  | 2026-06-20 02:33 | 129 | 258 | 2026-07-02 01:13 | Shift C | ✅ Machine OK
BJ-134 | 15 | RW | 2 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-05-23 16:47 | 11 | 22 | 2026-05-24 17:13 | Shift B | ✅ Machine OK
BJ-135 | 28 | 2P | 2 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-05-24 17:13 | 30 | 60 | 2026-05-27 11:53 | Shift A | ✅ Machine OK
BJ-132 | 57 | SOL | 4 | CARVING-MC-03 | General Workman | 2026-10-01 | 6 |  | 2026-07-02 01:13 | 60 | 240 | 2026-07-13 03:53 | Shift C | ✅ Machine OK
BJ-136 | 20 | RW | 2 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-05-27 11:53 | 18 | 36 | 2026-05-29 03:53 | Shift C | ✅ Machine OK
BJ-137 | 34 | RW | 2 | CARVING-MC-02 | General Workman | 2026-09-17 | 6 |  | 2026-05-28 03:27 | 51 | 102 | 2026-06-01 20:47 | Shift B | ✅ Machine OK
BJ-140 | 54 | RW | 2 | CARVING-MC-03 | General Workman | 2026-10-01 | 6 |  | 2026-07-13 03:53 | 88 | 176 | 2026-07-21 07:27 | Shift A | ✅ Machine OK
BJ-138 | 9 | RW | 2 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-05-29 03:53 | 5 | 10 | 2026-05-29 15:00 | Shift B | ✅ Machine OK
BJ-144 | 63 | RW | 2 | CARVING-MC-03 | General Workman | 2026-10-01 | 6 |  | 2026-07-21 07:27 | 90 | 180 | 2026-07-29 15:27 | Shift B | ✅ Machine OK
BJ-146 | 20 | RW | 2 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-05-29 15:00 | 18 | 36 | 2026-05-31 07:00 | Shift A | ✅ Machine OK
BJ-139 | 15 | RW | 2 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-05-31 07:00 | 11 | 22 | 2026-06-01 07:27 | Shift A | ✅ Machine OK
BJ-141 | 50 | SOL | 4 | CARVING-MC-03 | General Workman | 2026-10-01 | 6 |  | 2026-07-29 15:27 | 49 | 196 | 2026-08-07 17:13 | Shift B | ✅ Machine OK
BJ-142 | 9 | RW | 2 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-06-01 07:27 | 5 | 10 | 2026-06-01 18:33 | Shift B | ✅ Machine OK
BJ-147 | 34 | SOL | 4 | CARVING-MC-02 | General Workman | 2026-09-17 | 6 |  | 2026-06-01 20:47 | 32 | 128 | 2026-06-07 19:00 | Shift B | ✅ Machine OK
BJ-150 | 34 | SOL | 4 | CARVING-MC-02 | General Workman | 2026-09-17 | 6 |  | 2026-06-07 19:00 | 32 | 128 | 2026-06-13 17:13 | Shift B | ✅ Machine OK
BJ-151 | 25 | SOL | 4 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-06-01 18:33 | 26 | 104 | 2026-06-06 14:07 | Shift A | ✅ Machine OK
BJ-152 | 34 | 2P | 2 | CARVING-MC-02 | General Workman | 2026-09-17 | 6 |  | 2026-06-13 17:13 | 48 | 96 | 2026-06-18 03:53 | Shift C | ✅ Machine OK
BJ-143 | 17 | SOL | 4 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-06-06 14:07 | 20 | 80 | 2026-06-10 07:00 | Shift A | ✅ Machine OK
BJ-154 | 25 | RW | 2 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-06-10 07:00 | 30 | 60 | 2026-06-13 01:40 | Shift C | ✅ Machine OK
BJ-156 | 25 | 2P | 2 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-06-13 01:40 | 29 | 58 | 2026-06-15 18:07 | Shift B | ✅ Machine OK
BJ-145 | 15 | 2P | 2 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-06-15 18:07 | 12 | 24 | 2026-06-16 20:47 | Shift B | ✅ Machine OK
BJ-153 | 34 | SEG | 6 | CARVING-MC-02 | General Workman | 2026-09-17 | 6 |  | 2026-06-18 03:53 | 39 | 234 | 2026-06-28 23:53 | Shift C | ✅ Machine OK
BJ-160 | 34 | 2P | 2 | CARVING-MC-02 | General Workman | 2026-09-17 | 6 |  | 2026-06-28 23:53 | 48 | 96 | 2026-07-03 10:33 | Shift A | ✅ Machine OK
BJ-158 | 54 | 2P | 2 | CARVING-MC-03 | General Workman | 2026-10-01 | 6 |  | 2026-08-07 17:13 | 60 | 120 | 2026-08-13 06:33 | Shift C | ✅ Machine OK
BJ-157 | 50 | SEG | 6 | CARVING-MC-03 | General Workman | 2026-10-01 | 6 |  | 2026-08-13 06:33 | 70 | 420 | 2026-09-01 17:13 | Shift B | ✅ Machine OK
BJ-159 | 54 | RW | 2 | CARVING-MC-03 | General Workman | 2026-10-01 | 6 |  | 2026-09-01 17:13 | 88 | 176 | 2026-09-09 20:47 | Shift B | ✅ Machine OK
BJ-148 | 9 | SEG | 6 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-06-16 20:47 | 5 | 30 | 2026-06-18 06:07 | Shift C | ✅ Machine OK
BJ-161 | 30 | SEG | 6 | CARVING-MC-02 | General Workman | 2026-09-17 | 6 |  | 2026-07-03 10:33 | 31 | 186 | 2026-07-12 01:13 | Shift C | ✅ Machine OK
BJ-149 | 9 | 2P | 2 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-06-18 06:07 | 3 | 6 | 2026-06-18 12:47 | Shift A | ✅ Machine OK
BJ-163 | 70 | SOL | 4 | CARVING-MC-03 | General Workman | 2026-10-01 | 6 |  | 2026-09-09 20:47 | 71 | 284 | 2026-09-23 00:20 | Shift C | ✅ Machine OK
BJ-164 | 42 | SOL | 4 | CARVING-MC-02 | General Workman | 2026-09-17 | 6 |  | 2026-07-12 01:13 | 43 | 172 | 2026-07-20 00:20 | Shift C | ✅ Machine OK
BJ-168 | 20 | 2P | 2 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-06-18 12:47 | 24 | 48 | 2026-06-20 18:07 | Shift B | ✅ Machine OK
BJ-155 | 17 | RW | 2 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-06-20 18:07 | 21 | 42 | 2026-06-22 16:47 | Shift B | ✅ Machine OK
BJ-167 | 54 | 2P | 2 | CARVING-MC-03 | General Workman | 2026-10-01 | 6 |  | 2026-09-23 00:20 | 60 | 120 | 2026-09-28 13:40 | Shift A | ✅ Machine OK
BJ-166 | 50 | SOL | 4 | CARVING-MC-03 | General Workman | 2026-10-01 | 6 |  | 2026-09-28 13:40 | 49 | 196 | 2026-10-07 22:07 | Shift B | ✅ Machine OK
BJ-162 | 17 | SOL | 4 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-06-22 16:47 | 20 | 80 | 2026-06-26 09:40 | Shift A | ✅ Machine OK
BJ-165 | 17 | 2P | 2 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-06-26 09:40 | 14 | 28 | 2026-06-27 16:47 | Shift B | ✅ Machine OK
BJ-169 | 17 | SEG | 6 | CARVING-MC-01 | General Workman | 2027-01-31 | 6 |  | 2026-06-27 16:47 | 18 | 108 | 2026-07-02 16:47 | Shift B | ✅ Machine OK

## EDM_Plan
EDM — Monthly Load vs Capacity
[75 empty] | Apr-2026 | May-2026 | Jun-2026 | Jul-2026 | Aug-2026 | Sep-2026 | Oct-2026 | Nov-2026 | Dec-2026 | Jan-2027
Job ID | Size | Type | Parts | Allocated Machine | Worker | PM Date | PM Hrs | Override | Start Date | Unit CT | Total Load | End Date | Shift ¦ Time | Machine Helper (Pick Compatible) | [59 empty] | Load (Hrs) | 676 | 1042 | 1702 | 1804 | 816 | 1540 | 336 | 1428 | 0 | 0 | time axis 2026-04-01 to 2026-05-29
BJ-104 | 28 | 2P | 2 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-04-07 09:40 | 35 | 70 | 2026-04-10 15:27 | Shift B | ✅ Machine OK | [59 empty] | Capacity (Hrs) | 19440 | 20088 | 19440 | 20088 | 20088 | 19440 | 20088 | 19440 | 20088 | 20088
BJ-101 | 42 | SOL | 4 | EDM-MC-09 | General Workman | 2026-08-03 | 6 |  | 2026-04-19 01:40 | 63 | 252 | 2026-04-30 17:40 | Shift B | ✅ Machine OK
BJ-105 | 28 | RW | 2 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-04-10 15:27 | 36 | 72 | 2026-04-13 23:27 | Shift C | ✅ Machine OK
BJ-100 | 25 | SEG | 6 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-04-23 23:27 | 26 | 156 | 2026-05-01 04:47 | Shift C | ✅ Machine OK
BJ-102 | 34 | SEG | 6 | EDM-MC-02 | General Workman | 2026-05-18 | 6 |  | 2026-05-02 16:20 | 48 | 288 | 2026-05-16 00:20 | Shift C | ❌ Sug: EDM-MC-09
BJ-103 | 20 | RW | 2 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-05-01 04:47 | 22 | 44 | 2026-05-03 05:40 | Shift C | ✅ Machine OK
BJ-108 | 70 | RW | 2 | EDM-MC-03 | General Workman | 2026-02-04 | 6 |  | 2026-04-17 00:47 | 115 | 230 | 2026-04-27 16:20 | Shift B | ❌ Sug: EDM-MC-16
BJ-106 | 15 | RW | 2 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-05-03 05:40 | 14 | 28 | 2026-05-04 12:47 | Shift A | ✅ Machine OK
BJ-109 | 30 | RW | 2 | EDM-MC-02 | General Workman | 2026-05-18 | 6 |  | 2026-05-16 00:20 | 30 | 60 | 2026-05-19 01:40 | Shift C | ❌ Sug: EDM-MC-09
BJ-110 | 17 | 2P | 2 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-05-04 12:47 | 12 | 24 | 2026-05-05 15:27 | Shift B | ✅ Machine OK
BJ-111 | 25 | RW | 2 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-05-05 15:27 | 35 | 70 | 2026-05-08 21:13 | Shift B | ✅ Machine OK
BJ-107 | 20 | SEG | 6 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-05-10 04:20 | 17 | 102 | 2026-05-14 21:40 | Shift B | ✅ Machine OK
BJ-112 | 17 | 2P | 2 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-05-14 21:40 | 12 | 24 | 2026-05-16 00:20 | Shift C | ✅ Machine OK
BJ-114 | 50 | SEG | 6 | EDM-MC-03 | General Workman | 2026-02-04 | 6 |  | 2026-05-16 09:13 | 67 | 402 | 2026-06-03 23:53 | Shift C | ❌ Sug: EDM-MC-16
BJ-115 | 46 | 2P | 2 | EDM-MC-02 | General Workman | 2026-05-18 | 6 |  | 2026-05-19 01:40 | 72 | 144 | 2026-05-25 17:40 | Shift B | ❌ Sug: EDM-MC-09
BJ-116 | 54 | 2P | 2 | EDM-MC-03 | General Workman | 2026-02-04 | 6 |  | 2026-06-03 23:53 | 92 | 184 | 2026-06-12 12:20 | Shift A | ❌ Sug: EDM-MC-16
BJ-118 | 28 | SOL | 4 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-05-18 03:27 | 22 | 88 | 2026-05-22 05:13 | Shift C | ✅ Machine OK
BJ-119 | 63 | SOL | 4 | EDM-MC-03 | General Workman | 2026-02-04 | 6 |  | 2026-06-15 22:33 | 84 | 336 | 2026-07-01 11:53 | Shift A | ❌ Sug: EDM-MC-16
BJ-120 | 46 | 2P | 2 | EDM-MC-02 | General Workman | 2026-05-18 | 6 |  | 2026-05-25 17:40 | 72 | 144 | 2026-06-01 09:40 | Shift A | ❌ Sug: EDM-MC-09
BJ-113 | 9 | SEG | 6 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-05-22 05:13 | 7 | 42 | 2026-05-24 03:53 | Shift C | ✅ Machine OK
BJ-121 | 57 | RW | 2 | EDM-MC-03 | General Workman | 2026-02-04 | 6 |  | 2026-07-01 11:53 | 63 | 126 | 2026-07-07 07:53 | Shift A | ❌ Sug: EDM-MC-16
BJ-123 | 46 | RW | 2 | EDM-MC-02 | General Workman | 2026-05-18 | 6 |  | 2026-06-01 09:40 | 62 | 124 | 2026-06-07 03:27 | Shift C | ❌ Sug: EDM-MC-09
BJ-117 | 15 | RW | 2 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-05-24 03:53 | 14 | 28 | 2026-05-25 11:00 | Shift A | ✅ Machine OK
BJ-122 | 54 | SOL | 4 | EDM-MC-03 | General Workman | 2026-02-04 | 6 |  | 2026-07-11 11:53 | 80 | 320 | 2026-07-26 07:27 | Shift A | ❌ Sug: EDM-MC-16
BJ-124 | 42 | 2P | 2 | EDM-MC-02 | General Workman | 2026-05-18 | 6 |  | 2026-06-07 03:27 | 61 | 122 | 2026-06-12 19:00 | Shift B | ❌ Sug: EDM-MC-09
BJ-126 | 42 | 2P | 2 | EDM-MC-02 | General Workman | 2026-05-18 | 6 |  | 2026-06-12 19:00 | 61 | 122 | 2026-06-18 10:33 | Shift A | ❌ Sug: EDM-MC-09
BJ-127 | 15 | RW | 2 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-05-25 11:00 | 14 | 28 | 2026-05-26 18:07 | Shift B | ✅ Machine OK
BJ-128 | 46 | 2P | 2 | EDM-MC-02 | General Workman | 2026-05-18 | 6 |  | 2026-06-18 10:33 | 72 | 144 | 2026-06-25 02:33 | Shift C | ❌ Sug: EDM-MC-09
BJ-125 | 25 | SEG | 6 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-06-02 16:47 | 26 | 156 | 2026-06-09 22:07 | Shift B | ✅ Machine OK
BJ-129 | 9 | RW | 2 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-06-09 22:07 | 2 | 4 | 2026-06-10 02:33 | Shift C | ✅ Machine OK
BJ-130 | 57 | RW | 2 | EDM-MC-03 | General Workman | 2026-02-04 | 6 |  | 2026-07-26 07:27 | 63 | 126 | 2026-08-01 03:27 | Shift C | ❌ Sug: EDM-MC-16
BJ-133 | 25 | RW | 2 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-06-10 02:33 | 35 | 70 | 2026-06-13 08:20 | Shift A | ✅ Machine OK
BJ-131 | 70 | 2P | 2 | EDM-MC-03 | General Workman | 2026-02-04 | 6 |  | 2026-08-01 03:27 | 75 | 150 | 2026-08-08 02:07 | Shift C | ❌ Sug: EDM-MC-16
BJ-134 | 15 | RW | 2 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-06-13 08:20 | 14 | 28 | 2026-06-14 15:27 | Shift B | ✅ Machine OK
BJ-135 | 28 | 2P | 2 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-06-14 15:27 | 35 | 70 | 2026-06-17 21:13 | Shift B | ✅ Machine OK
BJ-132 | 57 | SOL | 4 | EDM-MC-03 | General Workman | 2026-02-04 | 6 |  | 2026-08-19 11:27 | 56 | 224 | 2026-08-29 20:20 | Shift B | ❌ Sug: EDM-MC-16
BJ-136 | 20 | RW | 2 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-06-17 21:13 | 22 | 44 | 2026-06-19 22:07 | Shift B | ✅ Machine OK
BJ-137 | 34 | RW | 2 | EDM-MC-02 | General Workman | 2026-05-18 | 6 |  | 2026-06-25 02:33 | 36 | 72 | 2026-06-28 10:33 | Shift A | ❌ Sug: EDM-MC-09
BJ-140 | 54 | RW | 2 | EDM-MC-03 | General Workman | 2026-02-04 | 6 |  | 2026-08-29 20:20 | 76 | 152 | 2026-09-05 21:13 | Shift B | ❌ Sug: EDM-MC-16
BJ-138 | 9 | RW | 2 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-06-19 22:07 | 2 | 4 | 2026-06-20 02:33 | Shift C | ✅ Machine OK
BJ-144 | 63 | RW | 2 | EDM-MC-03 | General Workman | 2026-02-04 | 6 |  | 2026-09-05 21:13 | 64 | 128 | 2026-09-11 19:27 | Shift B | ❌ Sug: EDM-MC-16
BJ-146 | 20 | RW | 2 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-06-20 02:33 | 22 | 44 | 2026-06-22 03:27 | Shift C | ✅ Machine OK
BJ-139 | 15 | RW | 2 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-06-22 03:27 | 14 | 28 | 2026-06-23 10:33 | Shift A | ✅ Machine OK
BJ-141 | 50 | SOL | 4 | EDM-MC-03 | General Workman | 2026-02-04 | 6 |  | 2026-09-23 15:53 | 49 | 196 | 2026-10-02 17:40 | Shift B | ❌ Sug: EDM-MC-16
BJ-142 | 9 | RW | 2 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-06-23 10:33 | 2 | 4 | 2026-06-23 15:00 | Shift B | ✅ Machine OK
BJ-147 | 34 | SOL | 4 | EDM-MC-02 | General Workman | 2026-05-18 | 6 |  | 2026-06-28 10:33 | 33 | 132 | 2026-07-04 13:13 | Shift A | ❌ Sug: EDM-MC-09
BJ-150 | 34 | SOL | 4 | EDM-MC-02 | General Workman | 2026-05-18 | 6 |  | 2026-07-04 13:13 | 33 | 132 | 2026-07-10 15:53 | Shift B | ❌ Sug: EDM-MC-09
BJ-151 | 25 | SOL | 4 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-06-23 15:00 | 36 | 144 | 2026-06-30 07:00 | Shift A | ✅ Machine OK
BJ-152 | 34 | 2P | 2 | EDM-MC-02 | General Workman | 2026-05-18 | 6 |  | 2026-07-10 15:53 | 54 | 108 | 2026-07-15 15:53 | Shift B | ❌ Sug: EDM-MC-09
BJ-143 | 17 | SOL | 4 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-06-30 07:00 | 11 | 44 | 2026-07-02 07:53 | Shift A | ✅ Machine OK
BJ-154 | 25 | RW | 2 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-07-02 07:53 | 35 | 70 | 2026-07-05 13:40 | Shift A | ✅ Machine OK
BJ-156 | 25 | 2P | 2 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-07-05 13:40 | 24 | 48 | 2026-07-07 19:00 | Shift B | ✅ Machine OK
BJ-145 | 15 | 2P | 2 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-07-07 19:00 | 12 | 24 | 2026-07-08 21:40 | Shift B | ✅ Machine OK
BJ-153 | 34 | SEG | 6 | EDM-MC-02 | General Workman | 2026-05-18 | 6 |  | 2026-07-22 03:27 | 48 | 288 | 2026-08-04 11:27 | Shift A | ❌ Sug: EDM-MC-09
BJ-160 | 34 | 2P | 2 | EDM-MC-02 | General Workman | 2026-05-18 | 6 |  | 2026-08-04 11:27 | 54 | 108 | 2026-08-09 11:27 | Shift A | ❌ Sug: EDM-MC-09
BJ-158 | 54 | 2P | 2 | EDM-MC-03 | General Workman | 2026-02-04 | 6 |  | 2026-10-02 22:07 | 92 | 184 | 2026-10-11 10:33 | Shift A | ❌ Sug: EDM-MC-16
BJ-157 | 50 | SEG | 6 | EDM-MC-03 | General Workman | 2026-02-04 | 6 |  | 2026-10-27 15:27 | 67 | 402 | 2026-11-15 06:07 | Shift C | ❌ Sug: EDM-MC-16
BJ-159 | 54 | RW | 2 | EDM-MC-03 | General Workman | 2026-02-04 | 6 |  | 2026-11-15 06:07 | 76 | 152 | 2026-11-22 07:00 | Shift A | ❌ Sug: EDM-MC-16
BJ-148 | 9 | SEG | 6 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-07-08 21:40 | 7 | 42 | 2026-07-10 20:20 | Shift B | ✅ Machine OK
BJ-161 | 30 | SEG | 6 | EDM-MC-02 | General Workman | 2026-05-18 | 6 |  | 2026-08-09 11:27 | 27 | 162 | 2026-08-16 23:27 | Shift C | ❌ Sug: EDM-MC-09
BJ-149 | 9 | 2P | 2 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-07-10 20:20 | 6 | 12 | 2026-07-11 09:40 | Shift A | ✅ Machine OK
BJ-163 | 70 | SOL | 4 | EDM-MC-03 | General Workman | 2026-02-04 | 6 |  | 2026-11-28 11:53 | 99 | 396 | 2026-12-16 19:53 | Shift B | ❌ Sug: EDM-MC-16
BJ-164 | 42 | SOL | 4 | EDM-MC-02 | General Workman | 2026-05-18 | 6 |  | 2026-08-16 23:27 | 63 | 252 | 2026-08-28 15:27 | Shift B | ❌ Sug: EDM-MC-09
BJ-168 | 20 | 2P | 2 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-07-11 09:40 | 20 | 40 | 2026-07-13 06:07 | Shift C | ✅ Machine OK
BJ-155 | 17 | RW | 2 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-07-13 06:07 | 19 | 38 | 2026-07-15 00:20 | Shift C | ✅ Machine OK
BJ-167 | 54 | 2P | 2 | EDM-MC-03 | General Workman | 2026-02-04 | 6 |  | 2026-12-16 19:53 | 92 | 184 | 2026-12-25 08:20 | Shift A | ❌ Sug: EDM-MC-16
BJ-166 | 50 | SOL | 4 | EDM-MC-03 | General Workman | 2026-02-04 | 6 |  | 2026-12-26 02:07 | 49 | 196 | 2027-01-04 03:53 | Shift C | ❌ Sug: EDM-MC-16
BJ-162 | 17 | SOL | 4 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-07-15 00:20 | 11 | 44 | 2026-07-17 01:13 | Shift C | ✅ Machine OK
BJ-165 | 17 | 2P | 2 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-07-17 01:13 | 12 | 24 | 2026-07-18 03:53 | Shift C | ✅ Machine OK
BJ-169 | 17 | SEG | 6 | EDM-MC-01 | General Workman | 2026-03-11 | 6 |  | 2026-07-20 07:00 | 20 | 120 | 2026-07-25 20:20 | Shift B | ✅ Machine OK

## ENG_Plan
ENG — Monthly Load vs Capacity
[75 empty] | Apr-2026 | May-2026 | Jun-2026 | Jul-2026 | Aug-2026 | Sep-2026 | Oct-2026 | Nov-2026 | Dec-2026 | Jan-2027
Job ID | Size | Type | Parts | Allocated Machine | Worker | PM Date | PM Hrs | Override | Start Date | Unit CT | Total Load | End Date | Shift ¦ Time | Machine Helper (Pick Compatible) | [59 empty] | Load (Hrs) | 278 | 884 | 836 | 1238 | 916 | 1236 | 500 | 730 | 784 | 0 | time axis 2026-04-01 to 2026-05-29
BJ-104 | 28 | 2P | 2 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-04-10 15:27 | 26 | 52 | 2026-04-13 01:13 | Shift C | ✅ Machine OK | [59 empty] | Capacity (Hrs) | 9072 | 9374.4 | 9072 | 9374.4 | 9374.4 | 9072 | 9374.4 | 9072 | 9374.4 | 9374.4
BJ-101 | 42 | SOL | 4 | ENG-MC-02 | General Workman | 2026-07-27 | 6 |  | 2026-04-30 17:40 | 41 | 164 | 2026-05-08 07:53 | Shift A | ❌ Sug: VTL-MC-02
BJ-105 | 28 | RW | 2 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-04-13 23:27 | 48 | 96 | 2026-04-18 10:07 | Shift A | ✅ Machine OK
BJ-100 | 25 | SEG | 6 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-05-01 04:47 | 35 | 210 | 2026-05-10 22:07 | Shift B | ✅ Machine OK
BJ-102 | 34 | SEG | 6 | ENG-MC-02 | General Workman | 2026-07-27 | 6 |  | 2026-05-16 00:20 | 42 | 252 | 2026-05-27 16:20 | Shift B | ✅ Machine OK
BJ-103 | 20 | RW | 2 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-05-10 22:07 | 28 | 56 | 2026-05-13 12:20 | Shift A | ✅ Machine OK
BJ-108 | 70 | RW | 2 | ENG-MC-03 | General Workman | 2027-02-15 | 6 |  | 2026-04-27 16:20 | 99 | 198 | 2026-05-06 20:20 | Shift B | ❌ Sug: VTL-MC-03
BJ-106 | 15 | RW | 2 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-05-13 12:20 | 10 | 20 | 2026-05-14 10:33 | Shift A | ✅ Machine OK
BJ-109 | 30 | RW | 2 | ENG-MC-02 | General Workman | 2026-07-27 | 6 |  | 2026-05-27 16:20 | 49 | 98 | 2026-06-01 05:13 | Shift C | ✅ Machine OK
BJ-110 | 17 | 2P | 2 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-05-14 10:33 | 12 | 24 | 2026-05-15 13:13 | Shift A | ✅ Machine OK
BJ-111 | 25 | RW | 2 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-05-15 13:13 | 39 | 78 | 2026-05-19 03:53 | Shift C | ✅ Machine OK
BJ-107 | 20 | SEG | 6 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-05-19 03:53 | 28 | 168 | 2026-05-26 22:33 | Shift B | ✅ Machine OK
BJ-112 | 17 | 2P | 2 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-05-26 22:33 | 12 | 24 | 2026-05-28 01:13 | Shift C | ✅ Machine OK
BJ-114 | 50 | SEG | 6 | ENG-MC-03 | General Workman | 2027-02-15 | 6 |  | 2026-06-03 23:53 | 57 | 342 | 2026-06-19 19:53 | Shift B | ❌ Sug: VTL-MC-03
BJ-115 | 46 | 2P | 2 | ENG-MC-02 | General Workman | 2026-07-27 | 6 |  | 2026-06-01 05:13 | 64 | 128 | 2026-06-07 03:27 | Shift C | ❌ Sug: VTL-MC-02
BJ-116 | 54 | 2P | 2 | ENG-MC-03 | General Workman | 2027-02-15 | 6 |  | 2026-06-19 19:53 | 66 | 132 | 2026-06-25 22:33 | Shift B | ❌ Sug: VTL-MC-03
BJ-118 | 28 | SOL | 4 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-05-28 01:13 | 32 | 128 | 2026-06-02 23:27 | Shift C | ✅ Machine OK
BJ-119 | 63 | SOL | 4 | ENG-MC-03 | General Workman | 2027-02-15 | 6 |  | 2026-07-01 11:53 | 120 | 480 | 2026-07-23 17:13 | Shift B | ❌ Sug: VTL-MC-03
BJ-120 | 46 | 2P | 2 | ENG-MC-02 | General Workman | 2026-07-27 | 6 |  | 2026-06-07 03:27 | 64 | 128 | 2026-06-13 01:40 | Shift C | ❌ Sug: VTL-MC-02
BJ-113 | 9 | SEG | 6 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-06-02 23:27 | 5 | 30 | 2026-06-04 08:47 | Shift A | ✅ Machine OK
BJ-121 | 57 | RW | 2 | ENG-MC-03 | General Workman | 2027-02-15 | 6 |  | 2026-07-23 17:13 | 94 | 188 | 2026-08-01 10:07 | Shift A | ❌ Sug: VTL-MC-03
BJ-123 | 46 | RW | 2 | ENG-MC-02 | General Workman | 2026-07-27 | 6 |  | 2026-06-13 01:40 | 49 | 98 | 2026-06-17 14:33 | Shift A | ❌ Sug: VTL-MC-02
BJ-117 | 15 | RW | 2 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-06-04 08:47 | 10 | 20 | 2026-06-05 07:00 | Shift A | ✅ Machine OK
BJ-122 | 54 | SOL | 4 | ENG-MC-03 | General Workman | 2027-02-15 | 6 |  | 2026-08-01 10:07 | 87 | 348 | 2026-08-17 12:47 | Shift A | ❌ Sug: VTL-MC-03
BJ-124 | 42 | 2P | 2 | ENG-MC-02 | General Workman | 2026-07-27 | 6 |  | 2026-06-17 14:33 | 64 | 128 | 2026-06-23 12:47 | Shift A | ❌ Sug: VTL-MC-02
BJ-126 | 42 | 2P | 2 | ENG-MC-02 | General Workman | 2026-07-27 | 6 |  | 2026-06-23 12:47 | 64 | 128 | 2026-06-29 11:00 | Shift A | ❌ Sug: VTL-MC-02
BJ-127 | 15 | RW | 2 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-06-05 07:00 | 10 | 20 | 2026-06-06 05:13 | Shift C | ✅ Machine OK
BJ-128 | 46 | 2P | 2 | ENG-MC-02 | General Workman | 2026-07-27 | 6 |  | 2026-06-29 11:00 | 64 | 128 | 2026-07-05 09:13 | Shift A | ❌ Sug: VTL-MC-02
BJ-125 | 25 | SEG | 6 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-06-09 22:07 | 35 | 210 | 2026-06-19 15:27 | Shift B | ✅ Machine OK
BJ-129 | 9 | RW | 2 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-06-19 15:27 | 6 | 12 | 2026-06-20 04:47 | Shift C | ✅ Machine OK
BJ-130 | 57 | RW | 2 | ENG-MC-03 | General Workman | 2027-02-15 | 6 |  | 2026-08-17 12:47 | 94 | 188 | 2026-08-26 05:40 | Shift C | ❌ Sug: VTL-MC-03
BJ-133 | 25 | RW | 2 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-06-20 04:47 | 39 | 78 | 2026-06-23 19:27 | Shift B | ✅ Machine OK
BJ-131 | 70 | 2P | 2 | ENG-MC-03 | General Workman | 2027-02-15 | 6 |  | 2026-08-26 05:40 | 106 | 212 | 2026-09-05 01:13 | Shift C | ❌ Sug: VTL-MC-03
BJ-134 | 15 | RW | 2 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-06-23 19:27 | 10 | 20 | 2026-06-24 17:40 | Shift B | ✅ Machine OK
BJ-135 | 28 | 2P | 2 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-06-24 17:40 | 26 | 52 | 2026-06-27 03:27 | Shift C | ✅ Machine OK
BJ-132 | 57 | SOL | 4 | ENG-MC-03 | General Workman | 2027-02-15 | 6 |  | 2026-09-05 01:13 | 89 | 356 | 2026-09-21 12:47 | Shift A | ❌ Sug: VTL-MC-03
BJ-136 | 20 | RW | 2 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-06-27 03:27 | 28 | 56 | 2026-06-29 17:40 | Shift B | ✅ Machine OK
BJ-137 | 34 | RW | 2 | ENG-MC-02 | General Workman | 2026-07-27 | 6 |  | 2026-07-05 09:13 | 52 | 104 | 2026-07-10 04:47 | Shift C | ✅ Machine OK
BJ-140 | 54 | RW | 2 | ENG-MC-03 | General Workman | 2027-02-15 | 6 |  | 2026-09-21 12:47 | 73 | 146 | 2026-09-28 07:00 | Shift A | ❌ Sug: VTL-MC-03
BJ-138 | 9 | RW | 2 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-06-29 17:40 | 6 | 12 | 2026-06-30 07:00 | Shift A | ✅ Machine OK
BJ-144 | 63 | RW | 2 | ENG-MC-03 | General Workman | 2027-02-15 | 6 |  | 2026-09-28 07:00 | 81 | 162 | 2026-10-05 19:00 | Shift B | ❌ Sug: VTL-MC-03
BJ-146 | 20 | RW | 2 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-06-30 07:00 | 28 | 56 | 2026-07-02 21:13 | Shift B | ✅ Machine OK
BJ-139 | 15 | RW | 2 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-07-02 21:13 | 10 | 20 | 2026-07-03 19:27 | Shift B | ✅ Machine OK
BJ-141 | 50 | SOL | 4 | ENG-MC-03 | General Workman | 2027-02-15 | 6 |  | 2026-10-05 19:00 | 66 | 264 | 2026-10-18 00:20 | Shift C | ❌ Sug: VTL-MC-03
BJ-142 | 9 | RW | 2 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-07-03 19:27 | 6 | 12 | 2026-07-04 08:47 | Shift A | ✅ Machine OK
BJ-147 | 34 | SOL | 4 | ENG-MC-02 | General Workman | 2026-07-27 | 6 |  | 2026-07-10 04:47 | 61 | 244 | 2026-07-21 11:53 | Shift A | ✅ Machine OK
BJ-150 | 34 | SOL | 4 | ENG-MC-02 | General Workman | 2026-07-27 | 6 |  | 2026-07-21 11:53 | 61 | 244 | 2026-08-02 01:40 | Shift C | ✅ Machine OK
BJ-151 | 25 | SOL | 4 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-07-04 08:47 | 30 | 120 | 2026-07-09 22:07 | Shift B | ✅ Machine OK
BJ-152 | 34 | 2P | 2 | ENG-MC-02 | General Workman | 2026-07-27 | 6 |  | 2026-08-02 01:40 | 35 | 70 | 2026-08-05 07:27 | Shift A | ✅ Machine OK
BJ-143 | 17 | SOL | 4 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-07-09 22:07 | 22 | 88 | 2026-07-13 23:53 | Shift C | ✅ Machine OK
BJ-154 | 25 | RW | 2 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-07-13 23:53 | 39 | 78 | 2026-07-17 14:33 | Shift A | ✅ Machine OK
BJ-156 | 25 | 2P | 2 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-07-17 14:33 | 24 | 48 | 2026-07-19 19:53 | Shift B | ✅ Machine OK
BJ-145 | 15 | 2P | 2 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-07-19 19:53 | 16 | 32 | 2026-07-21 07:27 | Shift A | ✅ Machine OK
BJ-153 | 34 | SEG | 6 | ENG-MC-02 | General Workman | 2026-07-27 | 6 |  | 2026-08-05 07:27 | 42 | 252 | 2026-08-16 23:27 | Shift C | ✅ Machine OK
BJ-160 | 34 | 2P | 2 | ENG-MC-02 | General Workman | 2026-07-27 | 6 |  | 2026-08-16 23:27 | 35 | 70 | 2026-08-20 05:13 | Shift C | ✅ Machine OK
BJ-158 | 54 | 2P | 2 | ENG-MC-03 | General Workman | 2027-02-15 | 6 |  | 2026-10-18 00:20 | 66 | 132 | 2026-10-24 03:00 | Shift C | ❌ Sug: VTL-MC-03
BJ-157 | 50 | SEG | 6 | ENG-MC-03 | General Workman | 2027-02-15 | 6 |  | 2026-11-15 06:07 | 57 | 342 | 2026-12-01 02:07 | Shift C | ❌ Sug: VTL-MC-03
BJ-159 | 54 | RW | 2 | ENG-MC-03 | General Workman | 2027-02-15 | 6 |  | 2026-12-01 02:07 | 73 | 146 | 2026-12-07 20:20 | Shift B | ❌ Sug: VTL-MC-03
BJ-148 | 9 | SEG | 6 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-07-21 07:27 | 5 | 30 | 2026-07-22 16:47 | Shift B | ✅ Machine OK
BJ-161 | 30 | SEG | 6 | ENG-MC-02 | General Workman | 2026-07-27 | 6 |  | 2026-08-20 05:13 | 38 | 228 | 2026-08-30 18:33 | Shift B | ✅ Machine OK
BJ-149 | 9 | 2P | 2 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-07-22 16:47 | 4 | 8 | 2026-07-23 01:40 | Shift C | ✅ Machine OK
BJ-163 | 70 | SOL | 4 | ENG-MC-03 | General Workman | 2027-02-15 | 6 |  | 2026-12-16 19:53 | 111 | 444 | 2027-01-06 09:13 | Shift A | ❌ Sug: VTL-MC-03
BJ-164 | 42 | SOL | 4 | ENG-MC-02 | General Workman | 2026-07-27 | 6 |  | 2026-08-30 18:33 | 41 | 164 | 2026-09-07 08:47 | Shift A | ❌ Sug: VTL-MC-02
BJ-168 | 20 | 2P | 2 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-07-23 01:40 | 27 | 54 | 2026-07-25 13:40 | Shift A | ✅ Machine OK
BJ-155 | 17 | RW | 2 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-07-25 13:40 | 22 | 44 | 2026-07-27 14:33 | Shift A | ✅ Machine OK
BJ-167 | 54 | 2P | 2 | ENG-MC-03 | General Workman | 2027-02-15 | 6 |  | 2027-01-06 09:13 | 66 | 132 | 2027-01-12 11:53 | Shift A | ❌ Sug: VTL-MC-03
BJ-166 | 50 | SOL | 4 | ENG-MC-03 | General Workman | 2027-02-15 | 6 |  | 2027-01-12 11:53 | 66 | 264 | 2027-01-24 17:13 | Shift B | ❌ Sug: VTL-MC-03
BJ-162 | 17 | SOL | 4 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-07-27 14:33 | 22 | 88 | 2026-07-31 16:20 | Shift B | ✅ Machine OK
BJ-165 | 17 | 2P | 2 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-07-31 16:20 | 12 | 24 | 2026-08-01 19:00 | Shift B | ✅ Machine OK
BJ-169 | 17 | SEG | 6 | ENG-MC-01 | General Workman | 2026-03-09 | 6 |  | 2026-08-01 19:00 | 20 | 120 | 2026-08-07 08:20 | Shift A | ✅ Machine OK

## VENT_Plan
VENT — Monthly Load vs Capacity
[75 empty] | Apr-2026 | May-2026 | Jun-2026 | Jul-2026 | Aug-2026 | Sep-2026 | Oct-2026 | Nov-2026 | Dec-2026 | Jan-2027
Job ID | Size | Type | Parts | Allocated Machine | Worker | PM Date | PM Hrs | Override | Start Date | Unit CT | Total Load | End Date | Shift ¦ Time | Machine Helper (Pick Compatible) | [59 empty] | Load (Hrs) | 122 | 882 | 460 | 876 | 1354 | 980 | 932 | 512 | 1230 | 0 | time axis 2026-04-01 to 2026-05-29
BJ-104 | 28 | 2P | 2 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-04-13 01:13 | 32 | 64 | 2026-04-15 21:48 | Shift S2 | ✅ Machine OK | [59 empty] | Capacity (Hrs) | 5184 | 5356.8 | 5184 | 5356.8 | 5356.8 | 5184 | 5356.8 | 5184 | 5356.8 | 5356.8
BJ-101 | 42 | SOL | 4 | VENT-MC-02 | Contract Workman | 2026-06-18 | 6 |  | 2026-05-08 07:53 | 37 | 148 | 2026-05-14 22:28 | Shift S2 | ❌ Sug: VTL-MC-02
BJ-105 | 28 | RW | 2 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-04-18 10:07 | 33 | 66 | 2026-04-21 08:50 | Shift S1 | ✅ Machine OK
BJ-100 | 25 | SEG | 6 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-05-10 22:07 | 32 | 192 | 2026-05-19 11:50 | Shift S1 | ✅ Machine OK
BJ-102 | 34 | SEG | 6 | VENT-MC-02 | Contract Workman | 2026-06-18 | 6 |  | 2026-05-27 16:20 | 32 | 192 | 2026-06-05 06:03 | Shift S2 | ❌ Sug: VTL-MC-02
BJ-103 | 20 | RW | 2 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-05-19 11:50 | 23 | 46 | 2026-05-21 13:07 | Shift S1 | ✅ Machine OK
BJ-108 | 70 | RW | 2 | VENT-MC-03 | Contract Workman | 2026-02-01 | 6 |  | 2026-05-06 20:20 | 77 | 154 | 2026-05-13 17:20 | Shift S1 | ❌ Sug: VTL-MC-03
BJ-106 | 15 | RW | 2 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-05-21 13:07 | 7 | 14 | 2026-05-22 04:07 | Shift S2 | ✅ Machine OK
BJ-109 | 30 | RW | 2 | VENT-MC-02 | Contract Workman | 2026-06-18 | 6 |  | 2026-06-05 06:03 | 31 | 62 | 2026-06-08 00:29 | Shift S2 | ❌ Sug: VTL-MC-02
BJ-110 | 17 | 2P | 2 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-05-22 04:07 | 16 | 32 | 2026-05-23 14:24 | Shift S1 | ✅ Machine OK
BJ-111 | 25 | RW | 2 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-05-23 14:24 | 23 | 46 | 2026-05-25 15:41 | Shift S1 | ✅ Machine OK
BJ-107 | 20 | SEG | 6 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-05-26 22:33 | 19 | 114 | 2026-06-01 00:42 | Shift S2 | ✅ Machine OK
BJ-112 | 17 | 2P | 2 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-06-01 00:42 | 16 | 32 | 2026-06-02 10:59 | Shift S1 | ✅ Machine OK
BJ-114 | 50 | SEG | 6 | VENT-MC-03 | Contract Workman | 2026-02-01 | 6 |  | 2026-06-19 19:53 | 53 | 318 | 2026-07-04 00:36 | Shift S2 | ❌ Sug: VTL-MC-03
BJ-115 | 46 | 2P | 2 | VENT-MC-02 | Contract Workman | 2026-06-18 | 6 |  | 2026-06-08 00:29 | 48 | 96 | 2026-06-12 07:20 | Shift S2 | ❌ Sug: VTL-MC-02
BJ-116 | 54 | 2P | 2 | VENT-MC-03 | Contract Workman | 2026-02-01 | 6 |  | 2026-07-04 00:36 | 57 | 114 | 2026-07-09 02:45 | Shift S2 | ❌ Sug: VTL-MC-03
BJ-118 | 28 | SOL | 4 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-06-02 23:27 | 28 | 112 | 2026-06-07 23:27 | Shift S2 | ✅ Machine OK
BJ-119 | 63 | SOL | 4 | VENT-MC-03 | Contract Workman | 2026-02-01 | 6 |  | 2026-07-23 17:13 | 75 | 300 | 2026-08-06 02:39 | Shift S2 | ❌ Sug: VTL-MC-03
BJ-120 | 46 | 2P | 2 | VENT-MC-02 | Contract Workman | 2026-06-18 | 6 |  | 2026-06-13 01:40 | 48 | 96 | 2026-06-17 08:31 | Shift S1 | ❌ Sug: VTL-MC-02
BJ-113 | 9 | SEG | 6 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-06-07 23:27 | 5 | 30 | 2026-06-09 07:35 | Shift S2 | ✅ Machine OK
BJ-121 | 57 | RW | 2 | VENT-MC-03 | Contract Workman | 2026-02-01 | 6 |  | 2026-08-06 02:39 | 53 | 106 | 2026-08-10 20:13 | Shift S2 | ❌ Sug: VTL-MC-03
BJ-123 | 46 | RW | 2 | VENT-MC-02 | Contract Workman | 2026-06-18 | 6 |  | 2026-06-17 14:33 | 66 | 132 | 2026-06-23 18:25 | Shift S1 | ❌ Sug: VTL-MC-02
BJ-117 | 15 | RW | 2 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-06-09 07:35 | 7 | 14 | 2026-06-09 22:35 | Shift S2 | ✅ Machine OK
BJ-122 | 54 | SOL | 4 | VENT-MC-03 | Contract Workman | 2026-02-01 | 6 |  | 2026-08-17 12:47 | 54 | 216 | 2026-08-27 04:12 | Shift S2 | ❌ Sug: VTL-MC-03
BJ-124 | 42 | 2P | 2 | VENT-MC-02 | Contract Workman | 2026-06-18 | 6 |  | 2026-06-23 18:25 | 62 | 124 | 2026-06-29 07:16 | Shift S2 | ❌ Sug: VTL-MC-02
BJ-126 | 42 | 2P | 2 | VENT-MC-02 | Contract Workman | 2026-06-18 | 6 |  | 2026-06-29 11:00 | 62 | 124 | 2026-07-04 23:51 | Shift S2 | ❌ Sug: VTL-MC-02
BJ-127 | 15 | RW | 2 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-06-09 22:35 | 7 | 14 | 2026-06-10 13:35 | Shift S1 | ✅ Machine OK
BJ-128 | 46 | 2P | 2 | VENT-MC-02 | Contract Workman | 2026-06-18 | 6 |  | 2026-07-05 09:13 | 48 | 96 | 2026-07-09 16:05 | Shift S1 | ❌ Sug: VTL-MC-02
BJ-125 | 25 | SEG | 6 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-06-19 15:27 | 32 | 192 | 2026-06-28 05:10 | Shift S2 | ✅ Machine OK
BJ-129 | 9 | RW | 2 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-06-28 05:10 | 2 | 4 | 2026-06-28 09:27 | Shift S1 | ✅ Machine OK
BJ-130 | 57 | RW | 2 | VENT-MC-03 | Contract Workman | 2026-02-01 | 6 |  | 2026-08-27 04:12 | 53 | 106 | 2026-08-31 21:47 | Shift S2 | ❌ Sug: VTL-MC-03
BJ-133 | 25 | RW | 2 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-06-28 09:27 | 23 | 46 | 2026-06-30 10:44 | Shift S1 | ✅ Machine OK
BJ-131 | 70 | 2P | 2 | VENT-MC-03 | Contract Workman | 2026-02-01 | 6 |  | 2026-09-05 01:13 | 90 | 180 | 2026-09-13 02:05 | Shift S2 | ❌ Sug: VTL-MC-03
BJ-134 | 15 | RW | 2 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-06-30 10:44 | 7 | 14 | 2026-07-01 01:44 | Shift S2 | ✅ Machine OK
BJ-135 | 28 | 2P | 2 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-07-01 01:44 | 32 | 64 | 2026-07-03 22:18 | Shift S2 | ✅ Machine OK
BJ-132 | 57 | SOL | 4 | VENT-MC-03 | Contract Workman | 2026-02-01 | 6 |  | 2026-09-21 12:47 | 74 | 296 | 2026-10-04 17:55 | Shift S1 | ❌ Sug: VTL-MC-03
BJ-136 | 20 | RW | 2 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-07-03 22:18 | 23 | 46 | 2026-07-05 23:35 | Shift S2 | ✅ Machine OK
BJ-137 | 34 | RW | 2 | VENT-MC-02 | Contract Workman | 2026-06-18 | 6 |  | 2026-07-10 04:47 | 32 | 64 | 2026-07-13 01:21 | Shift S2 | ❌ Sug: VTL-MC-02
BJ-140 | 54 | RW | 2 | VENT-MC-03 | Contract Workman | 2026-02-01 | 6 |  | 2026-10-04 17:55 | 86 | 172 | 2026-10-12 10:12 | Shift S1 | ❌ Sug: VTL-MC-03
BJ-138 | 9 | RW | 2 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-07-05 23:35 | 2 | 4 | 2026-07-06 03:52 | Shift S2 | ✅ Machine OK
BJ-144 | 63 | RW | 2 | VENT-MC-03 | Contract Workman | 2026-02-01 | 6 |  | 2026-10-12 10:12 | 61 | 122 | 2026-10-17 20:55 | Shift S2 | ❌ Sug: VTL-MC-03
BJ-146 | 20 | RW | 2 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-07-06 03:52 | 23 | 46 | 2026-07-08 05:10 | Shift S2 | ✅ Machine OK
BJ-139 | 15 | RW | 2 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-07-08 05:10 | 7 | 14 | 2026-07-08 20:10 | Shift S2 | ✅ Machine OK
BJ-141 | 50 | SOL | 4 | VENT-MC-03 | Contract Workman | 2026-02-01 | 6 |  | 2026-10-18 00:20 | 53 | 212 | 2026-10-27 11:29 | Shift S1 | ❌ Sug: VTL-MC-03
BJ-142 | 9 | RW | 2 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-07-08 20:10 | 2 | 4 | 2026-07-09 00:27 | Shift S2 | ✅ Machine OK
BJ-147 | 34 | SOL | 4 | VENT-MC-02 | Contract Workman | 2026-06-18 | 6 |  | 2026-07-21 11:53 | 38 | 152 | 2026-07-28 06:45 | Shift S2 | ❌ Sug: VTL-MC-02
BJ-150 | 34 | SOL | 4 | VENT-MC-02 | Contract Workman | 2026-06-18 | 6 |  | 2026-08-02 01:40 | 38 | 152 | 2026-08-08 20:31 | Shift S2 | ❌ Sug: VTL-MC-02
BJ-151 | 25 | SOL | 4 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-07-09 22:07 | 20 | 80 | 2026-07-13 11:50 | Shift S1 | ✅ Machine OK
BJ-152 | 34 | 2P | 2 | VENT-MC-02 | Contract Workman | 2026-06-18 | 6 |  | 2026-08-08 20:31 | 27 | 54 | 2026-08-11 06:23 | Shift S2 | ❌ Sug: VTL-MC-02
BJ-143 | 17 | SOL | 4 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-07-13 23:53 | 15 | 60 | 2026-07-16 16:10 | Shift S1 | ✅ Machine OK
BJ-154 | 25 | RW | 2 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-07-17 14:33 | 23 | 46 | 2026-07-19 15:50 | Shift S1 | ✅ Machine OK
BJ-156 | 25 | 2P | 2 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-07-19 19:53 | 27 | 54 | 2026-07-22 05:45 | Shift S2 | ✅ Machine OK
BJ-145 | 15 | 2P | 2 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-07-22 05:45 | 10 | 20 | 2026-07-23 03:10 | Shift S2 | ✅ Machine OK
BJ-153 | 34 | SEG | 6 | VENT-MC-02 | Contract Workman | 2026-06-18 | 6 |  | 2026-08-16 23:27 | 32 | 192 | 2026-08-25 13:10 | Shift S1 | ❌ Sug: VTL-MC-02
BJ-160 | 34 | 2P | 2 | VENT-MC-02 | Contract Workman | 2026-06-18 | 6 |  | 2026-08-25 13:10 | 27 | 54 | 2026-08-27 23:01 | Shift S2 | ❌ Sug: VTL-MC-02
BJ-158 | 54 | 2P | 2 | VENT-MC-03 | Contract Workman | 2026-02-01 | 6 |  | 2026-10-27 11:29 | 57 | 114 | 2026-11-01 13:37 | Shift S1 | ❌ Sug: VTL-MC-03
BJ-157 | 50 | SEG | 6 | VENT-MC-03 | Contract Workman | 2026-02-01 | 6 |  | 2026-12-01 02:07 | 53 | 318 | 2026-12-15 06:50 | Shift S2 | ❌ Sug: VTL-MC-03
BJ-159 | 54 | RW | 2 | VENT-MC-03 | Contract Workman | 2026-02-01 | 6 |  | 2026-12-15 06:50 | 86 | 172 | 2026-12-22 23:07 | Shift S2 | ❌ Sug: VTL-MC-03
BJ-148 | 9 | SEG | 6 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-07-23 03:10 | 5 | 30 | 2026-07-24 11:19 | Shift S1 | ✅ Machine OK
BJ-161 | 30 | SEG | 6 | VENT-MC-02 | Contract Workman | 2026-06-18 | 6 |  | 2026-08-30 18:33 | 26 | 156 | 2026-09-06 17:42 | Shift S1 | ❌ Sug: VTL-MC-02
BJ-149 | 9 | 2P | 2 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-07-24 11:19 | 5 | 10 | 2026-07-24 22:02 | Shift S2 | ✅ Machine OK
BJ-163 | 70 | SOL | 4 | VENT-MC-03 | Contract Workman | 2026-02-01 | 6 |  | 2027-01-06 09:13 | 86 | 344 | 2027-01-21 17:48 | Shift S1 | ❌ Sug: VTL-MC-03
BJ-164 | 42 | SOL | 4 | VENT-MC-02 | Contract Workman | 2026-06-18 | 6 |  | 2026-09-07 08:47 | 37 | 148 | 2026-09-13 23:21 | Shift S2 | ❌ Sug: VTL-MC-02
BJ-168 | 20 | 2P | 2 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-07-25 13:40 | 18 | 36 | 2026-07-27 10:40 | Shift S1 | ✅ Machine OK
BJ-155 | 17 | RW | 2 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-07-27 14:33 | 19 | 38 | 2026-07-29 07:16 | Shift S2 | ✅ Machine OK
BJ-167 | 54 | 2P | 2 | VENT-MC-03 | Contract Workman | 2026-02-01 | 6 |  | 2027-01-21 17:48 | 57 | 114 | 2027-01-26 19:56 | Shift S1 | ❌ Sug: VTL-MC-03
BJ-166 | 50 | SOL | 4 | VENT-MC-03 | Contract Workman | 2026-02-01 | 6 |  | 2027-01-26 19:56 | 53 | 212 | 2027-02-05 07:05 | Shift S2 | ❌ Sug: VTL-MC-03
BJ-162 | 17 | SOL | 4 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-07-31 16:20 | 15 | 60 | 2026-08-03 08:37 | Shift S1 | ✅ Machine OK
BJ-165 | 17 | 2P | 2 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-08-03 08:37 | 16 | 32 | 2026-08-04 18:54 | Shift S1 | ✅ Machine OK
BJ-169 | 17 | SEG | 6 | VENT-MC-01 | Contract Workman | 2026-07-27 | 6 |  | 2026-08-07 08:20 | 19 | 114 | 2026-08-12 10:29 | Shift S1 | ✅ Machine OK

## FID_Plan
FID — Monthly Load vs Capacity
[75 empty] | Apr-2026 | May-2026 | Jun-2026 | Jul-2026 | Aug-2026 | Sep-2026 | Oct-2026 | Nov-2026 | Dec-2026 | Jan-2027
Job ID | Size | Type | Parts | Allocated Machine | Worker | PM Date | PM Hrs | Override | Start Date | Unit CT | Total Load | End Date | Shift ¦ Time | Machine Helper (Pick Compatible) | [59 empty] | Load (Hrs) | 56 | 544 | 670 | 492 | 1038 | 996 | 1228 | 506 | 410 | 542 | time axis 2026-04-01 to 2026-05-29
BJ-104 | 28 | 2P | 2 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-04-15 21:48 | 32 | 64 | 2026-04-18 18:22 | Shift S1 | ✅ Machine OK | [59 empty] | Capacity (Hrs) | 6480 | 6696 | 6480 | 6696 | 6696 | 6480 | 6696 | 6480 | 6696 | 6696
BJ-101 | 42 | SOL | 4 | FID-MC-02 | Contract Workman | 2026-04-30 | 6 |  | 2026-05-14 22:28 | 41 | 164 | 2026-05-22 06:10 | Shift S2 | ✅ Machine OK
BJ-105 | 28 | RW | 2 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-04-21 08:50 | 24 | 48 | 2026-04-23 12:15 | Shift S1 | ✅ Machine OK
BJ-100 | 25 | SEG | 6 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-05-19 11:50 | 31 | 186 | 2026-05-27 19:07 | Shift S1 | ✅ Machine OK
BJ-102 | 34 | SEG | 6 | FID-MC-02 | Contract Workman | 2026-04-30 | 6 |  | 2026-06-05 06:03 | 33 | 198 | 2026-06-14 02:11 | Shift S2 | ✅ Machine OK
BJ-103 | 20 | RW | 2 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-05-27 19:07 | 15 | 30 | 2026-05-29 03:15 | Shift S2 | ✅ Machine OK
BJ-108 | 70 | RW | 2 | FID-MC-03 | Contract Workman | 2027-04-06 | 6 |  | 2026-05-13 17:20 | 87 | 174 | 2026-05-21 11:46 | Shift S1 | ✅ Machine OK
BJ-106 | 15 | RW | 2 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-05-29 03:15 | 14 | 28 | 2026-05-30 09:15 | Shift S1 | ✅ Machine OK
BJ-109 | 30 | RW | 2 | FID-MC-02 | Contract Workman | 2026-04-30 | 6 |  | 2026-06-14 02:11 | 20 | 40 | 2026-06-15 21:03 | Shift S2 | ✅ Machine OK
BJ-110 | 17 | 2P | 2 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-05-30 09:15 | 17 | 34 | 2026-05-31 21:41 | Shift S2 | ✅ Machine OK
BJ-111 | 25 | RW | 2 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-05-31 21:41 | 18 | 36 | 2026-06-02 12:15 | Shift S1 | ✅ Machine OK
BJ-107 | 20 | SEG | 6 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-06-02 12:15 | 22 | 132 | 2026-06-08 09:41 | Shift S1 | ✅ Machine OK
BJ-112 | 17 | 2P | 2 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-06-08 09:41 | 17 | 34 | 2026-06-09 22:07 | Shift S2 | ✅ Machine OK
BJ-114 | 50 | SEG | 6 | FID-MC-03 | Contract Workman | 2027-04-06 | 6 |  | 2026-07-04 00:36 | 59 | 354 | 2026-07-19 19:53 | Shift S1 | ✅ Machine OK
BJ-115 | 46 | 2P | 2 | FID-MC-02 | Contract Workman | 2026-04-30 | 6 |  | 2026-06-15 21:03 | 35 | 70 | 2026-06-19 00:03 | Shift S2 | ✅ Machine OK
BJ-116 | 54 | 2P | 2 | FID-MC-03 | Contract Workman | 2027-04-06 | 6 |  | 2026-07-19 19:53 | 77 | 154 | 2026-07-26 16:53 | Shift S1 | ✅ Machine OK
BJ-118 | 28 | SOL | 4 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-06-09 22:07 | 23 | 92 | 2026-06-14 00:41 | Shift S2 | ✅ Machine OK
BJ-119 | 63 | SOL | 4 | FID-MC-03 | Contract Workman | 2027-04-06 | 6 |  | 2026-08-06 02:39 | 52 | 208 | 2026-08-15 09:30 | Shift S1 | ✅ Machine OK
BJ-120 | 46 | 2P | 2 | FID-MC-02 | Contract Workman | 2026-04-30 | 6 |  | 2026-06-19 00:03 | 35 | 70 | 2026-06-22 03:03 | Shift S2 | ✅ Machine OK
BJ-113 | 9 | SEG | 6 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-06-14 00:41 | 2 | 12 | 2026-06-14 13:32 | Shift S1 | ✅ Machine OK
BJ-121 | 57 | RW | 2 | FID-MC-03 | Contract Workman | 2027-04-06 | 6 |  | 2026-08-15 09:30 | 84 | 168 | 2026-08-22 21:30 | Shift S2 | ✅ Machine OK
BJ-123 | 46 | RW | 2 | FID-MC-02 | Contract Workman | 2026-04-30 | 6 |  | 2026-06-23 18:25 | 35 | 70 | 2026-06-26 21:25 | Shift S2 | ✅ Machine OK
BJ-117 | 15 | RW | 2 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-06-14 13:32 | 14 | 28 | 2026-06-15 19:32 | Shift S1 | ✅ Machine OK
BJ-122 | 54 | SOL | 4 | FID-MC-03 | Contract Workman | 2027-04-06 | 6 |  | 2026-08-27 04:12 | 78 | 312 | 2026-09-10 02:30 | Shift S2 | ✅ Machine OK
BJ-124 | 42 | 2P | 2 | FID-MC-02 | Contract Workman | 2026-04-30 | 6 |  | 2026-06-29 07:16 | 51 | 102 | 2026-07-03 20:33 | Shift S2 | ✅ Machine OK
BJ-126 | 42 | 2P | 2 | FID-MC-02 | Contract Workman | 2026-04-30 | 6 |  | 2026-07-04 23:51 | 51 | 102 | 2026-07-09 13:09 | Shift S1 | ✅ Machine OK
BJ-127 | 15 | RW | 2 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-06-15 19:32 | 14 | 28 | 2026-06-17 01:32 | Shift S2 | ✅ Machine OK
BJ-128 | 46 | 2P | 2 | FID-MC-02 | Contract Workman | 2026-04-30 | 6 |  | 2026-07-09 16:05 | 35 | 70 | 2026-07-12 19:05 | Shift S1 | ✅ Machine OK
BJ-125 | 25 | SEG | 6 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-06-28 05:10 | 31 | 186 | 2026-07-06 12:27 | Shift S1 | ✅ Machine OK
BJ-129 | 9 | RW | 2 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-07-06 12:27 | 6 | 12 | 2026-07-07 01:18 | Shift S2 | ✅ Machine OK
BJ-130 | 57 | RW | 2 | FID-MC-03 | Contract Workman | 2027-04-06 | 6 |  | 2026-09-10 02:30 | 84 | 168 | 2026-09-17 14:30 | Shift S1 | ✅ Machine OK
BJ-133 | 25 | RW | 2 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-07-07 01:18 | 18 | 36 | 2026-07-08 15:52 | Shift S1 | ✅ Machine OK
BJ-131 | 70 | 2P | 2 | FID-MC-03 | Contract Workman | 2027-04-06 | 6 |  | 2026-09-17 14:30 | 70 | 140 | 2026-09-23 20:30 | Shift S2 | ✅ Machine OK
BJ-134 | 15 | RW | 2 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-07-08 15:52 | 14 | 28 | 2026-07-09 21:52 | Shift S2 | ✅ Machine OK
BJ-135 | 28 | 2P | 2 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-07-09 21:52 | 32 | 64 | 2026-07-12 18:27 | Shift S1 | ✅ Machine OK
BJ-132 | 57 | SOL | 4 | FID-MC-03 | Contract Workman | 2027-04-06 | 6 |  | 2026-10-04 17:55 | 54 | 216 | 2026-10-14 09:21 | Shift S1 | ✅ Machine OK
BJ-136 | 20 | RW | 2 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-07-12 18:27 | 15 | 30 | 2026-07-14 02:35 | Shift S2 | ✅ Machine OK
BJ-137 | 34 | RW | 2 | FID-MC-02 | Contract Workman | 2026-04-30 | 6 |  | 2026-07-13 01:21 | 37 | 74 | 2026-07-16 08:38 | Shift S1 | ✅ Machine OK
BJ-140 | 54 | RW | 2 | FID-MC-03 | Contract Workman | 2027-04-06 | 6 |  | 2026-10-14 09:21 | 54 | 108 | 2026-10-19 05:04 | Shift S2 | ✅ Machine OK
BJ-138 | 9 | RW | 2 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-07-14 02:35 | 6 | 12 | 2026-07-14 15:27 | Shift S1 | ✅ Machine OK
BJ-144 | 63 | RW | 2 | FID-MC-03 | Contract Workman | 2027-04-06 | 6 |  | 2026-10-19 05:04 | 76 | 152 | 2026-10-25 23:55 | Shift S2 | ✅ Machine OK
BJ-146 | 20 | RW | 2 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-07-14 15:27 | 15 | 30 | 2026-07-15 23:35 | Shift S2 | ✅ Machine OK
BJ-139 | 15 | RW | 2 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-07-15 23:35 | 14 | 28 | 2026-07-17 05:35 | Shift S2 | ✅ Machine OK
BJ-141 | 50 | SOL | 4 | FID-MC-03 | Contract Workman | 2027-04-06 | 6 |  | 2026-10-27 11:29 | 71 | 284 | 2026-11-09 03:46 | Shift S2 | ✅ Machine OK
BJ-142 | 9 | RW | 2 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-07-17 05:35 | 6 | 12 | 2026-07-17 18:27 | Shift S1 | ✅ Machine OK
BJ-147 | 34 | SOL | 4 | FID-MC-02 | Contract Workman | 2026-04-30 | 6 |  | 2026-07-28 06:45 | 25 | 100 | 2026-08-01 17:53 | Shift S1 | ✅ Machine OK
BJ-150 | 34 | SOL | 4 | FID-MC-02 | Contract Workman | 2026-04-30 | 6 |  | 2026-08-08 20:31 | 25 | 100 | 2026-08-13 07:40 | Shift S2 | ✅ Machine OK
BJ-151 | 25 | SOL | 4 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-07-17 18:27 | 23 | 92 | 2026-07-21 21:01 | Shift S2 | ✅ Machine OK
BJ-152 | 34 | 2P | 2 | FID-MC-02 | Contract Workman | 2026-04-30 | 6 |  | 2026-08-13 07:40 | 37 | 74 | 2026-08-16 14:57 | Shift S1 | ✅ Machine OK
BJ-143 | 17 | SOL | 4 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-07-21 21:01 | 11 | 44 | 2026-07-23 20:10 | Shift S2 | ✅ Machine OK
BJ-154 | 25 | RW | 2 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-07-23 20:10 | 18 | 36 | 2026-07-25 10:44 | Shift S1 | ✅ Machine OK
BJ-156 | 25 | 2P | 2 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-07-25 10:44 | 24 | 48 | 2026-07-27 14:10 | Shift S1 | ✅ Machine OK
BJ-145 | 15 | 2P | 2 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-07-27 14:10 | 12 | 24 | 2026-07-28 15:52 | Shift S1 | ✅ Machine OK
BJ-153 | 34 | SEG | 6 | FID-MC-02 | Contract Workman | 2026-04-30 | 6 |  | 2026-08-25 13:10 | 33 | 198 | 2026-09-03 09:18 | Shift S1 | ✅ Machine OK
BJ-160 | 34 | 2P | 2 | FID-MC-02 | Contract Workman | 2026-04-30 | 6 |  | 2026-09-03 09:18 | 37 | 74 | 2026-09-06 16:35 | Shift S1 | ✅ Machine OK
BJ-158 | 54 | 2P | 2 | FID-MC-03 | Contract Workman | 2027-04-06 | 6 |  | 2026-11-09 03:46 | 77 | 154 | 2026-11-16 00:46 | Shift S2 | ✅ Machine OK
BJ-157 | 50 | SEG | 6 | FID-MC-03 | Contract Workman | 2027-04-06 | 6 |  | 2026-12-15 06:50 | 59 | 354 | 2026-12-31 02:07 | Shift S2 | ✅ Machine OK
BJ-159 | 54 | RW | 2 | FID-MC-03 | Contract Workman | 2027-04-06 | 6 |  | 2026-12-31 02:07 | 54 | 108 | 2027-01-04 21:50 | Shift S2 | ✅ Machine OK
BJ-148 | 9 | SEG | 6 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-07-28 15:52 | 2 | 12 | 2026-07-29 04:44 | Shift S2 | ✅ Machine OK
BJ-161 | 30 | SEG | 6 | FID-MC-02 | Contract Workman | 2026-04-30 | 6 |  | 2026-09-06 17:42 | 27 | 162 | 2026-09-13 23:16 | Shift S2 | ✅ Machine OK
BJ-149 | 9 | 2P | 2 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-07-29 04:44 | 1 | 2 | 2026-07-29 06:52 | Shift S2 | ✅ Machine OK
BJ-163 | 70 | SOL | 4 | FID-MC-03 | Contract Workman | 2027-04-06 | 6 |  | 2027-01-21 17:48 | 84 | 336 | 2027-02-05 17:48 | Shift S1 | ✅ Machine OK
BJ-164 | 42 | SOL | 4 | FID-MC-02 | Contract Workman | 2026-04-30 | 6 |  | 2026-09-13 23:21 | 41 | 164 | 2026-09-21 07:04 | Shift S2 | ✅ Machine OK
BJ-168 | 20 | 2P | 2 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-07-29 06:52 | 14 | 28 | 2026-07-30 12:52 | Shift S1 | ✅ Machine OK
BJ-155 | 17 | RW | 2 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-07-30 12:52 | 11 | 22 | 2026-07-31 12:27 | Shift S1 | ✅ Machine OK
BJ-167 | 54 | 2P | 2 | FID-MC-03 | Contract Workman | 2027-04-06 | 6 |  | 2027-02-05 17:48 | 77 | 154 | 2027-02-12 14:48 | Shift S1 | ✅ Machine OK
BJ-166 | 50 | SOL | 4 | FID-MC-03 | Contract Workman | 2027-04-06 | 6 |  | 2027-02-12 14:48 | 71 | 284 | 2027-02-25 07:05 | Shift S2 | ✅ Machine OK
BJ-162 | 17 | SOL | 4 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-08-03 08:37 | 11 | 44 | 2026-08-05 07:46 | Shift S2 | ✅ Machine OK
BJ-165 | 17 | 2P | 2 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-08-05 07:46 | 17 | 34 | 2026-08-06 20:11 | Shift S2 | ✅ Machine OK
BJ-169 | 17 | SEG | 6 | FID-MC-01 | Contract Workman | 2026-03-25 | 6 |  | 2026-08-12 10:29 | 17 | 102 | 2026-08-16 23:46 | Shift S2 | ✅ Machine OK

## QC_Plan
QC — Monthly Load vs Capacity
[75 empty] | Apr-2026 | May-2026 | Jun-2026 | Jul-2026 | Aug-2026 | Sep-2026 | Oct-2026 | Nov-2026 | Dec-2026 | Jan-2027
Job ID | Size | Type | Parts | Allocated Machine | Worker | PM Date | PM Hrs | Override | Start Date | Unit CT | Total Load | End Date | Shift ¦ Time | Machine Helper (Pick Compatible) | [59 empty] | Load (Hrs) | 66 | 302 | 554 | 156 | 920 | 654 | 1084 | 564 | 258 | 880 | time axis 2026-04-01 to 2026-05-30
BJ-104 | 28 | 2P | 2 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-04-18 18:22 | 17 | 34 | 2026-04-20 08:09 | Shift A | ✅ Machine OK | 2026-04-18: BJ-104; 2026-04-19: BJ-104 | Capacity (Hrs) | 3240 | 3348 | 3240 | 3348 | 3348 | 3240 | 3348 | 3240 | 3348 | 3348
BJ-101 | 42 | SOL | 4 | QC-MC-02 | General Workman | 2026-04-03 | 6 |  | 2026-05-22 06:10 | 33 | 132 | 2026-05-28 08:50 | Shift A | ✅ Machine OK | 2026-05-22: BJ-101; 2026-05-23: BJ-101; 2026-05-24: BJ-101
BJ-105 | 28 | RW | 2 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-04-23 12:15 | 34 | 68 | 2026-04-26 15:49 | Shift B | ✅ Machine OK | 2026-04-23: BJ-105; 2026-04-24: BJ-105; 2026-04-25: BJ-105
BJ-100 | 25 | SEG | 6 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-05-27 19:07 | 23 | 138 | 2026-06-03 04:27 | Shift C | ✅ Machine OK
BJ-102 | 34 | SEG | 6 | QC-MC-02 | General Workman | 2026-04-03 | 6 |  | 2026-06-14 02:11 | 31 | 186 | 2026-06-22 16:51 | Shift B | ✅ Machine OK
BJ-103 | 20 | RW | 2 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-06-03 04:27 | 19 | 38 | 2026-06-04 22:40 | Shift B | ✅ Machine OK
BJ-108 | 70 | RW | 2 | QC-MC-03 | General Workman | 2026-05-30 | 6 |  | 2026-05-21 11:46 | 96 | 192 | 2026-05-30 09:06 | Shift A | ✅ Machine OK | 2026-05-21: BJ-108; 2026-05-22: BJ-108; 2026-05-23: BJ-108; 2026-05-24: BJ-108
BJ-106 | 15 | RW | 2 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-06-04 22:40 | 7 | 14 | 2026-06-05 14:13 | Shift A | ✅ Machine OK
BJ-109 | 30 | RW | 2 | QC-MC-02 | General Workman | 2026-04-03 | 6 |  | 2026-06-22 16:51 | 35 | 70 | 2026-06-25 22:38 | Shift B | ✅ Machine OK
BJ-110 | 17 | 2P | 2 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-06-05 14:13 | 13 | 26 | 2026-06-06 19:07 | Shift B | ✅ Machine OK
BJ-111 | 25 | RW | 2 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-06-06 19:07 | 16 | 32 | 2026-06-08 06:40 | Shift C | ✅ Machine OK
BJ-107 | 20 | SEG | 6 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-06-08 09:41 | 22 | 132 | 2026-06-14 12:21 | Shift A | ✅ Machine OK
BJ-112 | 17 | 2P | 2 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-06-14 12:21 | 13 | 26 | 2026-06-15 17:14 | Shift B | ✅ Machine OK
BJ-114 | 50 | SEG | 6 | QC-MC-03 | General Workman | 2026-05-30 | 6 |  | 2026-07-19 19:53 | 36 | 216 | 2026-07-29 19:53 | Shift B | ✅ Machine OK
BJ-115 | 46 | 2P | 2 | QC-MC-02 | General Workman | 2026-04-03 | 6 |  | 2026-06-25 22:38 | 35 | 70 | 2026-06-29 04:25 | Shift C | ✅ Machine OK
BJ-116 | 54 | 2P | 2 | QC-MC-03 | General Workman | 2026-05-30 | 6 |  | 2026-07-29 19:53 | 67 | 134 | 2026-08-05 00:47 | Shift C | ✅ Machine OK
BJ-118 | 28 | SOL | 4 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-06-15 17:14 | 28 | 112 | 2026-06-20 21:41 | Shift B | ✅ Machine OK
BJ-119 | 63 | SOL | 4 | QC-MC-03 | General Workman | 2026-05-30 | 6 |  | 2026-08-15 09:30 | 77 | 308 | 2026-08-29 15:44 | Shift B | ✅ Machine OK
BJ-120 | 46 | 2P | 2 | QC-MC-02 | General Workman | 2026-04-03 | 6 |  | 2026-06-29 04:25 | 35 | 70 | 2026-07-02 10:11 | Shift A | ✅ Machine OK
BJ-113 | 9 | SEG | 6 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-06-20 21:41 | 2 | 12 | 2026-06-21 11:01 | Shift A | ✅ Machine OK
BJ-121 | 57 | RW | 2 | QC-MC-03 | General Workman | 2026-05-30 | 6 |  | 2026-08-29 15:44 | 77 | 154 | 2026-09-05 18:50 | Shift B | ✅ Machine OK
BJ-123 | 46 | RW | 2 | QC-MC-02 | General Workman | 2026-04-03 | 6 |  | 2026-07-02 10:11 | 48 | 96 | 2026-07-06 20:51 | Shift B | ✅ Machine OK
BJ-117 | 15 | RW | 2 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-06-21 11:01 | 7 | 14 | 2026-06-22 02:34 | Shift C | ✅ Machine OK
BJ-122 | 54 | SOL | 4 | QC-MC-03 | General Workman | 2026-05-30 | 6 |  | 2026-09-10 02:30 | 50 | 200 | 2026-09-19 08:43 | Shift A | ✅ Machine OK
BJ-124 | 42 | 2P | 2 | QC-MC-02 | General Workman | 2026-04-03 | 6 |  | 2026-07-06 20:51 | 47 | 94 | 2026-07-11 05:18 | Shift C | ✅ Machine OK
BJ-126 | 42 | 2P | 2 | QC-MC-02 | General Workman | 2026-04-03 | 6 |  | 2026-07-11 05:18 | 47 | 94 | 2026-07-15 13:45 | Shift A | ✅ Machine OK
BJ-127 | 15 | RW | 2 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-06-22 02:34 | 7 | 14 | 2026-06-22 18:08 | Shift B | ✅ Machine OK
BJ-128 | 46 | 2P | 2 | QC-MC-02 | General Workman | 2026-04-03 | 6 |  | 2026-07-15 13:45 | 35 | 70 | 2026-07-18 19:31 | Shift B | ✅ Machine OK
BJ-125 | 25 | SEG | 6 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-07-06 12:27 | 23 | 138 | 2026-07-12 21:47 | Shift B | ✅ Machine OK
BJ-129 | 9 | RW | 2 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-07-12 21:47 | 5 | 10 | 2026-07-13 08:53 | Shift A | ✅ Machine OK
BJ-130 | 57 | RW | 2 | QC-MC-03 | General Workman | 2026-05-30 | 6 |  | 2026-09-19 08:43 | 77 | 154 | 2026-09-26 11:50 | Shift A | ✅ Machine OK
BJ-133 | 25 | RW | 2 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-07-13 08:53 | 16 | 32 | 2026-07-14 20:27 | Shift B | ✅ Machine OK
BJ-131 | 70 | 2P | 2 | QC-MC-03 | General Workman | 2026-05-30 | 6 |  | 2026-09-26 11:50 | 80 | 160 | 2026-10-03 21:36 | Shift B | ✅ Machine OK
BJ-134 | 15 | RW | 2 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-07-14 20:27 | 7 | 14 | 2026-07-15 12:00 | Shift A | ✅ Machine OK
BJ-135 | 28 | 2P | 2 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-07-15 12:00 | 17 | 34 | 2026-07-17 01:47 | Shift C | ✅ Machine OK
BJ-132 | 57 | SOL | 4 | QC-MC-03 | General Workman | 2026-05-30 | 6 |  | 2026-10-14 09:21 | 55 | 220 | 2026-10-24 13:48 | Shift A | ✅ Machine OK
BJ-136 | 20 | RW | 2 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-07-17 01:47 | 19 | 38 | 2026-07-18 20:00 | Shift B | ✅ Machine OK
BJ-137 | 34 | RW | 2 | QC-MC-02 | General Workman | 2026-04-03 | 6 |  | 2026-07-18 19:31 | 28 | 56 | 2026-07-21 09:45 | Shift A | ✅ Machine OK
BJ-140 | 54 | RW | 2 | QC-MC-03 | General Workman | 2026-05-30 | 6 |  | 2026-10-24 13:48 | 68 | 136 | 2026-10-30 20:54 | Shift B | ✅ Machine OK
BJ-138 | 9 | RW | 2 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-07-18 20:00 | 5 | 10 | 2026-07-19 07:07 | Shift A | ✅ Machine OK
BJ-144 | 63 | RW | 2 | QC-MC-03 | General Workman | 2026-05-30 | 6 |  | 2026-10-30 20:54 | 55 | 110 | 2026-11-04 23:08 | Shift C | ✅ Machine OK
BJ-146 | 20 | RW | 2 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-07-19 07:07 | 19 | 38 | 2026-07-21 01:20 | Shift C | ✅ Machine OK
BJ-139 | 15 | RW | 2 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-07-21 01:20 | 7 | 14 | 2026-07-21 16:53 | Shift B | ✅ Machine OK
BJ-141 | 50 | SOL | 4 | QC-MC-03 | General Workman | 2026-05-30 | 6 |  | 2026-11-09 03:46 | 47 | 188 | 2026-11-17 20:39 | Shift B | ✅ Machine OK
BJ-142 | 9 | RW | 2 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-07-21 16:53 | 5 | 10 | 2026-07-22 04:00 | Shift C | ✅ Machine OK
BJ-147 | 34 | SOL | 4 | QC-MC-02 | General Workman | 2026-04-03 | 6 |  | 2026-08-01 17:53 | 32 | 128 | 2026-08-07 16:07 | Shift B | ✅ Machine OK
BJ-150 | 34 | SOL | 4 | QC-MC-02 | General Workman | 2026-04-03 | 6 |  | 2026-08-13 07:40 | 32 | 128 | 2026-08-19 05:53 | Shift C | ✅ Machine OK
BJ-151 | 25 | SOL | 4 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-07-22 04:00 | 23 | 92 | 2026-07-26 10:13 | Shift A | ✅ Machine OK
BJ-152 | 34 | 2P | 2 | QC-MC-02 | General Workman | 2026-04-03 | 6 |  | 2026-08-19 05:53 | 27 | 54 | 2026-08-21 17:53 | Shift B | ✅ Machine OK
BJ-143 | 17 | SOL | 4 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-07-26 10:13 | 15 | 60 | 2026-07-29 04:53 | Shift C | ✅ Machine OK
BJ-154 | 25 | RW | 2 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-07-29 04:53 | 16 | 32 | 2026-07-30 16:27 | Shift B | ✅ Machine OK
BJ-156 | 25 | 2P | 2 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-07-30 16:27 | 27 | 54 | 2026-08-02 04:27 | Shift C | ✅ Machine OK
BJ-145 | 15 | 2P | 2 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-08-02 04:27 | 13 | 26 | 2026-08-03 09:20 | Shift A | ✅ Machine OK
BJ-153 | 34 | SEG | 6 | QC-MC-02 | General Workman | 2026-04-03 | 6 |  | 2026-09-03 09:18 | 31 | 186 | 2026-09-11 23:58 | Shift C | ✅ Machine OK
BJ-160 | 34 | 2P | 2 | QC-MC-02 | General Workman | 2026-04-03 | 6 |  | 2026-09-11 23:58 | 27 | 54 | 2026-09-14 11:58 | Shift A | ✅ Machine OK
BJ-158 | 54 | 2P | 2 | QC-MC-03 | General Workman | 2026-05-30 | 6 |  | 2026-11-17 20:39 | 67 | 134 | 2026-11-24 01:32 | Shift C | ✅ Machine OK
BJ-157 | 50 | SEG | 6 | QC-MC-03 | General Workman | 2026-05-30 | 6 |  | 2026-12-31 02:07 | 36 | 216 | 2027-01-10 02:07 | Shift C | ✅ Machine OK
BJ-159 | 54 | RW | 2 | QC-MC-03 | General Workman | 2026-05-30 | 6 |  | 2027-01-10 02:07 | 68 | 136 | 2027-01-16 09:13 | Shift A | ✅ Machine OK
BJ-148 | 9 | SEG | 6 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-08-03 09:20 | 2 | 12 | 2026-08-03 22:40 | Shift B | ✅ Machine OK
BJ-161 | 30 | SEG | 6 | QC-MC-02 | General Workman | 2026-04-03 | 6 |  | 2026-09-14 11:58 | 25 | 150 | 2026-09-21 10:38 | Shift A | ✅ Machine OK
BJ-149 | 9 | 2P | 2 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-08-03 22:40 | 5 | 10 | 2026-08-04 09:47 | Shift A | ✅ Machine OK
BJ-163 | 70 | SOL | 4 | QC-MC-03 | General Workman | 2026-05-30 | 6 |  | 2027-02-05 17:48 | 57 | 228 | 2027-02-16 07:08 | Shift A | ✅ Machine OK
BJ-164 | 42 | SOL | 4 | QC-MC-02 | General Workman | 2026-04-03 | 6 |  | 2026-09-21 10:38 | 33 | 132 | 2026-09-27 13:18 | Shift A | ✅ Machine OK
BJ-168 | 20 | 2P | 2 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-08-04 09:47 | 12 | 24 | 2026-08-05 12:27 | Shift A | ✅ Machine OK
BJ-155 | 17 | RW | 2 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-08-05 12:27 | 11 | 22 | 2026-08-06 12:53 | Shift A | ✅ Machine OK
BJ-167 | 54 | 2P | 2 | QC-MC-03 | General Workman | 2026-05-30 | 6 |  | 2027-02-16 07:08 | 67 | 134 | 2027-02-22 12:01 | Shift A | ✅ Machine OK
BJ-166 | 50 | SOL | 4 | QC-MC-03 | General Workman | 2026-05-30 | 6 |  | 2027-02-25 07:05 | 47 | 188 | 2027-03-05 23:58 | Shift C | ✅ Machine OK
BJ-162 | 17 | SOL | 4 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-08-06 12:53 | 15 | 60 | 2026-08-09 07:33 | Shift A | ✅ Machine OK
BJ-165 | 17 | 2P | 2 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-08-09 07:33 | 13 | 26 | 2026-08-10 12:27 | Shift A | ✅ Machine OK
BJ-169 | 17 | SEG | 6 | QC-MC-01 | General Workman | 2027-05-11 | 6 |  | 2026-08-16 23:46 | 11 | 66 | 2026-08-20 01:06 | Shift C | ✅ Machine OK

## Lists (hidden)
100 | 600 | Size | VTL | SPM | CARVING | EDM | ENG | VENT | FID | QC
300 | 800 | 9 | VTL-MC-01 | SPM-MC-01 | CARVING-MC-01 | EDM-MC-01 | ENG-MC-01 | VENT-MC-01 | FID-MC-01 | QC-MC-01
500 | 1000 | 15 | VTL-MC-01 | SPM-MC-01 | CARVING-MC-01 | EDM-MC-01 | ENG-MC-01 | VENT-MC-01 | FID-MC-01 | QC-MC-01
700 | 1200 | 17 | VTL-MC-01 | SPM-MC-01 | CARVING-MC-01 | EDM-MC-01 | ENG-MC-01 | VENT-MC-01 | FID-MC-01 | QC-MC-01
900 | 1400 | 20 | VTL-MC-01 | SPM-MC-01 | CARVING-MC-01 | EDM-MC-01 | ENG-MC-01 | VENT-MC-01 | FID-MC-01 | QC-MC-01
1100 | 1600 | 25 | VTL-MC-01 | SPM-MC-01 | CARVING-MC-01 | EDM-MC-01 | ENG-MC-01 | VENT-MC-01 | FID-MC-01 | QC-MC-01
1300 | 1800 | 28 | VTL-MC-01 | SPM-MC-01 | CARVING-MC-01 | EDM-MC-01 | ENG-MC-01 | VENT-MC-01 | FID-MC-01 | QC-MC-01
1500 | 2000 | 30 | VTL-MC-02 | SPM-MC-01 | CARVING-MC-01 | EDM-MC-09 | ENG-MC-01 | VENT-MC-04 | FID-MC-01 | QC-MC-01
1700 | 2200 | 34 | VTL-MC-02 | SPM-MC-01 | CARVING-MC-01 | EDM-MC-09 | ENG-MC-01 | VENT-MC-04 | FID-MC-01 | QC-MC-01
1900 | 2400 | 42 | VTL-MC-02 | SPM-MC-01 | CARVING-MC-01 | EDM-MC-09 | ENG-MC-03 | VENT-MC-04 | FID-MC-01 | QC-MC-01
2100 | 2600 | 46 | VTL-MC-02 | SPM-MC-01 | CARVING-MC-01 | EDM-MC-09 | ENG-MC-06 | VENT-MC-04 | FID-MC-01 | QC-MC-01
2300 | 2800 | 50 | VTL-MC-03 | SPM-MC-01 | CARVING-MC-01 | EDM-MC-16 | ENG-MC-06 | VENT-MC-04 | FID-MC-01 | QC-MC-01
2500 | 3000 | 54 | VTL-MC-03 | SPM-MC-01 | CARVING-MC-01 | EDM-MC-16 | ENG-MC-06 | VENT-MC-04 | FID-MC-01 | QC-MC-01
2700 | 3200 | 57 | VTL-MC-03 | SPM-MC-01 | CARVING-MC-01 | EDM-MC-16 | ENG-MC-06 | VENT-MC-04 | FID-MC-01 | QC-MC-01
2900 | 3400 | 63 | VTL-MC-03 | SPM-MC-01 | CARVING-MC-01 | EDM-MC-16 | ENG-MC-06 | VENT-MC-04 | FID-MC-01 | QC-MC-01
0 | 0 | 70 | VTL-MC-03 | SPM-MC-01 | CARVING-MC-01 | EDM-MC-16 | ENG-MC-12 | VENT-MC-04 | FID-MC-01 | QC-MC-01
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
100 | 600
300 | 800
500 | 1000
700 | 1200
900 | 1400
1100 | 1600
1300 | 1800
1500 | 2000
1700 | 2200
1900 | 2400
2100 | 2600
2300 | 2800
2500 | 3000
2700 | 3200
2900 | 3400
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
100 | 600
300 | 800
500 | 1000
700 | 1200
900 | 1400
1100 | 1600
1300 | 1800
1500 | 2000
1700 | 2200
1900 | 2400
2100 | 2600
2300 | 2800
2500 | 3000
2700 | 3200
2900 | 3400
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
100 | 600
300 | 800
500 | 1000
700 | 1200
900 | 1400
1100 | 1600
1300 | 1800
1500 | 2000
1700 | 2200
1900 | 2400
2100 | 2600
2300 | 2800
2500 | 3000
2700 | 3200
2900 | 3400
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0

## Dashboard
PRODUCTION & UTILIZATION DASHBOARD
Total Jobs Planned | Earliest Start | Latest Finish | Plan Duration (Days)
70 | 2026-04-01 07:00 | 2027-03-05 23:58 | 338
Stage | No. of Machines | Total Load (Hrs) | Capacity (Hrs) | Utilization % | Target 90%
VTL | 4 | 7040 | 32448 | 21.7% | 0.9
SPM | 6 | 10588 | 48672 | 21.75% | 0.9
CARVING | 6 | 8456 | 48672 | 17.37% | 0.9
EDM | 30 | 8620 | 243360 | 3.542% | 0.9
ENG | 14 | 9292 | 113568 | 8.182% | 0.9
VENT | 8 | 7402 | 64896 | 11.41% | 0.9
FID | 10 | 7338 | 81120 | 9.046% | 0.9
QC | 5 | 6460 | 40560 | 15.93% | 0.9
KEY PERFORMANCE INDICATORS
KPI | Target | Actual | Status
On-Time Delivery % | ≥95% | 100% | ✅ |  | 🔴 BOTTLENECK: | SPM
Avg Machine Utilization % | ≥85% | 13.62% | ✅ |  | Max Utilization: | 21.75%
Bottleneck Stage | N/A | SPM | ✅ |  | 🟢 LOWEST LOAD: | EDM
Jobs On Hold / Cancelled | 0 | 21 | ✅
Open Downtimes | 0 | 0 | ✅
Open Rejections | N/A | N/A | —
Out of Stock Materials | 0 | 0 | ✅
Low Stock Materials | 0 | 4 | ✅

## PM_Schedule
[6 empty] | Wk-14 | Wk-14 | Wk-14 | Wk-14 | Wk-14 | Wk-15 | Wk-15 | Wk-15 | Wk-15 | Wk-15 | Wk-15 | Wk-15 | Wk-16 | Wk-16 | Wk-16 | Wk-16 | Wk-16 | Wk-16 | Wk-16 | Wk-17 | Wk-17 | Wk-17 | Wk-17 | Wk-17 | Wk-17 | Wk-17 | Wk-18 | Wk-18 | Wk-18 | Wk-18 | Wk-18 | Wk-18 | Wk-18 | Wk-19 | Wk-19 | Wk-19 | Wk-19 | Wk-19 | Wk-19 | Wk-19 | Wk-20 | Wk-20 | Wk-20 | Wk-20 | Wk-20 | Wk-20 | Wk-20 | Wk-21 | Wk-21 | Wk-21 | Wk-21 | Wk-21 | Wk-21 | Wk-21 | Wk-22 | Wk-22 | Wk-22 | Wk-22 | Wk-22 | Wk-22 | Wk-1 | Wk-1 | Wk-1 | Wk-1 | Wk-1 | Wk-1 | Wk-1 | Wk-1 | Wk-1 | Wk-1 | Wk-1 | Wk-1 | Wk-1 | Wk-1 | Wk-1 | Wk-1 | Wk-1 | Wk-1 | Wk-1 | Wk-1 | Wk-1 | Wk-1 | Wk-1 | Wk-1 | Wk-1 | Wk-1 | Wk-1 | Wk-1 | Wk-1 | Wk-1
Operation | Machine ID | Next PM Date | Dur (Hrs) | Days Left | Alert Status | time axis 2026-04-01 to 2026-05-30
VTL | VTL-MC-01 | 2026-04-21 | 6 | 14 | OK | 2026-04-21: 21-Apr
VTL | VTL-MC-02 | 2027-05-14 | 6 | 402 | OK
VTL | VTL-MC-03 | 2026-06-01 | 6 | 55 | OK
VTL | VTL-MC-04 | 2027-05-10 | 6 | 398 | OK
SPM | SPM-MC-01 | 2026-09-20 | 6 | 166 | OK
SPM | SPM-MC-02 | 2027-03-13 | 6 | 340 | OK
SPM | SPM-MC-03 | 2026-03-23 | 6 | -15 | OVERDUE
SPM | SPM-MC-04 | 2026-06-24 | 6 | 78 | OK
SPM | SPM-MC-05 | 2026-09-06 | 6 | 152 | OK
SPM | SPM-MC-06 | 2026-06-03 | 6 | 57 | OK
CARVING | CARVING-MC-01 | 2027-01-31 | 6 | 299 | OK
CARVING | CARVING-MC-02 | 2026-09-17 | 6 | 163 | OK
CARVING | CARVING-MC-03 | 2026-10-01 | 6 | 177 | OK
CARVING | CARVING-MC-04 | 2026-08-03 | 6 | 118 | OK
CARVING | CARVING-MC-05 | 2026-08-04 | 6 | 119 | OK
CARVING | CARVING-MC-06 | 2027-01-10 | 6 | 278 | OK
EDM | EDM-MC-01 | 2026-03-11 | 6 | -27 | OVERDUE
EDM | EDM-MC-02 | 2026-05-18 | 6 | 41 | OK | 2026-05-18: 18-May
EDM | EDM-MC-03 | 2026-02-04 | 6 | -62 | OVERDUE
EDM | EDM-MC-04 | 2026-03-30 | 6 | -8 | OVERDUE
EDM | EDM-MC-05 | 2026-07-22 | 6 | 106 | OK
EDM | EDM-MC-06 | 2026-11-04 | 6 | 211 | OK
EDM | EDM-MC-07 | 2026-07-05 | 6 | 89 | OK
EDM | EDM-MC-08 | 2026-09-26 | 6 | 172 | OK
EDM | EDM-MC-09 | 2026-08-03 | 6 | 118 | OK
EDM | EDM-MC-10 | 2027-04-26 | 6 | 384 | OK
EDM | EDM-MC-11 | 2026-03-17 | 6 | -21 | OVERDUE
EDM | EDM-MC-12 | 2026-11-11 | 6 | 218 | OK
EDM | EDM-MC-13 | 2026-07-09 | 6 | 93 | OK
EDM | EDM-MC-14 | 2027-03-01 | 6 | 328 | OK
EDM | EDM-MC-15 | 2026-12-01 | 6 | 238 | OK
EDM | EDM-MC-16 | 2026-03-24 | 6 | -14 | OVERDUE
EDM | EDM-MC-17 | 2027-04-27 | 6 | 385 | OK
EDM | EDM-MC-18 | 2026-07-22 | 6 | 106 | OK
EDM | EDM-MC-19 | 2026-08-29 | 6 | 144 | OK
EDM | EDM-MC-20 | 2026-01-18 | 6 | -79 | OVERDUE
EDM | EDM-MC-21 | 2027-03-30 | 6 | 357 | OK
EDM | EDM-MC-22 | 2026-08-05 | 6 | 120 | OK
EDM | EDM-MC-23 | 2026-10-29 | 6 | 205 | OK
EDM | EDM-MC-24 | 2026-03-16 | 6 | -22 | OVERDUE
EDM | EDM-MC-25 | 2026-03-17 | 6 | -21 | OVERDUE
EDM | EDM-MC-26 | 2026-06-29 | 6 | 83 | OK
EDM | EDM-MC-27 | 2026-06-15 | 6 | 69 | OK
EDM | EDM-MC-28 | 2026-06-09 | 6 | 63 | OK
EDM | EDM-MC-29 | 2027-04-16 | 6 | 374 | OK
EDM | EDM-MC-30 | 2026-03-25 | 6 | -13 | OVERDUE
ENG | ENG-MC-01 | 2026-03-09 | 6 | -29 | OVERDUE
ENG | ENG-MC-02 | 2026-07-27 | 6 | 111 | OK
ENG | ENG-MC-03 | 2027-02-15 | 6 | 314 | OK
ENG | ENG-MC-04 | 2027-03-04 | 6 | 331 | OK
ENG | ENG-MC-05 | 2026-01-27 | 6 | -70 | OVERDUE
ENG | ENG-MC-06 | 2026-02-21 | 6 | -45 | OVERDUE
ENG | ENG-MC-07 | 2026-09-07 | 6 | 153 | OK
ENG | ENG-MC-08 | 2026-12-27 | 6 | 264 | OK
ENG | ENG-MC-09 | 2027-03-25 | 6 | 352 | OK
ENG | ENG-MC-10 | 2026-12-21 | 6 | 258 | OK
ENG | ENG-MC-11 | 2027-05-10 | 6 | 398 | OK
ENG | ENG-MC-12 | 2027-03-08 | 6 | 335 | OK
ENG | ENG-MC-13 | 2026-12-15 | 6 | 252 | OK
ENG | ENG-MC-14 | 2026-07-16 | 6 | 100 | OK
VENT | VENT-MC-01 | 2026-07-27 | 6 | 111 | OK
VENT | VENT-MC-02 | 2026-06-18 | 6 | 72 | OK
VENT | VENT-MC-03 | 2026-02-01 | 6 | -65 | OVERDUE
VENT | VENT-MC-04 | 2026-08-21 | 6 | 136 | OK
VENT | VENT-MC-05 | 2027-01-07 | 6 | 275 | OK
VENT | VENT-MC-06 | 2026-11-21 | 6 | 228 | OK
VENT | VENT-MC-07 | 2026-07-31 | 6 | 115 | OK
VENT | VENT-MC-08 | 2026-04-26 | 6 | 19 | OK | 2026-04-26: 26-Apr
FID | FID-MC-01 | 2026-03-25 | 6 | -13 | OVERDUE
FID | FID-MC-02 | 2026-04-30 | 6 | 23 | OK | 2026-04-30: 30-Apr
FID | FID-MC-03 | 2027-04-06 | 6 | 364 | OK
FID | FID-MC-04 | 2026-10-23 | 6 | 199 | OK
FID | FID-MC-05 | 2027-02-13 | 6 | 312 | OK
FID | FID-MC-06 | 2026-03-07 | 6 | -31 | OVERDUE
FID | FID-MC-07 | 2027-01-15 | 6 | 283 | OK
FID | FID-MC-08 | 2026-11-02 | 6 | 209 | OK
FID | FID-MC-09 | 2026-05-23 | 6 | 46 | OK | 2026-05-23: 23-May
FID | FID-MC-10 | 2027-04-06 | 6 | 364 | OK
QC | QC-MC-01 | 2027-05-11 | 6 | 399 | OK
QC | QC-MC-02 | 2026-04-03 | 6 | -4 | OVERDUE | 2026-04-03: 03-Apr
QC | QC-MC-03 | 2026-05-30 | 6 | 53 | OK | 2026-05-30: 30-May
QC | QC-MC-04 | 2026-06-22 | 6 | 76 | OK
QC | QC-MC-05 | 2026-12-17 | 6 | 254 | OK
Formulas:
Days Left = [Next PM Date]-TODAY()

## OPR_2P
Part No | 2
Size | VTL | SPM | CARVING | EDM | ENG | VENT | FID | QC | Min ID | Max OD
9 | 6 | 3 | 6 | 4 | 5 | 1 | 5 | 2 | 100 | 600
15 | 19 | 12 | 12 | 16 | 10 | 12 | 13 | 6 | 300 | 800
17 | 20 | 14 | 12 | 12 | 16 | 17 | 13 | 10 | 500 | 1000
20 | 31 | 24 | 20 | 27 | 18 | 14 | 12 | 15 | 700 | 1200
25 | 36 | 29 | 24 | 24 | 27 | 24 | 27 | 24 | 900 | 1400
28 | 38 | 30 | 35 | 26 | 32 | 32 | 17 | 28 | 1100 | 1600
30 | 35 | 42 | 27 | 38 | 22 | 31 | 30 | 16 | 1300 | 1800
34 | 50 | 48 | 54 | 35 | 27 | 37 | 27 | 27 | 1500 | 2000
42 | 48 | 48 | 61 | 64 | 62 | 51 | 47 | 39 | 1700 | 2200
46 | 59 | 74 | 72 | 64 | 48 | 35 | 35 | 29 | 1900 | 2400
50 | 56 | 84 | 67 | 84 | 69 | 46 | 65 | 55 | 2100 | 2600
54 | 100 | 60 | 92 | 66 | 57 | 77 | 67 | 61 | 2300 | 2800
57 | 71 | 61 | 61 | 77 | 69 | 69 | 46 | 38 | 2500 | 3000
63 | 115 | 92 | 61 | 77 | 71 | 93 | 67 | 44 | 2700 | 3200
70 | 115 | 129 | 75 | 106 | 90 | 70 | 80 | 51 | 2900 | 3400

## SEG_6P
Part No | 6
Size | VTL | SPM | CARVING | EDM | ENG | VENT | FID | QC | Min ID | Max OD
9 | 8 | 5 | 7 | 5 | 5 | 2 | 2 | 4 | 100 | 600
15 | 10 | 15 | 15 | 16 | 7 | 15 | 11 | 8 | 300 | 800
17 | 19 | 18 | 20 | 20 | 19 | 17 | 11 | 13 | 500 | 1000
20 | 26 | 29 | 17 | 28 | 19 | 22 | 22 | 9 | 700 | 1200
25 | 38 | 27 | 26 | 35 | 32 | 31 | 23 | 12 | 900 | 1400
28 | 31 | 43 | 25 | 25 | 32 | 27 | 17 | 19 | 1100 | 1600
30 | 35 | 31 | 27 | 38 | 26 | 27 | 25 | 29 | 1300 | 1800
34 | 49 | 39 | 48 | 42 | 32 | 33 | 31 | 29 | 1500 | 2000
42 | 73 | 54 | 58 | 44 | 53 | 37 | 54 | 36 | 1700 | 2200
46 | 74 | 76 | 76 | 67 | 59 | 61 | 38 | 34 | 1900 | 2400
50 | 89 | 70 | 67 | 57 | 53 | 59 | 36 | 32 | 2100 | 2600
54 | 102 | 84 | 73 | 91 | 65 | 48 | 57 | 62 | 2300 | 2800
57 | 110 | 66 | 68 | 96 | 91 | 76 | 61 | 43 | 2500 | 3000
63 | 94 | 105 | 93 | 94 | 62 | 78 | 50 | 39 | 2700 | 3200
70 | 102 | 92 | 112 | 130 | 90 | 104 | 91 | 52 | 2900 | 3400

## SOL_4P
Part No | 4
Size | VTL | SPM | CARVING | EDM | ENG | VENT | FID | QC | Min ID | Max OD
9 | 2 | 3 | 7 | 3 | 2 | 5 | 5 | 3 | 100 | 600
15 | 19 | 17 | 14 | 11 | 13 | 14 | 7 | 9 | 300 | 800
17 | 13 | 20 | 11 | 22 | 15 | 11 | 15 | 11 | 500 | 1000
20 | 16 | 27 | 21 | 16 | 15 | 14 | 16 | 11 | 700 | 1200
25 | 27 | 26 | 36 | 30 | 20 | 23 | 23 | 20 | 900 | 1400
28 | 33 | 46 | 22 | 32 | 28 | 23 | 28 | 16 | 1100 | 1600
30 | 49 | 40 | 29 | 35 | 39 | 24 | 22 | 21 | 1300 | 1800
34 | 65 | 32 | 33 | 61 | 38 | 25 | 32 | 26 | 1500 | 2000
42 | 54 | 43 | 63 | 41 | 37 | 41 | 33 | 29 | 1700 | 2200
46 | 65 | 55 | 41 | 84 | 69 | 35 | 41 | 44 | 1900 | 2400
50 | 99 | 49 | 49 | 66 | 53 | 71 | 47 | 51 | 2100 | 2600
54 | 84 | 54 | 80 | 87 | 54 | 78 | 50 | 53 | 2300 | 2800
57 | 99 | 60 | 56 | 89 | 74 | 54 | 55 | 63 | 2500 | 3000
63 | 115 | 95 | 84 | 120 | 75 | 52 | 77 | 68 | 2700 | 3200
70 | 133 | 71 | 99 | 111 | 86 | 84 | 57 | 56 | 2900 | 3400

## RW_2P
Part No | 2
Size | VTL | SPM | CARVING | EDM | ENG | VENT | FID | QC | Min ID | Max OD
9 | 2 | 5 | 2 | 6 | 2 | 6 | 5 | 1 | 100 | 600
15 | 15 | 11 | 14 | 10 | 7 | 14 | 7 | 5 | 300 | 800
17 | 17 | 21 | 19 | 22 | 19 | 11 | 11 | 9 | 500 | 1000
20 | 32 | 18 | 22 | 28 | 23 | 15 | 19 | 9 | 700 | 1200
25 | 30 | 30 | 35 | 39 | 23 | 18 | 16 | 16 | 900 | 1400
28 | 29 | 36 | 36 | 48 | 33 | 24 | 34 | 26 | 1100 | 1600
30 | 32 | 41 | 30 | 49 | 31 | 20 | 35 | 26 | 1300 | 1800
34 | 56 | 51 | 36 | 52 | 32 | 37 | 28 | 33 | 1500 | 2000
42 | 59 | 66 | 52 | 57 | 50 | 40 | 35 | 40 | 1700 | 2200
46 | 51 | 52 | 62 | 49 | 66 | 35 | 48 | 40 | 1900 | 2400
50 | 61 | 54 | 77 | 72 | 78 | 41 | 53 | 47 | 2100 | 2600
54 | 78 | 88 | 76 | 73 | 86 | 54 | 68 | 33 | 2300 | 2800
57 | 108 | 99 | 63 | 94 | 53 | 84 | 77 | 40 | 2500 | 3000
63 | 104 | 90 | 64 | 81 | 61 | 76 | 55 | 53 | 2700 | 3200
70 | 100 | 96 | 115 | 99 | 77 | 87 | 96 | 57 | 2900 | 3400

## RW2_4P
Part No | 4
Size | VTL | SPM | CARVING | EDM | ENG | VENT | FID | QC | Min ID | Max OD
9 | 3 | 4 | 4 | 4 | 4 | 6 | 4 | 3 | 100 | 600
15 | 18 | 17 | 18 | 14 | 7 | 13 | 12 | 6 | 300 | 800
17 | 22 | 19 | 17 | 14 | 10 | 9 | 12 | 11 | 500 | 1000
20 | 20 | 20 | 16 | 28 | 24 | 23 | 19 | 13 | 700 | 1200
25 | 45 | 21 | 30 | 30 | 26 | 25 | 22 | 17 | 900 | 1400
28 | 31 | 40 | 24 | 36 | 38 | 32 | 29 | 25 | 1100 | 1600
30 | 37 | 25 | 29 | 32 | 41 | 30 | 32 | 16 | 1300 | 1800
34 | 55 | 49 | 37 | 51 | 28 | 34 | 34 | 36 | 1500 | 2000
42 | 76 | 75 | 43 | 74 | 48 | 33 | 49 | 45 | 1700 | 2200
46 | 73 | 64 | 56 | 75 | 51 | 43 | 53 | 42 | 1900 | 2400
50 | 86 | 88 | 52 | 94 | 57 | 72 | 60 | 30 | 2100 | 2600
54 | 111 | 63 | 70 | 72 | 46 | 59 | 45 | 56 | 2300 | 2800
57 | 94 | 60 | 81 | 89 | 61 | 52 | 76 | 60 | 2500 | 3000
63 | 93 | 107 | 65 | 67 | 100 | 92 | 80 | 55 | 2700 | 3200
70 | 87 | 119 | 96 | 116 | 61 | 105 | 84 | 78 | 2900 | 3400

## FLAP_4P
Part No | 4
Size | VTL | SPM | CARVING | EDM | ENG | VENT | FID | QC | Min ID | Max OD
9 | 2 | 3 | 7 | 3 | 2 | 5 | 5 | 3 | 100 | 600
15 | 19 | 17 | 14 | 11 | 13 | 14 | 7 | 9 | 300 | 800
17 | 13 | 20 | 11 | 22 | 15 | 11 | 15 | 11 | 500 | 1000
20 | 16 | 27 | 21 | 16 | 15 | 14 | 16 | 11 | 700 | 1200
25 | 27 | 26 | 36 | 30 | 20 | 23 | 23 | 20 | 900 | 1400
28 | 33 | 46 | 22 | 32 | 28 | 23 | 28 | 16 | 1100 | 1600
30 | 49 | 40 | 29 | 35 | 39 | 24 | 22 | 21 | 1300 | 1800
34 | 65 | 32 | 33 | 61 | 38 | 25 | 32 | 26 | 1500 | 2000
42 | 54 | 43 | 63 | 41 | 37 | 41 | 33 | 29 | 1700 | 2200
46 | 65 | 55 | 41 | 84 | 69 | 35 | 41 | 44 | 1900 | 2400
50 | 99 | 49 | 49 | 66 | 53 | 71 | 47 | 51 | 2100 | 2600
54 | 84 | 54 | 80 | 87 | 54 | 78 | 50 | 53 | 2300 | 2800
57 | 99 | 60 | 56 | 89 | 74 | 54 | 55 | 63 | 2500 | 3000
63 | 115 | 95 | 84 | 120 | 75 | 52 | 77 | 68 | 2700 | 3200
70 | 133 | 71 | 99 | 111 | 86 | 84 | 57 | 56 | 2900 | 3400

## TUBE_4P
Part No | 4
Size | VTL | SPM | CARVING | EDM | ENG | VENT | FID | QC | Min ID | Max OD
9 | 2 | 3 | 7 | 3 | 2 | 5 | 5 | 3 | 100 | 600
15 | 19 | 17 | 14 | 11 | 13 | 14 | 7 | 9 | 300 | 800
17 | 13 | 20 | 11 | 22 | 15 | 11 | 15 | 11 | 500 | 1000
20 | 16 | 27 | 21 | 16 | 15 | 14 | 16 | 11 | 700 | 1200
25 | 27 | 26 | 36 | 30 | 20 | 23 | 23 | 20 | 900 | 1400
28 | 33 | 46 | 22 | 32 | 28 | 23 | 28 | 16 | 1100 | 1600
30 | 49 | 40 | 29 | 35 | 39 | 24 | 22 | 21 | 1300 | 1800
34 | 65 | 32 | 33 | 61 | 38 | 25 | 32 | 26 | 1500 | 2000
42 | 54 | 43 | 63 | 41 | 37 | 41 | 33 | 29 | 1700 | 2200
46 | 65 | 55 | 41 | 84 | 69 | 35 | 41 | 44 | 1900 | 2400
50 | 99 | 49 | 49 | 66 | 53 | 71 | 47 | 51 | 2100 | 2600
54 | 84 | 54 | 80 | 87 | 54 | 78 | 50 | 53 | 2300 | 2800
57 | 99 | 60 | 56 | 89 | 74 | 54 | 55 | 63 | 2500 | 3000
63 | 115 | 95 | 84 | 120 | 75 | 52 | 77 | 68 | 2700 | 3200
70 | 133 | 71 | 99 | 111 | 86 | 84 | 57 | 56 | 2900 | 3400

## WIP_Tracker
WORK IN PROGRESS TRACKER
Today | 2026-04-07
Job ID | Size | Type | Priority | Status | Current Stage | Stage Start | Stage End | % Complete | Due Date | On Time? | Remarks
BJ-104 | 28 | 2P | Medium | Released | QC | 2026-04-01 07:00 | 2026-04-20 08:09 | 100% | 2026-07-22 16:51 | ✅ On Time
BJ-101 | 42 | SOL | Medium | On Hold | QC | 2026-04-01 07:00 | 2026-05-28 08:50 | 100% | 2026-06-27 08:50 | ✅ On Time
BJ-105 | 28 | RW | Medium | Released | QC | 2026-04-03 21:13 | 2026-04-26 15:49 | 100% | 2026-07-04 22:40 | ✅ On Time
BJ-100 | 25 | SEG | Low | Released | QC | 2026-04-06 11:27 | 2026-06-03 04:27 | 100% | 2026-05-20 08:09 | ⚠ Delayed
BJ-102 | 34 | SEG | Medium | Cancelled | QC | 2026-04-09 01:40 | 2026-06-22 16:51 | 100% | 2026-05-26 15:49 | ⚠ Delayed
BJ-103 | 20 | RW | Low | Released | QC | 2026-04-13 10:07 | 2026-06-04 22:40 | 100% | 2026-07-03 04:27 | ✅ On Time
BJ-108 | 70 | RW | High | Released | QC | 2026-04-01 07:00 | 2026-05-30 09:06 | 100% | 2026-07-25 22:38 | ✅ On Time
BJ-106 | 15 | RW | Low | On Hold | QC | 2026-04-15 06:33 | 2026-06-05 14:13 | 100% | 2026-06-29 09:06 | ✅ On Time
BJ-109 | 30 | RW | Medium | Released | QC | 2026-04-18 12:20 | 2026-06-25 22:38 | 100% | 2026-07-06 19:07 | ✅ On Time
BJ-110 | 17 | 2P | Low | Released | QC | 2026-04-16 15:53 | 2026-06-06 19:07 | 100% | 2026-07-08 06:40 | ✅ On Time
BJ-111 | 25 | RW | Low | Released | QC | 2026-04-18 05:40 | 2026-06-08 06:40 | 100% | 2026-07-14 12:21 | ✅ On Time
BJ-107 | 20 | SEG | Low | On Hold | QC | 2026-04-20 13:13 | 2026-06-14 12:21 | 100% | 2026-07-05 14:13 | ✅ On Time
BJ-112 | 17 | 2P | Low | Released | QC | 2026-04-26 09:13 | 2026-06-15 17:14 | 100% | 2026-07-15 17:14 | ✅ On Time
BJ-114 | 50 | SEG | High | Released | QC | 2026-04-07 18:33 | 2026-07-29 19:53 | 100% | 2026-07-29 04:25 | ⚠ Delayed
BJ-115 | 46 | 2P | High | Cancelled | QC | 2026-04-21 07:00 | 2026-06-29 04:25 | 100% | 2026-09-04 00:47 | ✅ On Time
BJ-116 | 54 | 2P | High | Released | QC | 2026-04-21 15:53 | 2026-08-05 00:47 | 100% | 2026-07-20 21:41 | ⚠ Delayed
BJ-118 | 28 | SOL | Medium | Released | QC | 2026-04-27 23:00 | 2026-06-20 21:41 | 100% | 2026-08-01 10:11 | ✅ On Time
BJ-119 | 63 | SOL | High | On Hold | QC | 2026-04-26 15:53 | 2026-08-29 15:44 | 100% | 2026-07-21 11:01 | ⚠ Delayed
BJ-120 | 46 | 2P | High | Released | QC | 2026-04-25 13:13 | 2026-07-02 10:11 | 100% | 2026-10-05 18:50 | ✅ On Time
BJ-113 | 9 | SEG | Low | Released | QC | 2026-05-03 03:27 | 2026-06-21 11:01 | 100% | 2026-08-28 19:53 | ✅ On Time
BJ-121 | 57 | RW | High | Released | QC | 2026-05-08 07:53 | 2026-09-05 18:50 | 100% | 2026-08-05 20:51 | ⚠ Delayed
BJ-123 | 46 | RW | High | On Hold | QC | 2026-04-29 19:27 | 2026-07-06 20:51 | 100% | 2026-10-19 08:43 | ✅ On Time
BJ-117 | 15 | RW | Low | Released | QC | 2026-05-05 15:27 | 2026-06-22 02:34 | 100% | 2026-09-28 15:44 | ✅ On Time
BJ-122 | 54 | SOL | High | Released | QC | 2026-05-13 14:33 | 2026-09-19 08:43 | 100% | 2026-07-22 02:34 | ⚠ Delayed
BJ-124 | 42 | 2P | Medium | Cancelled | QC | 2026-05-04 01:40 | 2026-07-11 05:18 | 100% | 2026-08-10 05:18 | ✅ On Time
BJ-126 | 42 | 2P | Medium | Released | QC | 2026-05-07 23:00 | 2026-07-15 13:45 | 100% | 2026-07-22 18:08 | ✅ On Time
BJ-127 | 15 | RW | Low | Released | QC | 2026-05-07 00:47 | 2026-06-22 18:08 | 100% | 2026-08-17 19:31 | ✅ On Time
BJ-128 | 46 | 2P | High | On Hold | QC | 2026-05-11 20:20 | 2026-07-18 19:31 | 100% | 2026-08-11 21:47 | ✅ On Time
BJ-125 | 25 | SEG | Low | Released | QC | 2026-05-08 10:07 | 2026-07-12 21:47 | 100% | 2026-08-14 13:45 | ✅ On Time
BJ-129 | 9 | RW | Low | Released | QC | 2026-05-15 08:47 | 2026-07-13 08:53 | 100% | 2026-08-12 08:53 | ✅ On Time
BJ-130 | 57 | RW | High | Released | QC | 2026-05-23 14:33 | 2026-09-26 11:50 | 100% | 2026-10-26 11:50 | ✅ On Time
BJ-133 | 25 | RW | Low | On Hold | QC | 2026-05-16 04:47 | 2026-07-14 20:27 | 100% | 2026-08-14 12:00 | ✅ On Time
BJ-131 | 70 | 2P | High | Released | QC | 2026-05-28 21:13 | 2026-10-03 21:36 | 100% | 2026-08-13 20:27 | ⚠ Delayed
BJ-134 | 15 | RW | Low | Released | QC | 2026-05-18 12:20 | 2026-07-15 12:00 | 100% | 2026-08-16 01:47 | ✅ On Time
BJ-135 | 28 | 2P | Medium | Cancelled | QC | 2026-05-19 21:40 | 2026-07-17 01:47 | 100% | 2026-11-23 13:48 | ✅ On Time
BJ-132 | 57 | SOL | High | Released | QC | 2026-06-04 15:27 | 2026-10-24 13:48 | 100% | 2026-11-02 21:36 | ✅ On Time
BJ-136 | 20 | RW | Low | Released | QC | 2026-05-22 11:53 | 2026-07-18 20:00 | 100% | 2026-08-17 20:00 | ✅ On Time
BJ-137 | 34 | RW | Medium | On Hold | QC | 2026-05-16 02:33 | 2026-07-21 09:45 | 100% | 2026-08-20 09:45 | ✅ On Time
BJ-140 | 54 | RW | High | Released | QC | 2026-06-15 04:47 | 2026-10-30 20:54 | 100% | 2026-12-04 23:08 | ✅ On Time
BJ-138 | 9 | RW | Low | Released | QC | 2026-05-24 08:20 | 2026-07-19 07:07 | 100% | 2026-11-29 20:54 | ✅ On Time
BJ-144 | 63 | RW | High | Released | QC | 2026-06-20 04:47 | 2026-11-04 23:08 | 100% | 2026-08-21 04:00 | ⚠ Delayed
BJ-146 | 20 | RW | Low | On Hold | QC | 2026-05-25 04:20 | 2026-07-21 01:20 | 100% | 2026-09-18 05:53 | ✅ On Time
BJ-139 | 15 | RW | Low | Released | QC | 2026-05-27 00:47 | 2026-07-21 16:53 | 100% | 2026-08-18 07:07 | ✅ On Time
BJ-141 | 50 | SOL | High | Released | QC | 2026-06-26 00:47 | 2026-11-17 20:39 | 100% | 2026-08-20 01:20 | ⚠ Delayed
BJ-142 | 9 | RW | Low | Cancelled | QC | 2026-05-28 10:07 | 2026-07-22 04:00 | 100% | 2026-08-20 16:53 | ✅ On Time
BJ-147 | 34 | SOL | Medium | Released | QC | 2026-05-19 06:07 | 2026-08-07 16:07 | 100% | 2026-08-25 10:13 | ✅ On Time
BJ-150 | 34 | SOL | Medium | Released | QC | 2026-05-25 13:13 | 2026-08-19 05:53 | 100% | 2026-08-29 16:27 | ✅ On Time
BJ-151 | 25 | SOL | Low | On Hold | QC | 2026-05-29 06:07 | 2026-07-26 10:13 | 100% | 2026-09-01 04:27 | ✅ On Time
BJ-152 | 34 | 2P | Medium | Released | QC | 2026-05-31 20:20 | 2026-08-21 17:53 | 100% | 2026-09-02 09:20 | ✅ On Time
BJ-143 | 17 | SOL | Low | Released | QC | 2026-06-02 21:13 | 2026-07-29 04:53 | 100% | 2026-12-17 20:39 | ✅ On Time
BJ-154 | 25 | RW | Low | Released | QC | 2026-06-06 00:47 | 2026-07-30 16:27 | 100% | 2026-10-14 11:58 | ✅ On Time
BJ-156 | 25 | 2P | Low | On Hold | QC | 2026-06-08 08:20 | 2026-08-02 04:27 | 100% | 2027-02-09 02:07 | ✅ On Time
BJ-145 | 15 | 2P | Low | Released | QC | 2026-06-10 15:53 | 2026-08-03 09:20 | 100% | 2026-09-06 16:07 | ✅ On Time
BJ-153 | 34 | SEG | Medium | Released | QC | 2026-06-03 23:53 | 2026-09-11 23:58 | 100% | 2026-10-11 23:58 | ✅ On Time
BJ-160 | 34 | 2P | Medium | Cancelled | QC | 2026-06-13 10:33 | 2026-09-14 11:58 | 100% | 2026-09-03 09:47 | ⚠ Delayed
BJ-158 | 54 | 2P | High | Released | QC | 2026-07-05 07:00 | 2026-11-24 01:32 | 100% | 2026-09-02 22:40 | ⚠ Delayed
BJ-157 | 50 | SEG | High | Released | QC | 2026-07-10 07:00 | 2027-01-10 02:07 | 100% | 2027-02-15 09:13 | ✅ On Time
BJ-159 | 54 | RW | High | On Hold | QC | 2026-07-24 04:20 | 2027-01-16 09:13 | 100% | 2026-10-21 10:38 | ⚠ Delayed
BJ-148 | 9 | SEG | Low | Released | QC | 2026-06-12 01:13 | 2026-08-03 22:40 | 100% | 2026-09-20 17:53 | ✅ On Time
BJ-161 | 30 | SEG | Medium | Released | QC | 2026-06-16 14:07 | 2026-09-21 10:38 | 100% | 2027-03-18 07:08 | ✅ On Time
BJ-149 | 9 | 2P | Low | Released | QC | 2026-06-14 13:13 | 2026-08-04 09:47 | 100% | 2026-08-28 04:53 | ✅ On Time
BJ-163 | 70 | SOL | High | On Hold | QC | 2026-07-29 04:20 | 2027-02-16 07:08 | 100% | 2026-09-04 12:27 | ⚠ Delayed
BJ-164 | 42 | SOL | Medium | Released | QC | 2026-06-24 22:07 | 2026-09-27 13:18 | 100% | 2026-09-05 12:53 | ⚠ Delayed
BJ-168 | 20 | 2P | Low | Released | QC | 2026-06-15 09:13 | 2026-08-05 12:27 | 100% | 2026-09-09 12:27 | ✅ On Time
BJ-155 | 17 | RW | Low | Cancelled | QC | 2026-06-17 05:40 | 2026-08-06 12:53 | 100% | 2026-12-24 01:32 | ✅ On Time
BJ-167 | 54 | 2P | High | Released | QC | 2026-08-11 03:27 | 2027-02-22 12:01 | 100% | 2026-09-08 07:33 | ⚠ Delayed
BJ-166 | 50 | SOL | High | Released | QC | 2026-08-16 03:27 | 2027-03-05 23:58 | 100% | 2027-04-04 23:58 | ✅ On Time
BJ-162 | 17 | SOL | Low | On Hold | QC | 2026-06-18 19:27 | 2026-08-09 07:33 | 100% | 2026-10-27 13:18 | ✅ On Time
BJ-165 | 17 | 2P | Low | Released | QC | 2026-06-21 23:00 | 2026-08-10 12:27 | 100% | 2027-03-24 12:01 | ✅ On Time
BJ-169 | 17 | SEG | Low | Released | QC | 2026-06-23 12:47 | 2026-08-20 01:06 | 100% | 2026-09-19 01:06 | ✅ On Time

## Delivery_Tracker
CUSTOMER DELIVERY TRACKER
Job ID | Size | Type | Priority | Customer | Planned End | Due Date | Buffer Days | RAG Status | Dispatched? | Dispatch Date | Remarks
BJ-104 | 28 | 2P | Medium | Alpha Corp | 2026-06-22 16:51 | 2026-07-22 16:51 | 30 | 🟢 ON TRACK | No
BJ-101 | 42 | SOL | Medium | Beta Ltd | 2026-05-28 08:50 | 2026-06-27 08:50 | 30 | 🟢 ON TRACK | No
BJ-105 | 28 | RW | Medium | Alpha Corp | 2026-06-04 22:40 | 2026-07-04 22:40 | 30 | 🟢 ON TRACK | No
BJ-100 | 25 | SEG | Low | Gamma Inc | 2026-04-20 08:09 | 2026-05-20 08:09 | 30 | 🟢 ON TRACK | No
BJ-102 | 34 | SEG | Medium | Beta Ltd | 2026-04-26 15:49 | 2026-05-26 15:49 | 30 | 🟢 ON TRACK | No
BJ-103 | 20 | RW | Low | Delta Co | 2026-06-03 04:27 | 2026-07-03 04:27 | 30 | 🟢 ON TRACK | No
BJ-108 | 70 | RW | High | Alpha Corp | 2026-06-25 22:38 | 2026-07-25 22:38 | 30 | 🟢 ON TRACK | No
BJ-106 | 15 | RW | Low | Gamma Inc | 2026-05-30 09:06 | 2026-06-29 09:06 | 30 | 🟢 ON TRACK | No
BJ-109 | 30 | RW | Medium | Beta Ltd | 2026-06-06 19:07 | 2026-07-06 19:07 | 30 | 🟢 ON TRACK | No
BJ-110 | 17 | 2P | Low | Delta Co | 2026-06-08 06:40 | 2026-07-08 06:40 | 30 | 🟢 ON TRACK | No
BJ-111 | 25 | RW | Low | Alpha Corp | 2026-06-14 12:21 | 2026-07-14 12:21 | 30 | 🟢 ON TRACK | No
BJ-107 | 20 | SEG | Low | Beta Ltd | 2026-06-05 14:13 | 2026-07-05 14:13 | 30 | 🟢 ON TRACK | No
BJ-112 | 17 | 2P | Low | Alpha Corp | 2026-06-15 17:14 | 2026-07-15 17:14 | 30 | 🟢 ON TRACK | No
BJ-114 | 50 | SEG | High | Gamma Inc | 2026-06-29 04:25 | 2026-07-29 04:25 | 30 | 🟢 ON TRACK | No
BJ-115 | 46 | 2P | High | Beta Ltd | 2026-08-05 00:47 | 2026-09-04 00:47 | 30 | 🟢 ON TRACK | No
BJ-116 | 54 | 2P | High | Delta Co | 2026-06-20 21:41 | 2026-07-20 21:41 | 30 | 🟢 ON TRACK | No
BJ-118 | 28 | SOL | Medium | Alpha Corp | 2026-07-02 10:11 | 2026-08-01 10:11 | 30 | 🟢 ON TRACK | No
BJ-119 | 63 | SOL | High | Gamma Inc | 2026-06-21 11:01 | 2026-07-21 11:01 | 30 | 🟢 ON TRACK | No
BJ-120 | 46 | 2P | High | Beta Ltd | 2026-09-05 18:50 | 2026-10-05 18:50 | 30 | 🟢 ON TRACK | No
BJ-113 | 9 | SEG | Low | Delta Co | 2026-07-29 19:53 | 2026-08-28 19:53 | 30 | 🟢 ON TRACK | No
BJ-121 | 57 | RW | High | Alpha Corp | 2026-07-06 20:51 | 2026-08-05 20:51 | 30 | 🟢 ON TRACK | No
BJ-123 | 46 | RW | High | Beta Ltd | 2026-09-19 08:43 | 2026-10-19 08:43 | 30 | 🟢 ON TRACK | No
BJ-117 | 15 | RW | Low | Alpha Corp | 2026-08-29 15:44 | 2026-09-28 15:44 | 30 | 🟢 ON TRACK | No
BJ-122 | 54 | SOL | High | Gamma Inc | 2026-06-22 02:34 | 2026-07-22 02:34 | 30 | 🟢 ON TRACK | No
BJ-124 | 42 | 2P | Medium | Beta Ltd | 2026-07-11 05:18 | 2026-08-10 05:18 | 30 | 🟢 ON TRACK | No
BJ-126 | 42 | 2P | Medium | Delta Co | 2026-06-22 18:08 | 2026-07-22 18:08 | 30 | 🟢 ON TRACK | No
BJ-127 | 15 | RW | Low | Alpha Corp | 2026-07-18 19:31 | 2026-08-17 19:31 | 30 | 🟢 ON TRACK | No
BJ-128 | 46 | 2P | High | Gamma Inc | 2026-07-12 21:47 | 2026-08-11 21:47 | 30 | 🟢 ON TRACK | No
BJ-125 | 25 | SEG | Low | Beta Ltd | 2026-07-15 13:45 | 2026-08-14 13:45 | 30 | 🟢 ON TRACK | No
BJ-129 | 9 | RW | Low | Delta Co | 2026-07-13 08:53 | 2026-08-12 08:53 | 30 | 🟢 ON TRACK | No
BJ-130 | 57 | RW | High | Alpha Corp | 2026-09-26 11:50 | 2026-10-26 11:50 | 30 | 🟢 ON TRACK | No
BJ-133 | 25 | RW | Low | Beta Ltd | 2026-07-15 12:00 | 2026-08-14 12:00 | 30 | 🟢 ON TRACK | No
BJ-131 | 70 | 2P | High | Alpha Corp | 2026-07-14 20:27 | 2026-08-13 20:27 | 30 | 🟢 ON TRACK | No
BJ-134 | 15 | RW | Low | Gamma Inc | 2026-07-17 01:47 | 2026-08-16 01:47 | 30 | 🟢 ON TRACK | No
BJ-135 | 28 | 2P | Medium | Beta Ltd | 2026-10-24 13:48 | 2026-11-23 13:48 | 30 | 🟢 ON TRACK | No
BJ-132 | 57 | SOL | High | Delta Co | 2026-10-03 21:36 | 2026-11-02 21:36 | 30 | 🟢 ON TRACK | No
BJ-136 | 20 | RW | Low | Alpha Corp | 2026-07-18 20:00 | 2026-08-17 20:00 | 30 | 🟢 ON TRACK | No
BJ-137 | 34 | RW | Medium | Gamma Inc | 2026-07-21 09:45 | 2026-08-20 09:45 | 30 | 🟢 ON TRACK | No
BJ-140 | 54 | RW | High | Beta Ltd | 2026-11-04 23:08 | 2026-12-04 23:08 | 30 | 🟢 ON TRACK | No
BJ-138 | 9 | RW | Low | Delta Co | 2026-10-30 20:54 | 2026-11-29 20:54 | 30 | 🟢 ON TRACK | No
BJ-144 | 63 | RW | High | Alpha Corp | 2026-07-22 04:00 | 2026-08-21 04:00 | 30 | 🟢 ON TRACK | No
BJ-146 | 20 | RW | Low | Beta Ltd | 2026-08-19 05:53 | 2026-09-18 05:53 | 30 | 🟢 ON TRACK | No
BJ-139 | 15 | RW | Low | Alpha Corp | 2026-07-19 07:07 | 2026-08-18 07:07 | 30 | 🟢 ON TRACK | No
BJ-141 | 50 | SOL | High | Gamma Inc | 2026-07-21 01:20 | 2026-08-20 01:20 | 30 | 🟢 ON TRACK | No
BJ-142 | 9 | RW | Low | Beta Ltd | 2026-07-21 16:53 | 2026-08-20 16:53 | 30 | 🟢 ON TRACK | No
BJ-147 | 34 | SOL | Medium | Delta Co | 2026-07-26 10:13 | 2026-08-25 10:13 | 30 | 🟢 ON TRACK | No
BJ-150 | 34 | SOL | Medium | Alpha Corp | 2026-07-30 16:27 | 2026-08-29 16:27 | 30 | 🟢 ON TRACK | No
BJ-151 | 25 | SOL | Low | Gamma Inc | 2026-08-02 04:27 | 2026-09-01 04:27 | 30 | 🟢 ON TRACK | No
BJ-152 | 34 | 2P | Medium | Beta Ltd | 2026-08-03 09:20 | 2026-09-02 09:20 | 30 | 🟢 ON TRACK | No
BJ-143 | 17 | SOL | Low | Delta Co | 2026-11-17 20:39 | 2026-12-17 20:39 | 30 | 🟢 ON TRACK | No
BJ-154 | 25 | RW | Low | Alpha Corp | 2026-09-14 11:58 | 2026-10-14 11:58 | 30 | 🟢 ON TRACK | No
BJ-156 | 25 | 2P | Low | Beta Ltd | 2027-01-10 02:07 | 2027-02-09 02:07 | 30 | 🟢 ON TRACK | No
BJ-145 | 15 | 2P | Low | Alpha Corp | 2026-08-07 16:07 | 2026-09-06 16:07 | 30 | 🟢 ON TRACK | No
BJ-153 | 34 | SEG | Medium | Gamma Inc | 2026-09-11 23:58 | 2026-10-11 23:58 | 30 | 🟢 ON TRACK | No
BJ-160 | 34 | 2P | Medium | Beta Ltd | 2026-08-04 09:47 | 2026-09-03 09:47 | 30 | 🟢 ON TRACK | No
BJ-158 | 54 | 2P | High | Delta Co | 2026-08-03 22:40 | 2026-09-02 22:40 | 30 | 🟢 ON TRACK | No
BJ-157 | 50 | SEG | High | Alpha Corp | 2027-01-16 09:13 | 2027-02-15 09:13 | 30 | 🟢 ON TRACK | No
BJ-159 | 54 | RW | High | Gamma Inc | 2026-09-21 10:38 | 2026-10-21 10:38 | 30 | 🟢 ON TRACK | No
BJ-148 | 9 | SEG | Low | Beta Ltd | 2026-08-21 17:53 | 2026-09-20 17:53 | 30 | 🟢 ON TRACK | No
BJ-161 | 30 | SEG | Medium | Delta Co | 2027-02-16 07:08 | 2027-03-18 07:08 | 30 | 🟢 ON TRACK | No
BJ-149 | 9 | 2P | Low | Alpha Corp | 2026-07-29 04:53 | 2026-08-28 04:53 | 30 | 🟢 ON TRACK | No
BJ-163 | 70 | SOL | High | Beta Ltd | 2026-08-05 12:27 | 2026-09-04 12:27 | 30 | 🟢 ON TRACK | No
BJ-164 | 42 | SOL | Medium | Alpha Corp | 2026-08-06 12:53 | 2026-09-05 12:53 | 30 | 🟢 ON TRACK | No
BJ-168 | 20 | 2P | Low | Gamma Inc | 2026-08-10 12:27 | 2026-09-09 12:27 | 30 | 🟢 ON TRACK | No
BJ-155 | 17 | RW | Low | Beta Ltd | 2026-11-24 01:32 | 2026-12-24 01:32 | 30 | 🟢 ON TRACK | No
BJ-167 | 54 | 2P | High | Delta Co | 2026-08-09 07:33 | 2026-09-08 07:33 | 30 | 🟢 ON TRACK | No
BJ-166 | 50 | SOL | High | Alpha Corp | 2027-03-05 23:58 | 2027-04-04 23:58 | 30 | 🟢 ON TRACK | No
BJ-162 | 17 | SOL | Low | Gamma Inc | 2026-09-27 13:18 | 2026-10-27 13:18 | 30 | 🟢 ON TRACK | No
BJ-165 | 17 | 2P | Low | Beta Ltd | 2027-02-22 12:01 | 2027-03-24 12:01 | 30 | 🟢 ON TRACK | No
BJ-169 | 17 | SEG | Low | Delta Co | 2026-08-20 01:06 | 2026-09-19 01:06 | 30 | 🟢 ON TRACK | No

## WhatIf_Scenario
WHAT-IF SCENARIO PLANNER
SCENARIO INPUTS |  | SCENARIO IMPACT
Shift Hours — General Workman (hrs/day) | 21.6 | Stage | Current Load | Current Cap | Current Util% | Scenario Cap | Scenario Util%
Shift Hours — Contract Workman (hrs/day) | 22.4 | VTL | 7040 | 32448 | 21.7% | 29203.2 | 24.11%
Total Jobs in Plan | 70 | SPM | 10588 | 48672 | 21.75% | 43804.8 | 24.17%
Plan Start Date | 2026-04-01 07:00 | CARVING | 8456 | 48672 | 17.37% | 43804.8 | 19.3%
Additional Machines (VTL) | 0 | EDM | 8620 | 243360 | 3.542% | 219024 | 3.936%
Additional Machines (SPM) | 0 | ENG | 9292 | 113568 | 8.182% | 102211.2 | 9.091%
Additional Machines (EDM) | 0 | VENT | 7402 | 64896 | 11.41% | 58406.4 | 12.67%
% Productivity Gain (%) | 0 | FID | 7338 | 81120 | 9.046% | 73008 | 10.05%
|  | QC | 6460 | 40560 | 15.93% | 36504 | 17.7%

## 4Week_Horizon
ROLLING 4-WEEK PRODUCTION HORIZON
Horizon Start (Today): | 2026-04-07 |  | Horizon End (Today+28): | 2026-05-05
Job ID | Size | Type | Priority | Customer | Status | Plan Start | Plan End | Due Date | Buffer Days | RAG | Current Stage
BJ-104 | 28 | 2P | Medium | Alpha Corp | Released | 2026-04-09 01:40 | 2026-06-22 16:51 | 2026-07-22 16:51 | 30 | 🟢 | QC
BJ-101 | 42 | SOL | Medium | Beta Ltd | On Hold | 2026-04-01 07:00 | 2026-05-28 08:50 | 2026-06-27 08:50 | 30 | 🟢 | QC
BJ-105 | 28 | RW | Medium | Alpha Corp | Released | 2026-04-13 10:07 | 2026-06-04 22:40 | 2026-07-04 22:40 | 30 | 🟢 | QC
BJ-100 | 25 | SEG | Low | Gamma Inc | Released | 2026-04-01 07:00 | 2026-04-20 08:09 | 2026-05-20 08:09 | 30 | 🟢 | QC
BJ-102 | 34 | SEG | Medium | Beta Ltd | Cancelled | 2026-04-03 21:13 | 2026-04-26 15:49 | 2026-05-26 15:49 | 30 | 🟢 | QC
BJ-103 | 20 | RW | Low | Delta Co | Released | 2026-04-06 11:27 | 2026-06-03 04:27 | 2026-07-03 04:27 | 30 | 🟢 | QC
BJ-108 | 70 | RW | High | Alpha Corp | Released | 2026-04-18 12:20 | 2026-06-25 22:38 | 2026-07-25 22:38 | 30 | 🟢 | QC
BJ-106 | 15 | RW | Low | Gamma Inc | On Hold | 2026-04-01 07:00 | 2026-05-30 09:06 | 2026-06-29 09:06 | 30 | 🟢 | QC
BJ-109 | 30 | RW | Medium | Beta Ltd | Released | 2026-04-16 15:53 | 2026-06-06 19:07 | 2026-07-06 19:07 | 30 | 🟢 | QC
BJ-110 | 17 | 2P | Low | Delta Co | Released | 2026-04-18 05:40 | 2026-06-08 06:40 | 2026-07-08 06:40 | 30 | 🟢 | QC
BJ-111 | 25 | RW | Low | Alpha Corp | Released | 2026-04-20 13:13 | 2026-06-14 12:21 | 2026-07-14 12:21 | 30 | 🟢 | QC
BJ-107 | 20 | SEG | Low | Beta Ltd | On Hold | 2026-04-15 06:33 | 2026-06-05 14:13 | 2026-07-05 14:13 | 30 | 🟢 | QC
BJ-112 | 17 | 2P | Low | Alpha Corp | Released | 2026-04-26 09:13 | 2026-06-15 17:14 | 2026-07-15 17:14 | 30 | 🟢 | QC
BJ-114 | 50 | SEG | High | Gamma Inc | Released | 2026-04-21 07:00 | 2026-06-29 04:25 | 2026-07-29 04:25 | 30 | 🟢 | QC
BJ-115 | 46 | 2P | High | Beta Ltd | Cancelled | 2026-04-21 15:53 | 2026-08-05 00:47 | 2026-09-04 00:47 | 30 | 🟢 | QC
BJ-116 | 54 | 2P | High | Delta Co | Released | 2026-04-27 23:00 | 2026-06-20 21:41 | 2026-07-20 21:41 | 30 | 🟢 | QC
BJ-118 | 28 | SOL | Medium | Alpha Corp | Released | 2026-04-25 13:13 | 2026-07-02 10:11 | 2026-08-01 10:11 | 30 | 🟢 | QC
BJ-119 | 63 | SOL | High | Gamma Inc | On Hold | 2026-05-03 03:27 | 2026-06-21 11:01 | 2026-07-21 11:01 | 30 | 🟢 | QC
⚪
BJ-113 | 9 | SEG | Low | Delta Co | Released | 2026-04-07 18:33 | 2026-07-29 19:53 | 2026-08-28 19:53 | 30 | 🟢 | QC
BJ-121 | 57 | RW | High | Alpha Corp | Released | 2026-04-29 19:27 | 2026-07-06 20:51 | 2026-08-05 20:51 | 30 | 🟢 | QC
⚪
BJ-117 | 15 | RW | Low | Alpha Corp | Released | 2026-04-26 15:53 | 2026-08-29 15:44 | 2026-09-28 15:44 | 30 | 🟢 | QC
⚪
BJ-124 | 42 | 2P | Medium | Beta Ltd | Cancelled | 2026-05-04 01:40 | 2026-07-11 05:18 | 2026-08-10 05:18 | 30 | 🟢 | QC
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
⚪
Formulas:
Plan Start = IF([Job ID]="","",Job_Master!E4)
Plan End = IF([Job ID]="","",Job_Master!F4)
Due Date = IF([Job ID]="","",Job_Master!J4)

## Material_Stock
RAW MATERIAL / BLANK STOCK REGISTER
Job ID | Size | Type | No of Parts | Material Grade | Stock (Nos) | Required (Nos) | Deficit / Surplus | Status | Remarks
BJ-104 | 28 | 2P | 2 | EN36 | 22 | 2 | 20 | 🟢 OK
BJ-101 | 42 | SOL | 4 | EN36 | 2 | 4 | -2 | 🟡 Low Stock
BJ-105 | 28 | RW | 2 | EN19 | 10 | 2 | 8 | 🟢 OK
BJ-100 | 25 | SEG | 6 | EN19 | 9 | 6 | 3 | 🟢 OK
BJ-102 | 34 | SEG | 6 | EN36 | 25 | 6 | 19 | 🟢 OK
BJ-103 | 20 | RW | 2 | EN24 | 23 | 2 | 21 | 🟢 OK
BJ-108 | 70 | RW | 2 | EN24T | 19 | 2 | 17 | 🟢 OK
BJ-106 | 15 | RW | 2 | EN8 | 20 | 2 | 18 | 🟢 OK
BJ-109 | 30 | RW | 2 | EN19 | 3 | 2 | 1 | 🟢 OK
BJ-110 | 17 | 2P | 2 | EN24 | 4 | 2 | 2 | 🟢 OK
BJ-111 | 25 | RW | 2 | EN19 | 9 | 2 | 7 | 🟢 OK
BJ-107 | 20 | SEG | 6 | EN24 | 21 | 6 | 15 | 🟢 OK
BJ-112 | 17 | 2P | 2 | EN24 | 19 | 2 | 17 | 🟢 OK
BJ-114 | 50 | SEG | 6 | EN36 | 24 | 6 | 18 | 🟢 OK
BJ-115 | 46 | 2P | 2 | EN36 | 24 | 2 | 22 | 🟢 OK
BJ-116 | 54 | 2P | 2 | EN24T | 15 | 2 | 13 | 🟢 OK
BJ-118 | 28 | SOL | 4 | EN19 | 16 | 4 | 12 | 🟢 OK
BJ-119 | 63 | SOL | 4 | EN24T | 10 | 4 | 6 | 🟢 OK
BJ-120 | 46 | 2P | 2 | EN36 | 7 | 2 | 5 | 🟢 OK
BJ-113 | 9 | SEG | 6 | EN8 | 15 | 6 | 9 | 🟢 OK
BJ-121 | 57 | RW | 2 | EN24T | 10 | 2 | 8 | 🟢 OK
BJ-123 | 46 | RW | 2 | EN36 | 8 | 2 | 6 | 🟢 OK
BJ-117 | 15 | RW | 2 | EN8 | 5 | 2 | 3 | 🟢 OK
BJ-122 | 54 | SOL | 4 | EN24T | 14 | 4 | 10 | 🟢 OK
BJ-124 | 42 | 2P | 2 | EN36 | 13 | 2 | 11 | 🟢 OK
BJ-126 | 42 | 2P | 2 | EN36 | 21 | 2 | 19 | 🟢 OK
BJ-127 | 15 | RW | 2 | EN8 | 3 | 2 | 1 | 🟢 OK
BJ-128 | 46 | 2P | 2 | EN36 | 16 | 2 | 14 | 🟢 OK
BJ-125 | 25 | SEG | 6 | EN19 | 5 | 6 | -1 | 🟡 Low Stock
BJ-129 | 9 | RW | 2 | EN8 | 4 | 2 | 2 | 🟢 OK
BJ-130 | 57 | RW | 2 | EN24T | 11 | 2 | 9 | 🟢 OK
BJ-133 | 25 | RW | 2 | EN19 | 21 | 2 | 19 | 🟢 OK
BJ-131 | 70 | 2P | 2 | EN24T | 20 | 2 | 18 | 🟢 OK
BJ-134 | 15 | RW | 2 | EN8 | 24 | 2 | 22 | 🟢 OK
BJ-135 | 28 | 2P | 2 | EN19 | 3 | 2 | 1 | 🟢 OK
BJ-132 | 57 | SOL | 4 | EN24T | 9 | 4 | 5 | 🟢 OK
BJ-136 | 20 | RW | 2 | EN24 | 4 | 2 | 2 | 🟢 OK
BJ-137 | 34 | RW | 2 | EN36 | 5 | 2 | 3 | 🟢 OK
BJ-140 | 54 | RW | 2 | EN24T | 10 | 2 | 8 | 🟢 OK
BJ-138 | 9 | RW | 2 | EN8 | 22 | 2 | 20 | 🟢 OK
BJ-144 | 63 | RW | 2 | EN24T | 7 | 2 | 5 | 🟢 OK
BJ-146 | 20 | RW | 2 | EN24 | 13 | 2 | 11 | 🟢 OK
BJ-139 | 15 | RW | 2 | EN8 | 23 | 2 | 21 | 🟢 OK
BJ-141 | 50 | SOL | 4 | EN36 | 24 | 4 | 20 | 🟢 OK
BJ-142 | 9 | RW | 2 | EN8 | 22 | 2 | 20 | 🟢 OK
BJ-147 | 34 | SOL | 4 | EN36 | 21 | 4 | 17 | 🟢 OK
BJ-150 | 34 | SOL | 4 | EN36 | 7 | 4 | 3 | 🟢 OK
BJ-151 | 25 | SOL | 4 | EN19 | 25 | 4 | 21 | 🟢 OK
BJ-152 | 34 | 2P | 2 | EN36 | 7 | 2 | 5 | 🟢 OK
BJ-143 | 17 | SOL | 4 | EN24 | 14 | 4 | 10 | 🟢 OK
BJ-154 | 25 | RW | 2 | EN19 | 22 | 2 | 20 | 🟢 OK
BJ-156 | 25 | 2P | 2 | EN19 | 19 | 2 | 17 | 🟢 OK
BJ-145 | 15 | 2P | 2 | EN8 | 23 | 2 | 21 | 🟢 OK
BJ-153 | 34 | SEG | 6 | EN36 | 3 | 6 | -3 | 🟡 Low Stock
BJ-160 | 34 | 2P | 2 | EN36 | 3 | 2 | 1 | 🟢 OK
BJ-158 | 54 | 2P | 2 | EN24T | 14 | 2 | 12 | 🟢 OK
BJ-157 | 50 | SEG | 6 | EN36 | 4 | 6 | -2 | 🟡 Low Stock
BJ-159 | 54 | RW | 2 | EN24T | 20 | 2 | 18 | 🟢 OK
BJ-148 | 9 | SEG | 6 | EN8 | 12 | 6 | 6 | 🟢 OK
BJ-161 | 30 | SEG | 6 | EN19 | 22 | 6 | 16 | 🟢 OK
BJ-149 | 9 | 2P | 2 | EN8 | 14 | 2 | 12 | 🟢 OK
BJ-163 | 70 | SOL | 4 | EN24T | 16 | 4 | 12 | 🟢 OK
BJ-164 | 42 | SOL | 4 | EN36 | 10 | 4 | 6 | 🟢 OK
BJ-168 | 20 | 2P | 2 | EN24 | 9 | 2 | 7 | 🟢 OK
BJ-155 | 17 | RW | 2 | EN24 | 19 | 2 | 17 | 🟢 OK
BJ-167 | 54 | 2P | 2 | EN24T | 10 | 2 | 8 | 🟢 OK
BJ-166 | 50 | SOL | 4 | EN36 | 20 | 4 | 16 | 🟢 OK
BJ-162 | 17 | SOL | 4 | EN24 | 20 | 4 | 16 | 🟢 OK
BJ-165 | 17 | 2P | 2 | EN24 | 13 | 2 | 11 | 🟢 OK
BJ-169 | 17 | SEG | 6 | EN24 | 6 | 6 | 0 | 🟢 OK
* Stock (Nos) = manual input per job

## Shift_Roster
SHIFT ROSTER — 7-DAY WORKING PLAN
Shift hours & qty from Settings sheet
Shift | Category | Timing | Net Hrs/Day | Avl Hrs/Day | Gen Qty | Cont Qty | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Weekly Gen Hrs | Weekly Cont Hrs | Total Weekly Hrs
Shift A | Gen | 07:00 – 15:00 | 8 | 7.2 | 0 | 0 | A | A | A | A | A | OFF | OFF | 0 | 0 | 0
Shift B | Gen | 15:00 – 23:00 | 8 | 7.2 | 0 | 0 | B | B | B | B | B | OFF | OFF | 0 | 0 | 0
Shift C | Gen | 23:00 – 07:00 | 8 | 7.2 | 0 | 0 | C | C | C | C | C | OFF | OFF | 0 | 0 | 0
Shift S1 | Cont | 08:00 – 20:00 | 12 | 11.2 | 0 | 0 | S1 | S1 | S1 | S1 | S1 | S1 | OFF | 0 | 0 | 0
Shift S2 | Cont | 20:00 – 08:00 | 12 | 11.2 | 0 | 0 | S2 | S2 | S2 | S2 | S2 | S2 | OFF | 0 | 0 | 0
TOTAL | [13 empty] | 0 | 0 | 0
LEGEND: | Shift A | Shift B | Shift C | Shift S1 | Shift S2 | OFF

## Downtime_Register
MACHINE DOWNTIME / PM REGISTER
Machine ID | Operation | Next PM Date | PM Duration (Hrs) | PM Frequency (Wks) | Last Downtime Date | Downtime (Hrs) | Reason | Action Taken | Status | Remarks
VTL-MC-01 | VTL | 2026-04-21 | 6 | 4
VTL-MC-02 | VTL | 2027-05-14 | 6 | 4
VTL-MC-03 | VTL | 2026-06-01 | 6 | 4
VTL-MC-04 | VTL | 2027-05-10 | 6 | 4
SPM-MC-01 | SPM | 2026-09-20 | 6 | 4
SPM-MC-02 | SPM | 2027-03-13 | 6 | 4
SPM-MC-03 | SPM | 2026-03-23 | 6 | 4
SPM-MC-04 | SPM | 2026-06-24 | 6 | 4
SPM-MC-05 | SPM | 2026-09-06 | 6 | 4
SPM-MC-06 | SPM | 2026-06-03 | 6 | 4
CARVING-MC-01 | CARVING | 2027-01-31 | 6 | 4
CARVING-MC-02 | CARVING | 2026-09-17 | 6 | 4
CARVING-MC-03 | CARVING | 2026-10-01 | 6 | 4
CARVING-MC-04 | CARVING | 2026-08-03 | 6 | 4
CARVING-MC-05 | CARVING | 2026-08-04 | 6 | 4
CARVING-MC-06 | CARVING | 2027-01-10 | 6 | 4
EDM-MC-01 | EDM | 2026-03-11 | 6 | 4
EDM-MC-02 | EDM | 2026-05-18 | 6 | 4
EDM-MC-03 | EDM | 2026-02-04 | 6 | 4
EDM-MC-04 | EDM | 2026-03-30 | 6 | 4
EDM-MC-05 | EDM | 2026-07-22 | 6 | 4
EDM-MC-06 | EDM | 2026-11-04 | 6 | 4
EDM-MC-07 | EDM | 2026-07-05 | 6 | 4
EDM-MC-08 | EDM | 2026-09-26 | 6 | 4
EDM-MC-09 | EDM | 2026-08-03 | 6 | 4
EDM-MC-10 | EDM | 2027-04-26 | 6 | 4
EDM-MC-11 | EDM | 2026-03-17 | 6 | 4
EDM-MC-12 | EDM | 2026-11-11 | 6 | 4
EDM-MC-13 | EDM | 2026-07-09 | 6 | 4
EDM-MC-14 | EDM | 2027-03-01 | 6 | 4
EDM-MC-15 | EDM | 2026-12-01 | 6 | 4
EDM-MC-16 | EDM | 2026-03-24 | 6 | 4
EDM-MC-17 | EDM | 2027-04-27 | 6 | 4
EDM-MC-18 | EDM | 2026-07-22 | 6 | 4
EDM-MC-19 | EDM | 2026-08-29 | 6 | 4
EDM-MC-20 | EDM | 2026-01-18 | 6 | 4
EDM-MC-21 | EDM | 2027-03-30 | 6 | 4
EDM-MC-22 | EDM | 2026-08-05 | 6 | 4
EDM-MC-23 | EDM | 2026-10-29 | 6 | 4
EDM-MC-24 | EDM | 2026-03-16 | 6 | 4
EDM-MC-25 | EDM | 2026-03-17 | 6 | 4
EDM-MC-26 | EDM | 2026-06-29 | 6 | 4
EDM-MC-27 | EDM | 2026-06-15 | 6 | 4
EDM-MC-28 | EDM | 2026-06-09 | 6 | 4
EDM-MC-29 | EDM | 2027-04-16 | 6 | 4
EDM-MC-30 | EDM | 2026-03-25 | 6 | 4
ENG-MC-01 | ENG | 2026-03-09 | 6 | 4
ENG-MC-02 | ENG | 2026-07-27 | 6 | 4
ENG-MC-03 | ENG | 2027-02-15 | 6 | 4
ENG-MC-04 | ENG | 2027-03-04 | 6 | 4
ENG-MC-05 | ENG | 2026-01-27 | 6 | 4
ENG-MC-06 | ENG | 2026-02-21 | 6 | 4
ENG-MC-07 | ENG | 2026-09-07 | 6 | 4
ENG-MC-08 | ENG | 2026-12-27 | 6 | 4
ENG-MC-09 | ENG | 2027-03-25 | 6 | 4
ENG-MC-10 | ENG | 2026-12-21 | 6 | 4
ENG-MC-11 | ENG | 2027-05-10 | 6 | 4
ENG-MC-12 | ENG | 2027-03-08 | 6 | 4
ENG-MC-13 | ENG | 2026-12-15 | 6 | 4
ENG-MC-14 | ENG | 2026-07-16 | 6 | 4
VENT-MC-01 | VENT | 2026-07-27 | 6 | 4
VENT-MC-02 | VENT | 2026-06-18 | 6 | 4
VENT-MC-03 | VENT | 2026-02-01 | 6 | 4
VENT-MC-04 | VENT | 2026-08-21 | 6 | 4
VENT-MC-05 | VENT | 2027-01-07 | 6 | 4
VENT-MC-06 | VENT | 2026-11-21 | 6 | 4
VENT-MC-07 | VENT | 2026-07-31 | 6 | 4
VENT-MC-08 | VENT | 2026-04-26 | 6 | 4
FID-MC-01 | FID | 2026-03-25 | 6 | 4
FID-MC-02 | FID | 2026-04-30 | 6 | 4
FID-MC-03 | FID | 2027-04-06 | 6 | 4
FID-MC-04 | FID | 2026-10-23 | 6 | 4
FID-MC-05 | FID | 2027-02-13 | 6 | 4
FID-MC-06 | FID | 2026-03-07 | 6 | 4
FID-MC-07 | FID | 2027-01-15 | 6 | 4
FID-MC-08 | FID | 2026-11-02 | 6 | 4
FID-MC-09 | FID | 2026-05-23 | 6 | 4
FID-MC-10 | FID | 2027-04-06 | 6 | 4
QC-MC-01 | QC | 2027-05-11 | 6 | 4
QC-MC-02 | QC | 2026-04-03 | 6 | 4
QC-MC-03 | QC | 2026-05-30 | 6 | 4
QC-MC-04 | QC | 2026-06-22 | 6 | 4
QC-MC-05 | QC | 2026-12-17 | 6 | 4
Total Machines: | 83 |  | Total PM Hrs: | 498 |  | Open Downtimes: | 0

## OPR_BR1
OPR_BR1
Part No | 1
Size | VTL | SPM | CARVING | EDM | ENG | VENT | FID | QC | Min ID | Max OD
9 | 8 | 6 | 14 | 5 | 2 | 2 | 8 | 4 | 100 | 600
15 | 6 | 8 | 10 | 16 | 6 | 6 | 12 | 5 | 300 | 800
17 | 9 | 16 | 20 | 8 | 8 | 6 | 7 | 5 | 500 | 1000
20 | 10 | 7 | 13 | 21 | 8 | 12 | 21 | 4 | 700 | 1200
25 | 9 | 13 | 11 | 15 | 16 | 14 | 22 | 7 | 900 | 1400
28 | 6 | 24 | 34 | 21 | 14 | 12 | 24 | 7 | 1100 | 1600
30 | 8 | 25 | 17 | 22 | 7 | 9 | 14 | 7 | 1300 | 1800
34 | 11 | 11 | 18 | 14 | 15 | 15 | 13 | 7 | 1500 | 2000
42 | 13 | 23 | 39 | 19 | 15 | 14 | 29 | 5 | 1700 | 2200
46 | 23 | 28 | 41 | 25 | 19 | 15 | 33 | 11 | 1900 | 2400
50 | 16 | 27 | 40 | 37 | 24 | 21 | 29 | 13 | 2100 | 2600
54 | 12 | 37 | 41 | 30 | 18 | 24 | 28 | 6 | 2300 | 2800
57 | 13 | 28 | 38 | 34 | 26 | 21 | 20 | 14 | 2500 | 3000
63 | 14 | 42 | 45 | 23 | 14 | 24 | 36 | 10 | 2700 | 3200
70 | 22 | 45 | 30 | 35 | 30 | 19 | 42 | 14 | 2900 | 3400

## OPR_BR2
OPR_BR2
Part No | 2
Size | VTL | SPM | CARVING | EDM | ENG | VENT | FID | QC | Min ID | Max OD
9 | 2 | 14 | 8 | 14 | 9 | 6 | 13 | 3 | 100 | 600
15 | 5 | 16 | 16 | 13 | 11 | 7 | 9 | 2 | 300 | 800
17 | 4 | 19 | 17 | 8 | 7 | 10 | 15 | 3 | 500 | 1000
20 | 12 | 15 | 21 | 16 | 11 | 8 | 17 | 3 | 700 | 1200
25 | 10 | 19 | 21 | 20 | 11 | 11 | 22 | 6 | 900 | 1400
28 | 17 | 21 | 29 | 19 | 15 | 12 | 14 | 5 | 1100 | 1600
30 | 10 | 21 | 18 | 19 | 14 | 12 | 23 | 8 | 1300 | 1800
34 | 18 | 29 | 27 | 17 | 7 | 12 | 15 | 4 | 1500 | 2000
42 | 11 | 16 | 43 | 34 | 16 | 15 | 34 | 7 | 1700 | 2200
46 | 13 | 24 | 33 | 18 | 17 | 20 | 21 | 8 | 1900 | 2400
50 | 16 | 37 | 40 | 21 | 21 | 12 | 19 | 10 | 2100 | 2600
54 | 16 | 19 | 36 | 27 | 24 | 19 | 26 | 9 | 2300 | 2800
57 | 24 | 30 | 49 | 18 | 21 | 28 | 25 | 8 | 2500 | 3000
63 | 15 | 31 | 29 | 40 | 15 | 17 | 29 | 7 | 2700 | 3200
70 | 21 | 38 | 49 | 35 | 29 | 29 | 46 | 14 | 2900 | 3400

## OPR_CR2
OPR_CR2
Part No | 2
Size | VTL | SPM | CARVING | EDM | ENG | VENT | FID | QC | Min ID | Max OD
9 | 3 | 6 | 7 | 9 | 6 | 5 | 7 | 4 | 100 | 600
15 | 8 | 9 | 17 | 18 | 5 | 6 | 10 | 6 | 300 | 800
17 | 11 | 15 | 13 | 15 | 9 | 8 | 7 | 4 | 500 | 1000
20 | 8 | 15 | 28 | 9 | 11 | 5 | 13 | 4 | 700 | 1200
25 | 12 | 11 | 20 | 8 | 13 | 15 | 17 | 8 | 900 | 1400
28 | 10 | 17 | 23 | 9 | 17 | 13 | 15 | 5 | 1100 | 1600
30 | 7 | 21 | 23 | 19 | 16 | 14 | 27 | 8 | 1300 | 1800
34 | 12 | 20 | 14 | 21 | 12 | 14 | 22 | 8 | 1500 | 2000
42 | 17 | 33 | 43 | 30 | 11 | 20 | 34 | 10 | 1700 | 2200
46 | 13 | 22 | 20 | 16 | 14 | 20 | 28 | 5 | 1900 | 2400
50 | 23 | 33 | 29 | 20 | 14 | 20 | 29 | 11 | 2100 | 2600
54 | 16 | 40 | 53 | 24 | 19 | 21 | 24 | 13 | 2300 | 2800
57 | 19 | 18 | 54 | 26 | 20 | 23 | 26 | 7 | 2500 | 3000
63 | 31 | 25 | 31 | 24 | 23 | 24 | 38 | 12 | 2700 | 3200
70 | 30 | 33 | 54 | 25 | 31 | 17 | 42 | 17 | 2900 | 3400

## OPR_CR3
OPR_CR3
Part No | 3
Size | VTL | SPM | CARVING | EDM | ENG | VENT | FID | QC | Min ID | Max OD
9 | 5 | 5 | 11 | 10 | 9 | 9 | 6 | 4 | 100 | 600
15 | 4 | 6 | 7 | 12 | 10 | 6 | 15 | 5 | 300 | 800
17 | 7 | 18 | 14 | 7 | 8 | 7 | 19 | 6 | 500 | 1000
20 | 7 | 18 | 14 | 17 | 11 | 10 | 18 | 6 | 700 | 1200
25 | 15 | 18 | 11 | 14 | 12 | 13 | 23 | 7 | 900 | 1400
28 | 11 | 21 | 26 | 16 | 6 | 6 | 25 | 6 | 1100 | 1600
30 | 9 | 18 | 25 | 20 | 7 | 14 | 16 | 9 | 1300 | 1800
34 | 11 | 24 | 31 | 19 | 14 | 11 | 12 | 6 | 1500 | 2000
42 | 18 | 17 | 36 | 26 | 11 | 16 | 32 | 9 | 1700 | 2200
46 | 16 | 26 | 43 | 22 | 24 | 12 | 33 | 9 | 1900 | 2400
50 | 12 | 20 | 36 | 28 | 12 | 20 | 28 | 8 | 2100 | 2600
54 | 17 | 37 | 37 | 18 | 20 | 22 | 25 | 6 | 2300 | 2800
57 | 19 | 32 | 24 | 42 | 19 | 17 | 34 | 11 | 2500 | 3000
63 | 18 | 24 | 41 | 22 | 16 | 13 | 36 | 12 | 2700 | 3200
70 | 25 | 26 | 43 | 22 | 28 | 19 | 23 | 14 | 2900 | 3400

## OPR_CR4
OPR_CR4
Part No | 4
Size | VTL | SPM | CARVING | EDM | ENG | VENT | FID | QC | Min ID | Max OD
9 | 5 | 13 | 6 | 9 | 2 | 7 | 13 | 3 | 100 | 600
15 | 12 | 7 | 22 | 5 | 11 | 12 | 13 | 3 | 300 | 800
17 | 4 | 19 | 15 | 17 | 5 | 11 | 6 | 4 | 500 | 1000
20 | 12 | 19 | 23 | 8 | 8 | 13 | 16 | 3 | 700 | 1200
25 | 7 | 17 | 28 | 13 | 11 | 13 | 18 | 7 | 900 | 1400
28 | 11 | 11 | 25 | 11 | 16 | 12 | 22 | 6 | 1100 | 1600
30 | 18 | 14 | 35 | 13 | 17 | 11 | 24 | 9 | 1300 | 1800
34 | 13 | 13 | 30 | 18 | 14 | 12 | 28 | 6 | 1500 | 2000
42 | 22 | 14 | 33 | 20 | 17 | 10 | 27 | 9 | 1700 | 2200
46 | 11 | 30 | 29 | 32 | 15 | 17 | 18 | 5 | 1900 | 2400
50 | 17 | 19 | 21 | 32 | 22 | 14 | 20 | 8 | 2100 | 2600
54 | 18 | 35 | 38 | 23 | 22 | 20 | 31 | 13 | 2300 | 2800
57 | 21 | 38 | 28 | 43 | 26 | 25 | 33 | 7 | 2500 | 3000
63 | 21 | 23 | 55 | 37 | 16 | 28 | 29 | 11 | 2700 | 3200
70 | 34 | 46 | 50 | 41 | 29 | 17 | 49 | 17 | 2900 | 3400

## OPR_RIM
OPR_RIM
Part No | 1
Size | VTL | SPM | CARVING | EDM | ENG | VENT | FID | QC | Min ID | Max OD
9 | 2 | 7 | 11 | 10 | 9 | 9 | 8 | 4 | 100 | 600
15 | 12 | 7 | 24 | 9 | 10 | 12 | 13 | 4 | 300 | 800
17 | 8 | 18 | 25 | 6 | 10 | 5 | 16 | 2 | 500 | 1000
20 | 8 | 12 | 23 | 13 | 14 | 13 | 17 | 5 | 700 | 1200
25 | 14 | 21 | 25 | 21 | 11 | 13 | 24 | 5 | 900 | 1400
28 | 10 | 12 | 29 | 22 | 15 | 17 | 21 | 3 | 1100 | 1600
30 | 16 | 23 | 27 | 24 | 8 | 14 | 24 | 8 | 1300 | 1800
34 | 18 | 13 | 18 | 22 | 17 | 19 | 22 | 4 | 1500 | 2000
42 | 17 | 29 | 24 | 24 | 22 | 9 | 19 | 11 | 1700 | 2200
46 | 22 | 25 | 38 | 21 | 10 | 12 | 30 | 8 | 1900 | 2400
50 | 22 | 25 | 21 | 24 | 21 | 18 | 20 | 6 | 2100 | 2600
54 | 18 | 36 | 24 | 33 | 12 | 16 | 36 | 10 | 2300 | 2800
57 | 20 | 29 | 46 | 39 | 24 | 20 | 22 | 10 | 2500 | 3000
63 | 25 | 20 | 53 | 31 | 25 | 16 | 22 | 11 | 2700 | 3200
70 | 31 | 43 | 65 | 23 | 22 | 17 | 22 | 17 | 2900 | 3400

## OPR_BPR
OPR_BPR
Part No | 2
Size | VTL | SPM | CARVING | EDM | ENG | VENT | FID | QC | Min ID | Max OD
9 | 5 | 13 | 14 | 9 | 4 | 6 | 8 | 2 | 100 | 600
15 | 6 | 12 | 11 | 12 | 12 | 10 | 12 | 6 | 300 | 800
17 | 10 | 12 | 17 | 11 | 4 | 4 | 17 | 3 | 500 | 1000
20 | 14 | 15 | 24 | 18 | 5 | 14 | 7 | 7 | 700 | 1200
25 | 7 | 13 | 13 | 15 | 13 | 16 | 19 | 7 | 900 | 1400
28 | 12 | 20 | 28 | 22 | 14 | 17 | 13 | 6 | 1100 | 1600
30 | 10 | 27 | 23 | 18 | 8 | 17 | 23 | 8 | 1300 | 1800
34 | 19 | 19 | 39 | 22 | 9 | 19 | 13 | 6 | 1500 | 2000
42 | 21 | 26 | 29 | 20 | 20 | 18 | 17 | 10 | 1700 | 2200
46 | 10 | 21 | 19 | 23 | 24 | 17 | 32 | 8 | 1900 | 2400
50 | 15 | 38 | 40 | 29 | 24 | 15 | 27 | 13 | 2100 | 2600
54 | 15 | 29 | 31 | 25 | 16 | 24 | 18 | 7 | 2300 | 2800
57 | 14 | 22 | 56 | 41 | 23 | 13 | 28 | 9 | 2500 | 3000
63 | 29 | 43 | 55 | 40 | 22 | 29 | 31 | 13 | 2700 | 3200
70 | 15 | 34 | 66 | 37 | 15 | 16 | 28 | 12 | 2900 | 3400

## Job_Master_Ring
JOB MASTER — RING PARTS
← Type to override auto date
Job ID | Size | Type | No of Parts | Overall Start | Overall End | Priority | End Month | Status | Due Date | Customer | time axis 2026-04-01 to 2026-05-30
RJ-101 | 15 | BR2 | 2 | 2026-07-17 07:00 | 2026-08-10 07:00 | High | Aug-2026 | Cancelled | 2026-09-09 07:00 | Gamma Inc
RJ-102 | 54 | BR2 | 2 | 2026-07-27 07:00 | 2026-10-09 07:00 | Medium | Oct-2026 | Released | 2026-11-08 07:00 | Gamma Inc
RJ-103 | 42 | CR3 | 3 | 2026-05-11 07:00 | 2026-07-18 07:00 | Medium | Jul-2026 | Cancelled | 2026-08-17 07:00 | Delta Co | bar: 2026-05-12 to 2026-05-30
RJ-104 | 42 | BPR | 2 | 2026-04-06 07:00 | 2026-05-19 07:00 | Low | May-2026 | Released | 2026-06-18 07:00 | Gamma Inc | bar: 2026-04-07 to 2026-05-19
RJ-105 | 42 | RIM | 1 | 2026-07-17 07:00 | 2026-08-28 07:00 | High | Aug-2026 | Cancelled | 2026-09-27 07:00 | Delta Co
RJ-106 | 9 | CR3 | 3 | 2026-06-22 07:00 | 2026-08-29 07:00 | High | Aug-2026 | Released | 2026-09-28 07:00 | Sigma Mfg
RJ-107 | 20 | BR2 | 2 | 2026-05-10 07:00 | 2026-07-05 07:00 | High | Jul-2026 | On Hold | 2026-08-04 07:00 | Beta Ltd | bar: 2026-05-11 to 2026-05-30
RJ-108 | 63 | BR1 | 1 | 2026-05-12 07:00 | 2026-07-11 07:00 | High | Jul-2026 | On Hold | 2026-08-10 07:00 | Gamma Inc | bar: 2026-05-13 to 2026-05-30
RJ-109 | 46 | BR2 | 2 | 2026-07-17 07:00 | 2026-08-21 07:00 | High | Aug-2026 | On Hold | 2026-09-20 07:00 | Beta Ltd
RJ-110 | 20 | CR2 | 2 | 2026-04-27 07:00 | 2026-06-18 07:00 | Low | Jun-2026 | Released | 2026-07-18 07:00 | Delta Co | bar: 2026-04-28 to 2026-05-30
RJ-111 | 50 | BR2 | 2 | 2026-07-15 07:00 | 2026-09-27 07:00 | Low | Sep-2026 | Cancelled | 2026-10-27 07:00 | Delta Co
RJ-112 | 46 | CR4 | 4 | 2026-07-14 07:00 | 2026-08-07 07:00 | Low | Aug-2026 | Released | 2026-09-06 07:00 | Delta Co
RJ-113 | 25 | BR1 | 1 | 2026-05-09 07:00 | 2026-07-02 07:00 | Low | Jul-2026 | Cancelled | 2026-08-01 07:00 | Gamma Inc | bar: 2026-05-10 to 2026-05-30
RJ-114 | 25 | BR2 | 2 | 2026-07-11 07:00 | 2026-09-20 07:00 | High | Sep-2026 | Cancelled | 2026-10-20 07:00 | Delta Co
RJ-115 | 34 | CR3 | 3 | 2026-06-10 07:00 | 2026-08-08 07:00 | High | Aug-2026 | On Hold | 2026-09-07 07:00 | Gamma Inc
RJ-116 | 15 | CR2 | 2 | 2026-05-25 07:00 | 2026-08-07 07:00 | High | Aug-2026 | On Hold | 2026-09-06 07:00 | Sigma Mfg | bar: 2026-05-26 to 2026-05-30
RJ-117 | 46 | BR2 | 2 | 2026-05-01 07:00 | 2026-06-29 07:00 | Low | Jun-2026 | On Hold | 2026-07-29 07:00 | Alpha Corp | bar: 2026-05-02 to 2026-05-30
RJ-118 | 63 | CR3 | 3 | 2026-06-11 07:00 | 2026-06-25 07:00 | Medium | Jun-2026 | Cancelled | 2026-07-25 07:00 | Gamma Inc
RJ-119 | 9 | CR2 | 2 | 2026-06-02 07:00 | 2026-07-27 07:00 | Low | Jul-2026 | Cancelled | 2026-08-26 07:00 | Beta Ltd
RJ-120 | 34 | CR4 | 4 | 2026-05-05 07:00 | 2026-07-20 07:00 | Medium | Jul-2026 | Cancelled | 2026-08-19 07:00 | Delta Co | bar: 2026-05-06 to 2026-05-30
RJ-121 | 20 | RIM | 1 | 2026-04-27 07:00 | 2026-06-24 07:00 | High | Jun-2026 | Released | 2026-07-24 07:00 | Sigma Mfg | bar: 2026-04-28 to 2026-05-30
RJ-122 | 34 | CR4 | 4 | 2026-06-29 07:00 | 2026-07-19 07:00 | Low | Jul-2026 | On Hold | 2026-08-18 07:00 | Alpha Corp
RJ-123 | 42 | BR1 | 1 | 2026-04-24 07:00 | 2026-07-08 07:00 | Low | Jul-2026 | Cancelled | 2026-08-07 07:00 | Gamma Inc | bar: 2026-04-25 to 2026-05-30
RJ-124 | 20 | RIM | 1 | 2026-05-25 07:00 | 2026-07-03 07:00 | Low | Jul-2026 | On Hold | 2026-08-02 07:00 | Alpha Corp | bar: 2026-05-26 to 2026-05-30
RJ-125 | 25 | BPR | 2 | 2026-07-01 07:00 | 2026-08-12 07:00 | High | Aug-2026 | Cancelled | 2026-09-11 07:00 | Alpha Corp
RJ-126 | 34 | BPR | 2 | 2026-07-08 07:00 | 2026-08-17 07:00 | Low | Aug-2026 | On Hold | 2026-09-16 07:00 | Sigma Mfg
RJ-127 | 57 | CR3 | 3 | 2026-05-05 07:00 | 2026-05-30 07:00 | High | May-2026 | On Hold | 2026-06-29 07:00 | Delta Co | bar: 2026-05-06 to 2026-05-30
RJ-128 | 30 | CR2 | 2 | 2026-07-21 07:00 | 2026-09-14 07:00 | Medium | Sep-2026 | Cancelled | 2026-10-14 07:00 | Delta Co
RJ-129 | 15 | BR1 | 1 | 2026-04-04 07:00 | 2026-04-29 07:00 | High | Apr-2026 | On Hold | 2026-05-29 07:00 | Beta Ltd | bar: 2026-04-06 to 2026-04-29
RJ-130 | 57 | CR4 | 4 | 2026-07-05 07:00 | 2026-09-03 07:00 | Low | Sep-2026 | Released | 2026-10-03 07:00 | Gamma Inc
RJ-131 | 9 | BPR | 2 | 2026-04-09 07:00 | 2026-06-15 07:00 | Low | Jun-2026 | Cancelled | 2026-07-15 07:00 | Sigma Mfg | bar: 2026-04-10 to 2026-05-30
RJ-132 | 42 | RIM | 1 | 2026-06-04 07:00 | 2026-08-14 07:00 | High | Aug-2026 | Cancelled | 2026-09-13 07:00 | Alpha Corp
RJ-133 | 15 | BR1 | 1 | 2026-07-14 07:00 | 2026-09-18 07:00 | Medium | Sep-2026 | On Hold | 2026-10-18 07:00 | Alpha Corp
RJ-134 | 42 | BPR | 2 | 2026-04-20 07:00 | 2026-05-21 07:00 | Low | May-2026 | Released | 2026-06-20 07:00 | Gamma Inc | bar: 2026-04-21 to 2026-05-21
RJ-135 | 63 | CR4 | 4 | 2026-06-09 07:00 | 2026-08-28 07:00 | Low | Aug-2026 | Cancelled | 2026-09-27 07:00 | Gamma Inc
RJ-136 | 50 | CR4 | 4 | 2026-06-28 07:00 | 2026-07-20 07:00 | Low | Jul-2026 | On Hold | 2026-08-19 07:00 | Sigma Mfg
RJ-137 | 30 | CR3 | 3 | 2026-04-16 07:00 | 2026-07-05 07:00 | Low | Jul-2026 | Released | 2026-08-04 07:00 | Gamma Inc | bar: 2026-04-17 to 2026-05-30
RJ-138 | 46 | BR1 | 1 | 2026-06-21 07:00 | 2026-08-12 07:00 | Low | Aug-2026 | Cancelled | 2026-09-11 07:00 | Alpha Corp
RJ-139 | 15 | BR2 | 2 | 2026-06-01 07:00 | 2026-08-11 07:00 | High | Aug-2026 | Cancelled | 2026-09-10 07:00 | Alpha Corp
RJ-140 | 25 | BR1 | 1 | 2026-04-09 07:00 | 2026-07-02 07:00 | High | Jul-2026 | Cancelled | 2026-08-01 07:00 | Delta Co | bar: 2026-04-10 to 2026-05-30
RJ-141 | 17 | BPR | 2 | 2026-05-13 07:00 | 2026-07-19 07:00 | Medium | Jul-2026 | On Hold | 2026-08-18 07:00 | Alpha Corp | bar: 2026-05-14 to 2026-05-30
RJ-142 | 54 | BR1 | 1 | 2026-06-12 07:00 | 2026-09-08 07:00 | High | Sep-2026 | Released | 2026-10-08 07:00 | Alpha Corp
RJ-143 | 46 | BR1 | 1 | 2026-04-28 07:00 | 2026-07-01 07:00 | Medium | Jul-2026 | On Hold | 2026-07-31 07:00 | Gamma Inc | bar: 2026-04-29 to 2026-05-30
RJ-144 | 54 | BR1 | 1 | 2026-06-01 07:00 | 2026-07-29 07:00 | High | Jul-2026 | Released | 2026-08-28 07:00 | Gamma Inc
RJ-145 | 34 | BR1 | 1 | 2026-06-15 07:00 | 2026-09-04 07:00 | High | Sep-2026 | On Hold | 2026-10-04 07:00 | Delta Co
RJ-146 | 54 | CR2 | 2 | 2026-06-12 07:00 | 2026-08-06 07:00 | Low | Aug-2026 | Released | 2026-09-05 07:00 | Alpha Corp
RJ-147 | 50 | CR3 | 3 | 2026-05-04 07:00 | 2026-07-18 07:00 | Medium | Jul-2026 | On Hold | 2026-08-17 07:00 | Sigma Mfg | bar: 2026-05-05 to 2026-05-30
RJ-148 | 15 | RIM | 1 | 2026-07-02 07:00 | 2026-07-28 07:00 | Medium | Jul-2026 | Released | 2026-08-27 07:00 | Alpha Corp
RJ-149 | 17 | CR2 | 2 | 2026-06-06 07:00 | 2026-08-30 07:00 | High | Aug-2026 | On Hold | 2026-09-29 07:00 | Delta Co
RJ-150 | 17 | RIM | 1 | 2026-07-16 07:00 | 2026-08-10 07:00 | Medium | Aug-2026 | Released | 2026-09-09 07:00 | Gamma Inc
Formulas:
Due Date = IF([Job ID]="","",[Overall End]+30)