## Dashboard
RING PARTS — PRODUCTION PLANNING DASHBOARD
Auto-refreshed on open
PLAN SUMMARY
Total Jobs | Released | On Hold | Cancelled | High Priority | Plan Start | Plan End | Plan Duration (Days)
STAGE CAPACITY ANALYSIS
STAGE LOAD vs CAPACITY SUMMARY | Stage | Machines | Total Load (Hrs) | Capacity (Hrs) | Utilization % | Target |  | 🔴 Bottleneck:
Stage | VTL | 4 |  |  |  | 90% |  | Max Util:
CNC | 8 |  |  |  | 90% | 90% |  | 🟢 Lowest:
ENG | 14 |  |  |  | 90% | 90%
VENT | 8 |  |  |  | 90% | 90% |  | Released Jobs %:
FID | 10 |  |  |  | 90% | 90% |  | High Priority:
QC | 5 |  |  |  | 90% | 90%
90%
JOB TYPE BREAKDOWN
BR1 | BR2 | CR2 | CR3 | CR4 | RIM | BPR
PRIORITY BREAKDOWN |  |  |  | STATUS BREAKDOWN
High | Medium | Low |  | Released | On Hold | Cancelled
BOTTLENECK ALERT
Highest Loaded Stage:
Utilization %:
Lowest Loaded Stage:
JOB TYPE BREAKDOWN
| Type | Count | % of Total
BR1
BR2
CR2
CR3
CR4
RIM
BPR

## Job_Master_Ring
JOB MASTER — RING PARTS
← Type to override auto date
Job ID | Size | Type | No of Parts | Overall Start | Overall End | Priority | End Month | Status | Due Date | Customer | time axis 2026-04-01 to 2026-05-30
RJ-101 | 15 | BR2 |  | 2026-07-17 07:00 | 2026-08-10 07:00 | High |  | Cancelled |  | Gamma Inc
RJ-102 | 54 | BR2 |  | 2026-07-27 07:00 | 2026-10-09 07:00 | Medium |  | Released |  | Gamma Inc
RJ-103 | 42 | CR3 |  | 2026-05-11 07:00 | 2026-07-18 07:00 | Medium |  | Cancelled |  | Delta Co
RJ-104 | 42 | BPR |  | 2026-04-06 07:00 | 2026-05-19 07:00 | Low |  | Released |  | Gamma Inc
RJ-105 | 42 | RIM |  | 2026-07-17 07:00 | 2026-08-28 07:00 | High |  | Cancelled |  | Delta Co
RJ-106 | 9 | CR3 |  | 2026-06-22 07:00 | 2026-08-29 07:00 | High |  | Released |  | Sigma Mfg
RJ-107 | 20 | BR2 |  | 2026-05-10 07:00 | 2026-07-05 07:00 | High |  | On Hold |  | Beta Ltd
RJ-108 | 63 | BR1 |  | 2026-05-12 07:00 | 2026-07-11 07:00 | High |  | On Hold |  | Gamma Inc
RJ-109 | 46 | BR2 |  | 2026-07-17 07:00 | 2026-08-21 07:00 | High |  | On Hold |  | Beta Ltd
RJ-110 | 20 | CR2 |  | 2026-04-27 07:00 | 2026-06-18 07:00 | Low |  | Released |  | Delta Co
RJ-111 | 50 | BR2 |  | 2026-07-15 07:00 | 2026-09-27 07:00 | Low |  | Cancelled |  | Delta Co
RJ-112 | 46 | CR4 |  | 2026-07-14 07:00 | 2026-08-07 07:00 | Low |  | Released |  | Delta Co
RJ-113 | 25 | BR1 |  | 2026-05-09 07:00 | 2026-07-02 07:00 | Low |  | Cancelled |  | Gamma Inc
RJ-114 | 25 | BR2 |  | 2026-07-11 07:00 | 2026-09-20 07:00 | High |  | Cancelled |  | Delta Co
RJ-115 | 34 | CR3 |  | 2026-06-10 07:00 | 2026-08-08 07:00 | High |  | On Hold |  | Gamma Inc
RJ-116 | 15 | CR2 |  | 2026-05-25 07:00 | 2026-08-07 07:00 | High |  | On Hold |  | Sigma Mfg
RJ-117 | 46 | BR2 |  | 2026-05-01 07:00 | 2026-06-29 07:00 | Low |  | On Hold |  | Alpha Corp
RJ-118 | 63 | CR3 |  | 2026-06-11 07:00 | 2026-06-25 07:00 | Medium |  | Cancelled |  | Gamma Inc
RJ-119 | 9 | CR2 |  | 2026-06-02 07:00 | 2026-07-27 07:00 | Low |  | Cancelled |  | Beta Ltd
RJ-120 | 34 | CR4 |  | 2026-05-05 07:00 | 2026-07-20 07:00 | Medium |  | Cancelled |  | Delta Co
RJ-121 | 20 | RIM |  | 2026-04-27 07:00 | 2026-06-24 07:00 | High |  | Released |  | Sigma Mfg
RJ-122 | 34 | CR4 |  | 2026-06-29 07:00 | 2026-07-19 07:00 | Low |  | On Hold |  | Alpha Corp
RJ-123 | 42 | BR1 |  | 2026-04-24 07:00 | 2026-07-08 07:00 | Low |  | Cancelled |  | Gamma Inc
RJ-124 | 20 | RIM |  | 2026-05-25 07:00 | 2026-07-03 07:00 | Low |  | On Hold |  | Alpha Corp
RJ-125 | 25 | BPR |  | 2026-07-01 07:00 | 2026-08-12 07:00 | High |  | Cancelled |  | Alpha Corp
RJ-126 | 34 | BPR |  | 2026-07-08 07:00 | 2026-08-17 07:00 | Low |  | On Hold |  | Sigma Mfg
RJ-127 | 57 | CR3 |  | 2026-05-05 07:00 | 2026-05-30 07:00 | High |  | On Hold |  | Delta Co
RJ-128 | 30 | CR2 |  | 2026-07-21 07:00 | 2026-09-14 07:00 | Medium |  | Cancelled |  | Delta Co
RJ-129 | 15 | BR1 |  | 2026-04-04 07:00 | 2026-04-29 07:00 | High |  | On Hold |  | Beta Ltd
RJ-130 | 57 | CR4 |  | 2026-07-05 07:00 | 2026-09-03 07:00 | Low |  | Released |  | Gamma Inc
RJ-131 | 9 | BPR |  | 2026-04-09 07:00 | 2026-06-15 07:00 | Low |  | Cancelled |  | Sigma Mfg
RJ-132 | 42 | RIM |  | 2026-06-04 07:00 | 2026-08-14 07:00 | High |  | Cancelled |  | Alpha Corp
RJ-133 | 15 | BR1 |  | 2026-07-14 07:00 | 2026-09-18 07:00 | Medium |  | On Hold |  | Alpha Corp
RJ-134 | 42 | BPR |  | 2026-04-20 07:00 | 2026-05-21 07:00 | Low |  | Released |  | Gamma Inc
RJ-135 | 63 | CR4 |  | 2026-06-09 07:00 | 2026-08-28 07:00 | Low |  | Cancelled |  | Gamma Inc
RJ-136 | 50 | CR4 |  | 2026-06-28 07:00 | 2026-07-20 07:00 | Low |  | On Hold |  | Sigma Mfg
RJ-137 | 30 | CR3 |  | 2026-04-16 07:00 | 2026-07-05 07:00 | Low |  | Released |  | Gamma Inc
RJ-138 | 46 | BR1 |  | 2026-06-21 07:00 | 2026-08-12 07:00 | Low |  | Cancelled |  | Alpha Corp
RJ-139 | 15 | BR2 |  | 2026-06-01 07:00 | 2026-08-11 07:00 | High |  | Cancelled |  | Alpha Corp
RJ-140 | 25 | BR1 |  | 2026-04-09 07:00 | 2026-07-02 07:00 | High |  | Cancelled |  | Delta Co
RJ-141 | 17 | BPR |  | 2026-05-13 07:00 | 2026-07-19 07:00 | Medium |  | On Hold |  | Alpha Corp
RJ-142 | 54 | BR1 |  | 2026-06-12 07:00 | 2026-09-08 07:00 | High |  | Released |  | Alpha Corp
RJ-143 | 46 | BR1 |  | 2026-04-28 07:00 | 2026-07-01 07:00 | Medium |  | On Hold |  | Gamma Inc
RJ-144 | 54 | BR1 |  | 2026-06-01 07:00 | 2026-07-29 07:00 | High |  | Released |  | Gamma Inc
RJ-145 | 34 | BR1 |  | 2026-06-15 07:00 | 2026-09-04 07:00 | High |  | On Hold |  | Delta Co
RJ-146 | 54 | CR2 |  | 2026-06-12 07:00 | 2026-08-06 07:00 | Low |  | Released |  | Alpha Corp
RJ-147 | 50 | CR3 |  | 2026-05-04 07:00 | 2026-07-18 07:00 | Medium |  | On Hold |  | Sigma Mfg
RJ-148 | 15 | RIM |  | 2026-07-02 07:00 | 2026-07-28 07:00 | Medium |  | Released |  | Alpha Corp
RJ-149 | 17 | CR2 |  | 2026-06-06 07:00 | 2026-08-30 07:00 | High |  | On Hold |  | Delta Co
RJ-150 | 17 | RIM |  | 2026-07-16 07:00 | 2026-08-10 07:00 | Medium |  | Released |  | Gamma Inc

## OPR_BR1
OPR_BR1
Part No | 1
Size | CNC | SPM | CARVING | EDM | ENG | VENT | FID | QC | Min ID | Max OD
9 | 8 | 6 | 12 | 5 | 2 | 2 | 8 | 4 | 100 | 600
15 | 6 | 8 | 3 | 16 | 6 | 6 | 12 | 5 | 300 | 800
17 | 9 | 16 | 3 | 8 | 8 | 6 | 7 | 5 | 500 | 1000
20 | 10 | 7 | 7 | 21 | 8 | 12 | 21 | 4 | 700 | 1200
25 | 9 | 13 | 6 | 15 | 16 | 14 | 22 | 7 | 900 | 1400
28 | 6 | 24 | 5 | 21 | 14 | 12 | 24 | 7 | 1100 | 1600
30 | 8 | 25 | 4 | 22 | 7 | 9 | 14 | 7 | 1300 | 1800
34 | 11 | 11 | 4 | 14 | 15 | 15 | 13 | 7 | 1500 | 2000
42 | 13 | 23 | 14 | 19 | 15 | 14 | 29 | 5 | 1700 | 2200
46 | 23 | 28 | 18 | 25 | 19 | 15 | 33 | 11 | 1900 | 2400
50 | 16 | 27 | 13 | 37 | 24 | 21 | 29 | 13 | 2100 | 2600
54 | 12 | 37 | 5 | 30 | 18 | 24 | 28 | 6 | 2300 | 2800
57 | 13 | 28 | 13 | 34 | 26 | 21 | 20 | 14 | 2500 | 3000
63 | 14 | 42 | 10 | 23 | 14 | 24 | 36 | 10 | 2700 | 3200
70 | 22 | 45 | 7 | 35 | 30 | 19 | 42 | 14 | 2900 | 3400

## OPR_BR2
OPR_BR2
Part No | 2
Size | CNC | SPM | CARVING | EDM | ENG | VENT | FID | QC | Min ID | Max OD
9 | 2 | 14 | 2 | 14 | 9 | 6 | 13 | 3 | 100 | 600
15 | 5 | 16 | 3 | 13 | 11 | 7 | 9 | 2 | 300 | 800
17 | 4 | 19 | 5 | 8 | 7 | 10 | 15 | 3 | 500 | 1000
20 | 12 | 15 | 7 | 16 | 11 | 8 | 17 | 3 | 700 | 1200
25 | 10 | 19 | 11 | 20 | 11 | 11 | 22 | 6 | 900 | 1400
28 | 17 | 21 | 14 | 19 | 15 | 12 | 14 | 5 | 1100 | 1600
30 | 10 | 21 | 3 | 19 | 14 | 12 | 23 | 8 | 1300 | 1800
34 | 18 | 29 | 14 | 17 | 7 | 12 | 15 | 4 | 1500 | 2000
42 | 11 | 16 | 6 | 34 | 16 | 15 | 34 | 7 | 1700 | 2200
46 | 13 | 24 | 14 | 18 | 17 | 20 | 21 | 8 | 1900 | 2400
50 | 16 | 37 | 16 | 21 | 21 | 12 | 19 | 10 | 2100 | 2600
54 | 16 | 19 | 13 | 27 | 24 | 19 | 26 | 9 | 2300 | 2800
57 | 24 | 30 | 14 | 18 | 21 | 28 | 25 | 8 | 2500 | 3000
63 | 15 | 31 | 8 | 40 | 15 | 17 | 29 | 7 | 2700 | 3200
70 | 21 | 38 | 14 | 35 | 29 | 29 | 46 | 14 | 2900 | 3400

## OPR_CR2
OPR_CR2
Part No | 2
Size | CNC | SPM | CARVING | EDM | ENG | VENT | FID | QC | Min ID | Max OD
9 | 3 | 6 | 11 | 9 | 6 | 5 | 7 | 4 | 100 | 600
15 | 8 | 9 | 6 | 18 | 5 | 6 | 10 | 6 | 300 | 800
17 | 11 | 15 | 3 | 15 | 9 | 8 | 7 | 4 | 500 | 1000
20 | 8 | 15 | 4 | 9 | 11 | 5 | 13 | 4 | 700 | 1200
25 | 12 | 11 | 10 | 8 | 13 | 15 | 17 | 8 | 900 | 1400
28 | 10 | 17 | 8 | 9 | 17 | 13 | 15 | 5 | 1100 | 1600
30 | 7 | 21 | 6 | 19 | 16 | 14 | 27 | 8 | 1300 | 1800
34 | 12 | 20 | 6 | 21 | 12 | 14 | 22 | 8 | 1500 | 2000
42 | 17 | 33 | 8 | 30 | 11 | 20 | 34 | 10 | 1700 | 2200
46 | 13 | 22 | 9 | 16 | 14 | 20 | 28 | 5 | 1900 | 2400
50 | 23 | 33 | 8 | 20 | 14 | 20 | 29 | 11 | 2100 | 2600
54 | 16 | 40 | 6 | 24 | 19 | 21 | 24 | 13 | 2300 | 2800
57 | 19 | 18 | 12 | 26 | 20 | 23 | 26 | 7 | 2500 | 3000
63 | 31 | 25 | 11 | 24 | 23 | 24 | 38 | 12 | 2700 | 3200
70 | 30 | 33 | 15 | 25 | 31 | 17 | 42 | 17 | 2900 | 3400

## OPR_CR3
OPR_CR3
Part No | 3
Size | CNC | SPM | CARVING | EDM | ENG | VENT | FID | QC | Min ID | Max OD
9 | 5 | 5 | 7 | 10 | 9 | 9 | 6 | 4 | 100 | 600
15 | 4 | 6 | 11 | 12 | 10 | 6 | 15 | 5 | 300 | 800
17 | 7 | 18 | 6 | 7 | 8 | 7 | 19 | 6 | 500 | 1000
20 | 7 | 18 | 2 | 17 | 11 | 10 | 18 | 6 | 700 | 1200
25 | 15 | 18 | 12 | 14 | 12 | 13 | 23 | 7 | 900 | 1400
28 | 11 | 21 | 11 | 16 | 6 | 6 | 25 | 6 | 1100 | 1600
30 | 9 | 18 | 4 | 20 | 7 | 14 | 16 | 9 | 1300 | 1800
34 | 11 | 24 | 9 | 19 | 14 | 11 | 12 | 6 | 1500 | 2000
42 | 18 | 17 | 7 | 26 | 11 | 16 | 32 | 9 | 1700 | 2200
46 | 16 | 26 | 13 | 22 | 24 | 12 | 33 | 9 | 1900 | 2400
50 | 12 | 20 | 8 | 28 | 12 | 20 | 28 | 8 | 2100 | 2600
54 | 17 | 37 | 15 | 18 | 20 | 22 | 25 | 6 | 2300 | 2800
57 | 19 | 32 | 15 | 42 | 19 | 17 | 34 | 11 | 2500 | 3000
63 | 18 | 24 | 11 | 22 | 16 | 13 | 36 | 12 | 2700 | 3200
70 | 25 | 26 | 17 | 22 | 28 | 19 | 23 | 14 | 2900 | 3400

## OPR_CR4
OPR_CR4
Part No | 4
Size | CNC | SPM | CARVING | EDM | ENG | VENT | FID | QC | Min ID | Max OD
9 | 5 | 13 | 5 | 9 | 2 | 7 | 13 | 3 | 100 | 600
15 | 12 | 7 | 5 | 5 | 11 | 12 | 13 | 3 | 300 | 800
17 | 4 | 19 | 2 | 17 | 5 | 11 | 6 | 4 | 500 | 1000
20 | 12 | 19 | 14 | 8 | 8 | 13 | 16 | 3 | 700 | 1200
25 | 7 | 17 | 5 | 13 | 11 | 13 | 18 | 7 | 900 | 1400
28 | 11 | 11 | 7 | 11 | 16 | 12 | 22 | 6 | 1100 | 1600
30 | 18 | 14 | 7 | 13 | 17 | 11 | 24 | 9 | 1300 | 1800
34 | 13 | 13 | 7 | 18 | 14 | 12 | 28 | 6 | 1500 | 2000
42 | 22 | 14 | 8 | 20 | 17 | 10 | 27 | 9 | 1700 | 2200
46 | 11 | 30 | 9 | 32 | 15 | 17 | 18 | 5 | 1900 | 2400
50 | 17 | 19 | 9 | 32 | 22 | 14 | 20 | 8 | 2100 | 2600
54 | 18 | 35 | 13 | 23 | 22 | 20 | 31 | 13 | 2300 | 2800
57 | 21 | 38 | 17 | 43 | 26 | 25 | 33 | 7 | 2500 | 3000
63 | 21 | 23 | 12 | 37 | 16 | 28 | 29 | 11 | 2700 | 3200
70 | 34 | 46 | 13 | 41 | 29 | 17 | 49 | 17 | 2900 | 3400

## OPR_RIM
OPR_RIM
Part No | 1
Size | CNC | SPM | CARVING | EDM | ENG | VENT | FID | QC | Min ID | Max OD
9 | 2 | 7 | 7 | 10 | 9 | 9 | 8 | 4 | 100 | 600
15 | 12 | 7 | 9 | 9 | 10 | 12 | 13 | 4 | 300 | 800
17 | 8 | 18 | 5 | 6 | 10 | 5 | 16 | 2 | 500 | 1000
20 | 8 | 12 | 12 | 13 | 14 | 13 | 17 | 5 | 700 | 1200
25 | 14 | 21 | 8 | 21 | 11 | 13 | 24 | 5 | 900 | 1400
28 | 10 | 12 | 13 | 22 | 15 | 17 | 21 | 3 | 1100 | 1600
30 | 16 | 23 | 15 | 24 | 8 | 14 | 24 | 8 | 1300 | 1800
34 | 18 | 13 | 7 | 22 | 17 | 19 | 22 | 4 | 1500 | 2000
42 | 17 | 29 | 14 | 24 | 22 | 9 | 19 | 11 | 1700 | 2200
46 | 22 | 25 | 17 | 21 | 10 | 12 | 30 | 8 | 1900 | 2400
50 | 22 | 25 | 9 | 24 | 21 | 18 | 20 | 6 | 2100 | 2600
54 | 18 | 36 | 14 | 33 | 12 | 16 | 36 | 10 | 2300 | 2800
57 | 20 | 29 | 17 | 39 | 24 | 20 | 22 | 10 | 2500 | 3000
63 | 25 | 20 | 11 | 31 | 25 | 16 | 22 | 11 | 2700 | 3200
70 | 31 | 43 | 12 | 23 | 22 | 17 | 22 | 17 | 2900 | 3400

## OPR_BPR
OPR_BPR
Part No | 2
Size | CNC | SPM | CARVING | EDM | ENG | VENT | FID | QC | Min ID | Max OD
9 | 5 | 13 | 9 | 9 | 4 | 6 | 8 | 2 | 100 | 600
15 | 6 | 12 | 8 | 12 | 12 | 10 | 12 | 6 | 300 | 800
17 | 10 | 12 | 7 | 11 | 4 | 4 | 17 | 3 | 500 | 1000
20 | 14 | 15 | 14 | 18 | 5 | 14 | 7 | 7 | 700 | 1200
25 | 7 | 13 | 13 | 15 | 13 | 16 | 19 | 7 | 900 | 1400
28 | 12 | 20 | 12 | 22 | 14 | 17 | 13 | 6 | 1100 | 1600
30 | 10 | 27 | 6 | 18 | 8 | 17 | 23 | 8 | 1300 | 1800
34 | 19 | 19 | 16 | 22 | 9 | 19 | 13 | 6 | 1500 | 2000
42 | 21 | 26 | 12 | 20 | 20 | 18 | 17 | 10 | 1700 | 2200
46 | 10 | 21 | 3 | 23 | 24 | 17 | 32 | 8 | 1900 | 2400
50 | 15 | 38 | 8 | 29 | 24 | 15 | 27 | 13 | 2100 | 2600
54 | 15 | 29 | 5 | 25 | 16 | 24 | 18 | 7 | 2300 | 2800
57 | 14 | 22 | 9 | 41 | 23 | 13 | 28 | 9 | 2500 | 3000
63 | 29 | 43 | 15 | 40 | 22 | 29 | 31 | 13 | 2700 | 3200
70 | 15 | 34 | 9 | 37 | 15 | 16 | 28 | 12 | 2900 | 3400

## Settings
[7 empty] | Lunch/Tea Break hrs | 0.8
Shift | Category | Start | End | String | Gen Qty | Cont Qty | Net Hrs | Avl hrs
Shift A | General Workman | 7:00 | 15:00 | 07:00 – 15:00 | 40 | 0 | 8 | 7.2 | General Workman | 21.6 | BR1 | 9
Shift B | General Workman | 15:00 | 23:00 | 15:00 – 23:00 | 40 | 0 | 8 | 7.2 | Contract Workman | 22.4 | BR2 | 15
Shift C | General Workman | 23:00 | 7:00 | 23:00 – 07:00 | 40 | 0 | 8 | 7.2 |  |  | CR2 | 17
Shift S1 | Contract Workman | 8:00 | 20:00 | 08:00 – 20:00 | 0 | 60 | 12 | 11.2 | Global Start | 2026-04-01 07:00 | CR3 | 20
Shift S2 | Contract Workman | 20:00 | 8:00 | 20:00 – 08:00 | 0 | 60 | 12 | 11.2 |  |  | CR4 | 25
[11 empty] | RIM | 28
[11 empty] | BPR | 30
34
42
46
50

## Machine_List
Operation | Machine ID | Next PM Date | Dur | Freq | Status | Worker Category | Machine Min ID Limit | Machine Max OD Limit (New) | Compatible Size Range
VTL | VTL-MC-01 | 2026-04-21 | 6 | 4 | Active | General Workman | 100 | 1600 | 9, 15, 17, 20, 25, 28
VTL | VTL-MC-02 | 2027-05-14 | 6 | 4 | Active | General Workman | 600 | 2500 | 20, 25, 28, 30, 34, 42, 46
VTL | VTL-MC-03 | 2026-06-01 | 6 | 4 | Active | General Workman | 800 | 3500 | 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
VTL | VTL-MC-04 | 2027-05-10 | 6 | 4 | Active | General Workman | 1000 | 4500 | 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
SPM | SPM-MC-01 | 2026-09-20 | 6 | 4 | Active | General Workman | 100 | 3500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
SPM | SPM-MC-02 | 2027-03-13 | 6 | 4 | Active | General Workman | 100 | 3500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
SPM | SPM-MC-03 | 2026-03-23 | 6 | 4 | Active | General Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
SPM | SPM-MC-04 | 2026-06-24 | 6 | 4 | Active | General Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
SPM | SPM-MC-05 | 2026-09-06 | 6 | 4 | Active | General Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
SPM | SPM-MC-06 | 2026-06-03 | 6 | 4 | Active | General Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
CARVING | CARVING-MC-01 | 2027-01-31 | 6 | 4 | Active | General Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
CARVING | CARVING-MC-02 | 2026-09-17 | 6 | 4 | Active | General Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
CARVING | CARVING-MC-03 | 2026-10-01 | 6 | 4 | Active | General Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
CARVING | CARVING-MC-04 | 2026-08-03 | 6 | 4 | Active | General Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
CARVING | CARVING-MC-05 | 2026-08-04 | 6 | 4 | Active | General Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
CARVING | CARVING-MC-06 | 2027-01-10 | 6 | 4 | Active | General Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
EDM | EDM-MC-01 | 2026-03-11 | 6 | 4 | Active | General Workman | 100 | 1600 | 9, 15, 17, 20, 25, 28
EDM | EDM-MC-02 | 2026-05-18 | 6 | 4 | Active | General Workman | 100 | 1600 | 9, 15, 17, 20, 25, 28
EDM | EDM-MC-03 | 2026-02-04 | 6 | 4 | Active | General Workman | 100 | 1600 | 9, 15, 17, 20, 25, 28
EDM | EDM-MC-04 | 2026-03-30 | 6 | 4 | Active | General Workman | 100 | 1600 | 9, 15, 17, 20, 25, 28
EDM | EDM-MC-05 | 2026-07-22 | 6 | 4 | Active | General Workman | 100 | 1600 | 9, 15, 17, 20, 25, 28
EDM | EDM-MC-06 | 2026-11-04 | 6 | 4 | Active | General Workman | 100 | 1600 | 9, 15, 17, 20, 25, 28
EDM | EDM-MC-07 | 2026-07-05 | 6 | 4 | Active | General Workman | 100 | 1600 | 9, 15, 17, 20, 25, 28
EDM | EDM-MC-08 | 2026-09-26 | 6 | 4 | Active | General Workman | 100 | 1600 | 9, 15, 17, 20, 25, 28
EDM | EDM-MC-09 | 2026-08-03 | 6 | 4 | Active | General Workman | 300 | 2500 | 15, 17, 20, 25, 28, 30, 34, 42, 46
EDM | EDM-MC-10 | 2027-04-26 | 6 | 4 | Active | General Workman | 300 | 2500 | 15, 17, 20, 25, 28, 30, 34, 42, 46
EDM | EDM-MC-11 | 2026-03-17 | 6 | 4 | Active | General Workman | 300 | 2500 | 15, 17, 20, 25, 28, 30, 34, 42, 46
EDM | EDM-MC-12 | 2026-11-11 | 6 | 4 | Active | General Workman | 300 | 2500 | 15, 17, 20, 25, 28, 30, 34, 42, 46
EDM | EDM-MC-13 | 2026-07-09 | 6 | 4 | Active | General Workman | 300 | 2500 | 15, 17, 20, 25, 28, 30, 34, 42, 46
EDM | EDM-MC-14 | 2027-03-01 | 6 | 4 | Active | General Workman | 300 | 2500 | 15, 17, 20, 25, 28, 30, 34, 42, 46
EDM | EDM-MC-15 | 2026-12-01 | 6 | 4 | Active | General Workman | 300 | 2500 | 15, 17, 20, 25, 28, 30, 34, 42, 46
EDM | EDM-MC-16 | 2026-03-24 | 6 | 4 | Active | General Workman | 800 | 3500 | 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
EDM | EDM-MC-17 | 2027-04-27 | 6 | 4 | Active | General Workman | 800 | 3500 | 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
EDM | EDM-MC-18 | 2026-07-22 | 6 | 4 | Active | General Workman | 800 | 3500 | 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
EDM | EDM-MC-19 | 2026-08-29 | 6 | 4 | Active | General Workman | 800 | 3500 | 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
EDM | EDM-MC-20 | 2026-01-18 | 6 | 4 | Active | General Workman | 800 | 3500 | 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
EDM | EDM-MC-21 | 2027-03-30 | 6 | 4 | Active | General Workman | 800 | 3500 | 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
EDM | EDM-MC-22 | 2026-08-05 | 6 | 4 | Active | General Workman | 800 | 3500 | 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
EDM | EDM-MC-23 | 2026-10-29 | 6 | 4 | Active | General Workman | 1000 | 4500 | 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
EDM | EDM-MC-24 | 2026-03-16 | 6 | 4 | Active | General Workman | 1000 | 4500 | 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
EDM | EDM-MC-25 | 2026-03-17 | 6 | 4 | Active | General Workman | 1000 | 4500 | 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
EDM | EDM-MC-26 | 2026-06-29 | 6 | 4 | Active | General Workman | 1000 | 4500 | 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
EDM | EDM-MC-27 | 2026-06-15 | 6 | 4 | Active | General Workman | 1000 | 4500 | 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
EDM | EDM-MC-28 | 2026-06-09 | 6 | 4 | Active | General Workman | 1000 | 4500 | 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
EDM | EDM-MC-29 | 2027-04-16 | 6 | 4 | Active | General Workman | 1000 | 4500 | 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
EDM | EDM-MC-30 | 2026-03-25 | 6 | 4 | Active | General Workman | 1000 | 4500 | 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
ENG | ENG-MC-01 | 2026-03-09 | 6 | 4 | Active | General Workman | 100 | 2000 | 9, 15, 17, 20, 25, 28, 30, 34
ENG | ENG-MC-02 | 2026-07-27 | 6 | 4 | Active | General Workman | 100 | 2000 | 9, 15, 17, 20, 25, 28, 30, 34
ENG | ENG-MC-03 | 2027-02-15 | 6 | 4 | Active | General Workman | 100 | 2200 | 9, 15, 17, 20, 25, 28, 30, 34, 42
ENG | ENG-MC-04 | 2027-03-04 | 6 | 4 | Active | General Workman | 100 | 2200 | 9, 15, 17, 20, 25, 28, 30, 34, 42
ENG | ENG-MC-05 | 2026-01-27 | 6 | 4 | Active | General Workman | 100 | 2000 | 9, 15, 17, 20, 25, 28, 30, 34
ENG | ENG-MC-06 | 2026-02-21 | 6 | 4 | Active | General Workman | 600 | 3200 | 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63
ENG | ENG-MC-07 | 2026-09-07 | 6 | 4 | Active | General Workman | 600 | 3200 | 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63
ENG | ENG-MC-08 | 2026-12-27 | 6 | 4 | Active | General Workman | 600 | 3200 | 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63
ENG | ENG-MC-09 | 2027-03-25 | 6 | 4 | Active | General Workman | 600 | 3000 | 20, 25, 28, 30, 34, 42, 46, 50, 54, 57
ENG | ENG-MC-10 | 2026-12-21 | 6 | 4 | Active | General Workman | 600 | 3000 | 20, 25, 28, 30, 34, 42, 46, 50, 54, 57
ENG | ENG-MC-11 | 2027-05-10 | 6 | 4 | Active | General Workman | 600 | 3000 | 20, 25, 28, 30, 34, 42, 46, 50, 54, 57
ENG | ENG-MC-12 | 2027-03-08 | 6 | 4 | Active | General Workman | 600 | 4000 | 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
ENG | ENG-MC-13 | 2026-12-15 | 6 | 4 | Active | General Workman | 600 | 4000 | 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
ENG | ENG-MC-14 | 2026-07-16 | 6 | 4 | Active | General Workman | 600 | 4000 | 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
VENT | VENT-MC-01 | 2026-07-27 | 6 | 4 | Active | Contract Workman | 100 | 1600 | 9, 15, 17, 20, 25, 28
VENT | VENT-MC-02 | 2026-06-18 | 6 | 4 | Active | Contract Workman | 100 | 1600 | 9, 15, 17, 20, 25, 28
VENT | VENT-MC-03 | 2026-02-01 | 6 | 4 | Active | Contract Workman | 100 | 1600 | 9, 15, 17, 20, 25, 28
VENT | VENT-MC-04 | 2026-08-21 | 6 | 4 | Active | Contract Workman | 300 | 3500 | 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
VENT | VENT-MC-05 | 2027-01-07 | 6 | 4 | Active | Contract Workman | 300 | 3500 | 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
VENT | VENT-MC-06 | 2026-11-21 | 6 | 4 | Active | Contract Workman | 300 | 3500 | 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
VENT | VENT-MC-07 | 2026-07-31 | 6 | 4 | Active | Contract Workman | 500 | 4000 | 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
VENT | VENT-MC-08 | 2026-04-26 | 6 | 4 | Active | Contract Workman | 500 | 4000 | 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
FID | FID-MC-01 | 2026-03-25 | 6 | 4 | Active | Contract Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
FID | FID-MC-02 | 2026-04-30 | 6 | 4 | Active | Contract Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
FID | FID-MC-03 | 2027-04-06 | 6 | 4 | Active | Contract Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
FID | FID-MC-04 | 2026-10-23 | 6 | 4 | Active | Contract Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
FID | FID-MC-05 | 2027-02-13 | 6 | 4 | Active | Contract Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
FID | FID-MC-06 | 2026-03-07 | 6 | 4 | Active | Contract Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
FID | FID-MC-07 | 2027-01-15 | 6 | 4 | Active | Contract Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
FID | FID-MC-08 | 2026-11-02 | 6 | 4 | Active | Contract Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
FID | FID-MC-09 | 2026-05-23 | 6 | 4 | Active | Contract Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
FID | FID-MC-10 | 2027-04-06 | 6 | 4 | Active | Contract Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
QC | QC-MC-01 | 2027-05-11 | 6 | 4 | Active | General Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
QC | QC-MC-02 | 2026-04-03 | 6 | 4 | Active | General Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
QC | QC-MC-03 | 2026-05-30 | 6 | 4 | Active | General Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
QC | QC-MC-04 | 2026-06-22 | 6 | 4 | Active | General Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
QC | QC-MC-05 | 2026-12-17 | 6 | 4 | Active | General Workman | 100 | 4500 | 9, 15, 17, 20, 25, 28, 30, 34, 42, 46, 50, 54, 57, 63, 70
CNC | CNC-MC-01 | 2026-07-01 | 6 | 4 | Active | General Workman | 100 | 4500 | All Sizes
CNC | CNC-MC-02 | 2026-07-31 | 6 | 4 | Active | General Workman | 100 | 4500 | All Sizes
CNC | CNC-MC-03 | 2026-08-30 | 6 | 4 | Active | General Workman | 100 | 4500 | All Sizes
CNC | CNC-MC-04 | 2026-09-29 | 6 | 4 | Active | General Workman | 100 | 4500 | All Sizes
CNC | CNC-MC-05 | 2026-10-29 | 6 | 4 | Active | General Workman | 100 | 4500 | All Sizes
CNC | CNC-MC-06 | 2026-11-28 | 6 | 4 | Active | General Workman | 100 | 4500 | All Sizes
CNC | CNC-MC-07 | 2026-12-28 | 6 | 4 | Active | General Workman | 100 | 4500 | All Sizes
CNC | CNC-MC-08 | 2027-01-27 | 6 | 4 | Active | General Workman | 100 | 4500 | All Sizes

## Lists
9
15
17
20
25
28
30
34
42
46
50
54
57
63
70

## CNC_Plan
CNC — Monthly Load vs Capacity
[75 empty] | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27
Job ID | Size | Type | Parts | Allocated Machine | Worker | PM Date | PM Hrs | Override | Start Date | Unit CT | Total Load | End Date | Shift ¦ Time | Machine Helper (Pick Compatible) | [59 empty] | Load (Hrs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | time axis 2026-04-01 to 2026-05-30
[74 empty] | Capacity (Hrs) | 5184 | 5356.8 | 5184 | 5356.8 | 5356.8 | 5184 | 5356.8 | 5184 | 5356.8 | 5356.8

## ENG_Plan
ENG — Monthly Load vs Capacity
[75 empty] | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27
Job ID | Size | Type | Parts | Allocated Machine | Worker | PM Date | PM Hrs | Override | Start Date | Unit CT | Total Load | End Date | Shift ¦ Time | Machine Helper (Pick Compatible) | [59 empty] | Load (Hrs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | time axis 2026-04-01 to 2026-05-30
[74 empty] | Capacity (Hrs) | 9072 | 9374.4 | 9072 | 9374.4 | 9374.4 | 9072 | 9374.4 | 9072 | 9374.4 | 9374.4

## VENT_Plan
VENT — Monthly Load vs Capacity
[75 empty] | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27
Job ID | Size | Type | Parts | Allocated Machine | Worker | PM Date | PM Hrs | Override | Start Date | Unit CT | Total Load | End Date | Shift ¦ Time | Machine Helper (Pick Compatible) | [59 empty] | Load (Hrs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | time axis 2026-04-01 to 2026-05-30
[74 empty] | Capacity (Hrs) | 5184 | 5356.8 | 5184 | 5356.8 | 5356.8 | 5184 | 5356.8 | 5184 | 5356.8 | 5356.8

## FID_Plan
FID — Monthly Load vs Capacity
[75 empty] | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27
Job ID | Size | Type | Parts | Allocated Machine | Worker | PM Date | PM Hrs | Override | Start Date | Unit CT | Total Load | End Date | Shift ¦ Time | Machine Helper (Pick Compatible) | [59 empty] | Load (Hrs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | time axis 2026-04-01 to 2026-05-30
[74 empty] | Capacity (Hrs) | 6480 | 6696 | 6480 | 6696 | 6696 | 6480 | 6696 | 6480 | 6696 | 6696

## QC_Plan
QC — Monthly Load vs Capacity
[75 empty] | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27
Job ID | Size | Type | Parts | Allocated Machine | Worker | PM Date | PM Hrs | Override | Start Date | Unit CT | Total Load | End Date | Shift ¦ Time | Machine Helper (Pick Compatible) | [59 empty] | Load (Hrs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | time axis 2026-04-01 to 2026-05-30
[74 empty] | Capacity (Hrs) | 3240 | 3348 | 3240 | 3348 | 3348 | 3240 | 3348 | 3240 | 3348 | 3348